## Project_Status_Next-CMSPE_2026
Project Status
Division |  |  | All
Project Manager |  |  | All
Projects |  |  | All
Milestones |  |  | Next CMS/PE
(Planned:N Committed, In Queue:Y In Process:Y On Hold:Y Completed:N Cancelled:N)
| Project Name | Project Type | Project UID | Project Status | Description | Due Date | Projected Date | Delay | Buffer Consumed | Longest Chain Complete | Penetrating Task | Last Update | Help Needed | Comments | Buffer Trend | Remaining Float
R | T44_February_2019 2Tier! |  | 299 | In Process | Project End | 2023-06-09 | 2027-08-31 | 1544d | 32000%, 320d/1d | 0%, 0d/263d | IMS-Release to A0=Induction | 2026-08-27 04:30 |  |  | NA | -1103d
R | AutomationChainPanrlSelectionProject! |  | 2764 | In Process | Project End | 2023-06-11 | 2027-08-31 | 1542d | 32000%, 320d/1d | 0%, 0d/263d | IMS-Release to A0=Induction | 2026-08-27 04:32 |  |  | NA | -1103d
R | Gama2! |  | 997 | In Process | Project End | 2023-09-02 | 2026-07-30 | 1062d | 32000%, 320d/1d | -575%, -6d/1d | t1 | 2026-07-16 03:25 |  |  | NA | -1362d
R | T44_February_2019! |  | 294 | In Process | Project End | 2023-05-17 | 2025-08-12 | 818d | 32000%, 320d/1d | 0%, 0d/247d | IMS-Release to A0=Induction | 2022-08-04 09:57 |  |  | NA
R | ACE Demo detiled tasks 240822_RZ! |  | 461 | In Process | Project End | 2023-10-17 | 2025-06-10 | 602d | 32000%, 320d/1d | 0%, 0d/196d | Develop System HLD | 2026-07-14 23:22 |  |  | NA
R | ACE Demo 240822! |  | 413 | In Process | Project End | 2023-10-17 | 2025-06-09 | 601d | 32000%, 320d/1d | 0%, 0d/195d | Develop System HLD | 2024-09-09 01:04 |  |  | NA | -429d
R | ACE Demo 240822_RZ! |  | 460 | In Process | Project End | 2023-10-17 | 2025-06-09 | 601d | 32000%, 320d/1d | 0%, 0d/195d | Develop System HLD | 2024-09-09 01:15 |  |  | NA
R | ACE Demo 240822 updated! |  | 542 | Committed, In Queue | Project End | 2023-10-17 | 2025-06-06 | 598d | 32000%, 320d/1d | 0%, 0d/194d | Develop System HLD | 2024-09-09 01:16 |  |  | NA | -428d
R | V1 S05 1 85! |  | 1108 | Committed, In Queue | Project End | 2024-02-04 | 2024-11-28 | 298d | 29760%, 298d/1d | 0%, 0d/80d | Pre Repair | 2024-01-19 03:16 |  |  | NA | -263d
R | V1 S06 1 86! |  | 1109 | In Process | Project End | 2024-02-18 | 2024-11-28 | 284d | 28360%, 284d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:31 |  |  | NA | -263d
R | V1 S07 1 81 (Descoped)! |  | 1110 | Committed, In Queue | Project End | 2024-04-21 | 2024-11-28 | 221d | 22060%, 221d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -263d
R | 81 pre descoping! |  | 1128 | Committed, In Queue | Project End | 2024-05-13 | 2024-12-18 | 219d | 21860%, 219d/1d | 0%, 0d/100d | Pre Repair | 2023-11-28 07:53 |  |  | NA | -213d
R | V1 S08 1 82! |  | 1111 | In Process | Project End | 2024-06-02 | 2024-11-28 | 179d | 17860%, 179d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -263d
R | V1 S09 1 87! |  | 1112 | In Process | Project End | 2024-07-14 | 2024-11-28 | 137d | 13660%, 137d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -263d
R | Andrea Test Plan! |  | 103 | On Hold | Project End | 2021-10-12 | 2022-04-14 | 184d | 12300%, 123d/1d | 3%, 1d/32d | First Task | 2021-11-17 09:11 |  |  | NA | -132d
R | Project 01! |  | 838 | In Process | Project End | 2023-04-27 | 2024-09-22 | 514d | 10302%, 515d/5d | 0%, 0d/9d | T1 | 2026-07-09 05:58 |  |  | NA | -497d
R | V1 S11 1 89! |  | 1114 | In Process | Project End | 2024-08-25 | 2024-11-28 | 95d | 9460%, 95d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -263d
R | SUBTASK-RTS-WIP! |  | 1163 | In Process | Project End | 2024-01-02 | 2024-09-16 | 258d | 9200%, 184d/2d | 0%, 0d/4d | Task-1 | 2026-07-13 00:16 |  |  | NA | -184d
R | REEL TEST! |  | 1030 | In Process | Project End | 2023-10-19 | 2024-09-19 | 336d | 7979%, 239d/3d | 0%, 0d/5d | P&IDs (PTH 1to 4) | 2024-09-09 01:02 |  |  | NA | -240d
R | Test-Chains! |  | 1204 | In Process | Project End | 2024-03-01 | 2024-09-13 | 196d | 7000%, 140d/2d | 0%, 0d/3d | T1 | 2024-02-25 22:48 |  |  | NA | -140d
R | 1+Task! |  | 557 | In Process | Project End | 2023-11-08 | 2024-09-25 | 322d | 5500%, 275d/5d | 0%, 0d/10d | T1 | 2026-07-15 05:40 |  |  | NA | -570d
R | V1 S12 1 90! |  | 1115 | Committed, In Queue | Project End | 2024-10-06 | 2024-11-28 | 53d | 5260%, 53d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:30 |  |  | NA | -263d
R | ACE Demo 2-Tier! |  | 1300 | In Process | Deliver MC | 2025-03-06 | 2025-05-19 | 74d | 5200%, 52d/1d | 0%, 0d/180d | Develop MC HLD | 2024-09-09 01:03 |  |  | NA | -414d
R | Test-Purchaing task! |  | 1192 | In Process | Project End | 2024-02-27 | 2024-09-18 | 204d | 4874%, 146d/3d | -4%, 0d/5d | Task-1 | 2024-02-15 23:22 |  |  | NA | -146d
R | SUBTASK-RTS-NETWORK! |  | 1162 | In Process | Project End | 2024-01-09 | 2024-09-23 | 258d | 4600%, 184d/4d | 0%, 0d/7d | Task-1 | 2024-09-09 01:03 |  |  | NA | -184d
R | v2_22_DEV! |  | 483 | In Process | Project End | 2023-02-02 | 2024-10-01 | 607d | 3660%, 439d/12d | 50%, 11d/23d | ELK | 2026-07-16 05:31 |  |  | NA | -538d
R | Full Kit Test CCGAN-2483! |  | 1277 | In Process | Project End | 2024-08-01 | 2026-08-24 | 753d | 3580%, 537d/15d | 0%, 0d/30d | T1 | 2026-08-20 21:56 |  |  | NA | -558d
R | Test Project 1! |  | 64 | On Hold | Project End | 2021-10-11 | 2025-01-03 | 1180d | 3376%, 844d/25d | 0%, 0d/60d | Task 1 | 2021-11-17 09:11 |  |  | NA | -844d
R | Penchard v1! |  | 215 | In Process | Project End | 2022-04-27 | 2024-12-12 | 960d | 2983%, 686d/23d | 0%, 0d/46d | Communication and buy in ready | 2022-01-21 08:18 |  |  | NA | -686d
R | test-purchasing2! |  | 1193 | In Process | Project End | 2024-03-06 | 2024-09-26 | 204d | 2920%, 146d/5d | 0%, 0d/9d | Task-1 | 2024-09-09 01:03 |  |  | NA | -146d
R | Test 2_Airnostrum! |  | 1130 | In Process | Project End | 2023-12-26 | 2024-10-07 | 286d | 2914%, 204d/7d | 0%, 0d/14d | Precheck_Priority Tasks | 2026-08-21 08:00 |  |  | NA | -217d
R | 169425! |  | 118 | In Process | Project End | 2022-05-09 | 2024-12-20 | 956d | 2735%, 684d/25d | 0%, 0d/50d | Purge Fuel Cells | 2024-09-09 01:14 |  |  | NA
R | AutomationNewUIConfigProject! |  | 2761 | In Process | Project End | 2026-08-21 | 2026-09-18 | 28d | 2067%, 21d/1d | 100%, -1d/0d | FK-Task | 2026-09-18 07:11 |  |  | NA | -20d
R | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA! |  | 723 | In Process | Project End | 2023-02-14 | 2024-12-17 | 672d | 1998%, 480d/24d | 0%, 0d/48d | Engineering - Select Design Engineer | 2023-02-14 10:47 |  |  | NA | -480d
R | TestAutoRollup! |  | 1018 | In Process | Project End | 2023-09-26 | 2024-10-07 | 377d | 1847%, 277d/15d | 53%, 16d/30d | T1 | 2024-09-09 01:17 |  |  | NA | -269d
R | W9585 - 9917-11-100 2-Tier Example! |  | 724 | In Process | Project End | 2023-05-24 | 2024-12-17 | 573d | 1703%, 408d/24d | 0%, 0d/48d | Engineering | 2026-06-22 21:56 |  |  | NA | -409d
R | Blank! |  | 1031 | In Process | Project End | 2023-12-06 | 2024-10-30 | 329d | 1580%, 237d/15d | 14%, 4d/29d | T1 | 2024-09-09 01:02 |  |  | NA | -241d
R | ERP en ABC! |  | 1238 | In Process | Salida a VIVO | 2024-10-02 | 2026-12-17 | 806d | 1311%, 577d/44d | 2%, 2d/87d | Activaciones Iniciales | 2026-07-16 05:33 |  |  | NA | -578d
R | TEST_Airnostrum! |  | 1096 | In Process | Project End | 2024-02-02 | 2024-11-29 | 301d | 1247%, 212d/17d | -21%, -7d/33d | Precheck_Priority Tasks | 2024-09-09 01:15 |  |  | NA | -256d
R | Pluto! |  | 538 | On Hold | Project End | 2023-04-16 | 2025-02-20 | 676d | 1208%, 483d/40d | 0%, 0d/79d | Preparatory work | 2024-09-09 01:15 |  |  | NA | -483d
R | Jupitor! |  | 540 | Committed, In Queue | Project End | 2023-04-24 | 2025-02-20 | 668d | 1195%, 478d/40d | 0%, 0d/79d | Preparatory work | 2024-09-09 01:02 |  |  | NA | -478d
R | Mars! |  | 536 | Committed, In Queue | Project End | 2023-05-08 | 2025-02-20 | 654d | 1170%, 468d/40d | 0%, 0d/79d | Preparatory work | 2024-09-09 01:16 |  |  | NA | -468d
R | Neptune! |  | 539 | Committed, In Queue | Project End | 2023-05-20 | 2025-02-20 | 642d | 1145%, 458d/40d | 0%, 0d/79d | Preparatory work | 2024-09-09 01:01 |  |  | NA | -458d
R | V1 S13 1 92! |  | 1131 | Committed, In Queue | Project End | 2024-11-17 | 2024-11-28 | 11d | 1060%, 11d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -263d
R | automation_test_10158! |  | 2732 | In Process | Project End | 2026-07-14 | 2026-07-24 | 10d | 800%, 8d/1d | 0%, 0d/1d | task | 2026-07-14 23:46 |  |  | NA | -9d
R | EC-MRI! |  | 1311 | In Process | Project End | 2024-07-18 | 2024-10-08 | 82d | 700%, 70d/10d | 0%, 0d/16d | FK1 | 2026-06-22 22:14 |  |  | NA | -72d
R | nr1! |  | 1253 | Committed, In Queue | Project End | 2024-09-03 | 2024-09-11 | 8d | 600%, 6d/1d | 0%, 0d/2d | t1 | 2024-08-30 06:38 |  |  | NA | -6d
R | Test Part 1! |  | 1127 | In Process | Project End | 2024-05-31 | 2025-04-03 | 307d | 541%, 216d/40d | -7%, -7d/100d | Team Kick Off Meeting | 2023-11-27 13:03 | Waiting for Resources |  | NA | -219d
R | S020026A! |  | 107 | On Hold | Project End | 2023-10-31 | 2027-01-14 | 1171d | 537%, 852d/159d | 11%, 58d/530d | PT-Receipt and clearance of heater | 2021-11-17 09:11 |  |  | NA | -837d
R | Gama1! |  | 996 | In Process | Project End | 2023-08-30 | 2023-09-15 | 16d | 400%, 12d/3d | 0%, 0d/5d | Task1 | 2023-09-06 23:09 |  |  | NA | -12d
R | Test11! |  | 1209 | In Process | Project End | 2024-08-19 | 2025-03-01 | 194d | 334%, 167d/50d | 0%, 0d/100d | BE Main Equipment | 2024-02-26 13:11 |  |  | NA | -167d
R | PT Testing! |  | 1132 | In Process | Project End | 2024-09-28 | 2024-11-07 | 40d | 333%, 40d/12d | 0%, 0d/48d | Kickoff | 2024-07-31 09:16 |  |  | NA
R | Navy Cloud Pilot Deployment! |  | 1050 | In Process | Project End | 2024-03-01 | 2024-05-16 | 76d | 314%, 66d/21d | 56%, 23d/41d | Phase 3 - Concerto Setup | 2024-04-10 01:03 |  |  | NA | -54d
R | Phase 175 Only! |  | 49 | On Hold | Project End | 2021-05-06 | 2022-07-04 | 424d | 315%, 301d/96d | 0%, 0d/191d | Zone 4 Section 2: Purchase, Build, Ship | 2021-07-08 15:32 |  |  | NA | -302d
R | Earth! |  | 534 | Committed, In Queue | Project End | 2023-04-14 | 2023-10-06 | 175d | 313%, 125d/40d | 0%, 0d/79d | Preparatory work | 2023-04-25 01:01 |  |  | NA | -125d
R | Hydrogen R&D Work! |  | 98 | On Hold | Project End | 2021-09-30 | 2021-11-22 | 53d | 307%, 43d/14d | 40%, 11d/27d | Fin Fan Cooler and CCW Pump Data Complete | 2021-11-17 09:11 |  |  | NA | -37d
R | Test Automation Project 2! |  | 2725 | In Process | Project End | 2026-07-03 | 2027-02-03 | 215d | 306%, 153d/50d | 0%, 0d/100d | T1 | 2026-07-22 05:02 |  |  | NA | -154d
R | DP273! |  | 1354 | In Process | Project End | 2024-08-15 | 2028-03-05 | 1298d | 305%, 1110d/364d | 0%, 0d/728d | Final Tests | 2024-08-15 22:49 |  | Microcleanliness retest Failed 2/29, EMT is reviewing | NA | -977d
R | testM! |  | 906 | In Process | Project End | 2023-06-27 | 2023-06-30 | 3d | 300%, 3d/1d | 0%, 0d/1d | T1 | 2023-06-27 04:27 |  |  | NA | -3d
R | Test Automation Project 3! |  | 2726 | In Process | Project End | 2026-07-02 | 2027-01-26 | 208d | 296%, 148d/50d | 0%, 0d/100d | T1 | 2026-07-01 23:27 |  |  | NA | -148d
R | WMS en RETAIL! |  | 1239 | In Process | Salida a VIVO | 2024-09-30 | 2025-03-05 | 156d | 257%, 113d/44d | 2%, 2d/87d | Activaciones Iniciales | 2024-09-09 01:13 |  |  | NA | -112d
R | AutomationTaskEditingFieldProject! |  | 2763 | In Process | Project End | 2026-08-27 | 2026-09-03 | 7d | 233%, 5d/2d | 8%, 0d/4d | FK-Task | 2026-08-27 01:48 |  |  | NA | -6d
R | AutomatiionFullKitDetailPopUpProject! |  | 2758 | In Process | Project End | 2026-08-19 | 2026-08-21 | 2d | 200%, 2d/1d | 0%, 0d/2d | FK-Task | 2026-09-18 06:37 |  |  | NA | -2d
R | Automation_Checklst_Project! |  | 2740 | In Process | Project End | 2026-07-20 | 2026-07-22 | 2d | 200%, 2d/1d | 0%, 0d/2d | T1 | 2026-07-23 04:02 |  |  | NA | -2d
R | Automation_UILayout! |  | 2767 | In Process | Project End | 2026-08-28 | 2026-09-01 | 4d | 200%, 2d/1d | -100%, -1d/1d | Task | 2026-08-27 22:44 |  |  | NA | -2d
R | AutomationPrivilegeTest! |  | 2773 | In Process | Project End | 2026-09-09 | 2026-09-15 | 6d | 200%, 4d/2d | 0%, 0d/3d | test | 2026-09-08 20:16 |  |  | NA | -4d
R | Integration Example Execution! |  | 354 | In Process | Project End | 2022-08-31 | 2022-09-02 | 2d | 200%, 2d/1d | 0%, 0d/34d | B1 | 2022-07-13 10:41 |  |  | NA | -2d
R | ACE Execution! |  | 271 | In Process | Project End | 2023-07-07 | 2024-03-12 | 249d | 168%, 180d/108d | 4%, 8d/215d | Develop MC HLD | 2022-05-15 23:17 |  |  | NA | -177d
R | Automation Project ReadyToStart! |  | 2734 | In Process | Project End | 2026-07-17 | 2026-07-24 | 7d | 167%, 5d/3d | 0%, 0d/6d | Task1 | 2026-07-28 03:18 |  |  | NA | -5d
R | V1 S10 1 88! |  | 1113 | Committed, In Queue | Project End | 2024-11-26 | 2024-11-28 | 2d | 160%, 2d/1d | 0%, 0d/80d | Pre Repair | 2023-12-12 17:33 |  |  | NA | -263d
R | TestIMS! |  | 1368 | In Process | Project End | 2024-09-18 | 2024-09-27 | 9d | 140%, 7d/5d | 0%, 0d/10d | T1 | 2024-08-29 00:41 |  |  | NA | -7d
R | Automation Project InlineEdit_DD1! |  | 2736 | In Process | Project End | 2026-07-22 | 2026-07-28 | 6d | 133%, 4d/3d | 0%, 0d/6d | Task1 | 2026-07-29 01:48 |  |  | NA | -5d
R | Glow Lab! |  | 1275 | In Process | Project End | 2024-09-12 | 2024-09-27 | 15d | 132%, 25d/19d | 73%, 28d/38d | Parallel run of MRP toolset | 2024-08-22 02:37 |  |  | NA | -84d
R | Medifab - RFID implementation plan! |  | 1232 | In Process | Project End | 2024-10-22 | 2024-11-21 | 30d | 113%, 36d/32d | 58%, 49d/85d | Configure and Test two-way integration between Odoo and MWE | 2024-09-02 14:14 |  |  | NA | -22d
R | Automation Project QuickAccess_RunBM! |  | 2741 | In Process | Project End | 2026-07-24 | 2026-07-28 | 4d | 100%, 2d/2d | 0%, 0d/3d | Task1 | 2026-07-22 07:25 |  |  | NA | -2d
R | Automation_Edit_Checkout_Validation! |  | 2772 | In Process | Project End | 2026-09-05 | 2026-09-08 | 3d | 100%, 1d/1d | 0%, 0d/1d | FK-Task | 2026-09-04 18:07 |  |  | NA | -1d
R | Automation_FK_Pred_Test! |  | 2730 | In Process | Project End | 2026-07-10 | 2026-07-13 | 3d | 100%, 1d/1d | 0%, 0d/1d | FK-Task | 2026-07-10 04:25 |  |  | NA | -1d
R | Automation_FKStatusTransitionProject! |  | 2751 | In Process | Project End | 2026-08-06 | 2026-08-07 | 1d | 100%, 1d/1d | 0%, 0d/1d | FK-Task | 2026-09-18 04:55 |  |  | NA | -1d
R | Automation_General_UI_TEST! |  | 2746 | In Process | Project End | 2026-07-30 | 2026-07-31 | 1d | 100%, 1d/1d | 0%, 0d/1d | FK-Task | 2026-09-18 03:12 |  |  | NA | -1d
R | Automation_HelpNeeded_Project! |  | 2744 | In Process | Project End | 2026-07-21 | 2026-07-22 | 1d | 100%, 1d/1d | 0%, 0d/1d | HelpNeed Task | 2026-07-23 03:52 |  |  | NA | -1d
R | Automation_Privilege_Admin! |  | 2774 | In Process | Project End | 2026-09-09 | 2026-09-10 | 1d | 100%, 1d/1d | 0%, 0d/1d | Task | 2026-09-08 23:25 |  |  | NA | -1d
R | Automation_Test_Status_Update_Project! |  | 2735 | In Process | Project End | 2026-07-16 | 2026-07-17 | 1d | 100%, 1d/1d | 0%, 0d/1d | Status Automation - 2 | 2026-09-15 05:41 |  |  | NA | -43d
R | AutomationEditNetworkProject! |  | 2770 | In Process | Project End | 2026-09-18 | 2026-09-21 | 3d | 100%, 1d/1d | 0%, 0d/1d | Task | 2026-09-18 03:34 |  | db-persist-check-1789727793246 | NA | -15d
R | AutomationEntryPointAccess! |  | 2769 | In Process | Project End | 2026-09-01 | 2026-09-02 | 1d | 100%, 1d/1d | 0%, 0d/2d | task | 2026-08-30 22:54 |  |  | NA | -2d
R | AutomationRealTimeUpdateProject! |  | 2757 | In Process | Project End | 2026-08-18 | 2026-08-19 | 1d | 100%, 1d/1d | 0%, 0d/1d | FK-Task | 2026-09-18 06:24 |  |  | NA | -2d
R | test6578! |  | 2743 | In Process | Project End | 2026-07-21 | 2026-07-22 | 1d | 100%, 1d/1d | 0%, 0d/1d | t1 | 2026-07-20 23:20 |  |  | NA | -1d
R | EU PIM G! |  | 69 | On Hold | Project End | 2025-01-07 | 2025-02-07 | 31d | 96%, 27d/28d | 0%, 0d/103d | (S41,S42,S43) PMDM Chip. Transl. Serv TP Integration Test | 2024-07-31 09:33 |  |  | NA
R | MetaBook! |  | 207 | In Process | Project End | 2022-06-08 | 2022-07-26 | 48d | 97%, 35d/36d | 3%, 2d/71d | Team | 2022-01-11 05:04 |  |  | NA | -34d
R | nr! |  | 1252 | Committed, In Queue | Project End | 2024-09-18 | 2024-09-22 | 4d | 80%, 3d/4d | -25%, -1d/6d | t1 | 2024-08-30 06:38 |  |  | NA | -3d
R | V1 S14 1 91! |  | 1117 | Committed, In Queue | Project End | 2024-12-29 | 2024-12-30 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -295d
R | V1 S15 1 93! |  | 1118 | Committed, In Queue | Project End | 2025-02-09 | 2025-02-10 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -337d
R | V1 S16 1 94! |  | 1119 | Committed, In Queue | Project End | 2025-03-23 | 2025-03-24 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -379d
R | V1 S17 1 95! |  | 1120 | Committed, In Queue | Project End | 2025-08-25 | 2025-08-26 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-19 03:53 |  |  | NA | -534d
R | V1 S18 1 96! |  | 1121 | Committed, In Queue | Project End | 2025-05-04 | 2025-05-05 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -421d
R | V1 S19 1 97! |  | 1122 | Committed, In Queue | Project End | 2025-06-08 | 2025-06-09 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -456d
R | V1 S20 1 98! |  | 1123 | Committed, In Queue | Project End | 2025-07-20 | 2025-07-21 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -498d
R | V1 S21 1 99! |  | 1125 | Committed, In Queue | Project End | 2025-10-05 | 2025-10-06 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -575d
R | V2 S01 1 80! |  | 1135 | Committed, In Queue | Project End | 2026-03-01 | 2026-03-02 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:16 |  |  | NA | -722d
R | V2 S01 1 83! |  | 1124 | Committed, In Queue | Project End | 2025-11-03 | 2025-11-04 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2024-01-19 03:53 |  |  | NA | -604d
R | V2 S02 2 79! |  | 1129 | Committed, In Queue | Project End | 2026-01-03 | 2026-01-04 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2024-01-18 19:22 |  |  | NA | -595d
R | V2 S03 2 84! |  | 1134 | Committed, In Queue | Project End | 2026-01-31 | 2026-02-01 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 12:53 |  |  | NA | -623d
R | V2 S04 2 81! |  | 1136 | Committed, In Queue | Project End | 2026-04-18 | 2026-04-19 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:16 |  |  | NA | -700d
R | V2 S05 1 85! |  | 1137 | Committed, In Queue | Project End | 2026-05-17 | 2026-05-18 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:06 |  |  | NA | -799d
R | V2 S06 1 86! |  | 1139 | Committed, In Queue | Project End | 2026-08-09 | 2026-08-10 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:16 |  |  | NA | -883d
R | V2 S08 2 82! |  | 1138 | Committed, In Queue | Project End | 2026-07-11 | 2026-07-12 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -784d
R | V2 S09 2 87! |  | 1140 | Committed, In Queue | Project End | 2026-09-26 | 2026-09-27 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -861d
R | V2 S10 1 88! |  | 1141 | Committed, In Queue | Project End | 2026-11-01 | 2026-11-02 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -967d
R | V2 S11 2 89! |  | 1142 | Committed, In Queue | Project End | 2026-12-19 | 2026-12-20 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:16 |  |  | NA | -945d
R | V2 S12 1 90! |  | 1143 | Committed, In Queue | Project End | 2027-01-17 | 2027-01-18 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1044d
R | V2 S13 2 92! |  | 1144 | Committed, In Queue | Project End | 2027-03-13 | 2027-03-14 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1029d
R | V2 S14 1 91! |  | 1145 | Committed, In Queue | Project End | 2027-04-11 | 2027-04-12 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1128d
R | V2 S15 2 93! |  | 1146 | Committed, In Queue | Project End | 2027-05-29 | 2027-05-30 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1106d
R | V2 S16 1 94! |  | 1147 | Committed, In Queue | Project End | 2027-07-04 | 2027-07-05 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1212d
R | V2 S17 2 96! |  | 1148 | Committed, In Queue | Project End | 2027-08-21 | 2027-08-22 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1190d
R | V2 S18 1 97! |  | 1149 | Committed, In Queue | Project End | 2027-09-19 | 2027-09-20 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1289d
R | V2 S19 2 98! |  | 1150 | Committed, In Queue | Project End | 2027-11-13 | 2027-11-14 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1274d
R | V2 S20 1 95! |  | 1151 | Committed, In Queue | Project End | 2027-12-12 | 2027-12-13 | 1d | 60%, 1d/1d | 0%, 0d/80d | Pre Repair | 2023-11-07 13:20 |  |  | NA | -1373d
R | V2 S21 2 99! |  | 1153 | On Hold | Project End | 2028-01-01 | 2028-01-02 | 1d | 60%, 1d/1d | 0%, 0d/100d | Pre Repair | 2023-11-07 13:16 |  |  | NA | -1323d
R | Majoris - 1 Mega INV_04-04_14-52! |  | 833 | In Process | Mech Batch (2 Prototypes assembly with STUB + Samples) | 2023-03-16 | 2024-10-18 | 582d | 32000%, 320d/1d | 88%, 212d/241d | Design (Enclosure Base plate) | 2023-04-04 09:32 |  |  | NA
R | RZTest_AWL027177_20230912! |  | 1017 | In Process | KG00001787 Rev 0 Drawing Submittal Milestone *CS 09/12/2023 | 2023-09-12 | 2024-09-12 | 366d | 13117%, 262d/2d | 17%, 0d/3d | Design and Detail - KG00001787 | 2024-09-09 01:15 |  | *Engineering Only Order. PCMK Drawings as they will be fabbed in future order | NA
R | Test for Integration MRO! |  | 1177 | In Process | Completion Milestone - End of Inspection Phase | 2023-08-29 | 2024-01-16 | 140d | 9310%, 93d/1d | 0%, 0d/0d | Disassembly Complete | 2024-01-16 10:59 |  |  | NA
R | SHIPYARD Analysis Rev1! |  | 679 | Committed, In Queue | Preliminary analysis Brief | 2023-03-03 | 2024-09-26 | 573d | 8180%, 409d/5d | 0%, 0d/9d | Remote Data Collection | 2024-09-09 01:14 |  |  | NA
R | Test Automation Project 1! |  | 2724 | In Process | Completion Milestone | 2024-03-04 | 2026-08-07 | 886d | 7925%, 634d/8d | 0%, 0d/15d | T3 | 2026-07-10 04:51 |  |  | NA
R | SHIPYARD Analysis Feb24 Start! |  | 736 | Committed, In Queue | Preliminary analysis Brief | 2023-04-20 | 2024-09-26 | 525d | 7340%, 367d/5d | 0%, 0d/9d | Remote Data Collection | 2024-09-09 01:01 |  |  | NA
R | Example MRO Project! |  | 895 | In Process | Completion Milestone - End of Inspection Phase | 2023-06-21 | 2024-09-12 | 449d | 6222%, 311d/5d | 75%, 6d/8d | P2: Disassembly - Post Power Off | 2026-08-18 22:24 |  |  | NA
R | V1 S05 169185 PMI-1 R2! |  | 1154 | In Process | Inspection Complete | 2024-03-20 | 2024-09-16 | 180d | 6169%, 123d/2d | 7%, 0d/4d | P2: Disassembly - Pre Power Off | 2024-09-09 01:16 |  |  | NA
R | PMA-274 Implementation Plan Rev1! |  | 285 | On Hold | Go Live Milestone | 2023-04-21 | 2024-09-24 | 522d | 5175%, 362d/7d | 64%, 17d/26d | Final Go-Live Preparations | 2024-03-13 18:22 |  |  | NA
R | ADW Recyclable_3! |  | 137 | On Hold | CMS-Technical Readiness (LPA) for S and M sizes | 2020-09-30 | 2022-04-13 | 560d | 2667%, 400d/15d | 0%, 0d/30d | PO for Material Meeting Tech Spec | 2021-11-17 09:11 |  |  | NA
R | Chris_Product Enhancement! |  | 33 | In Process | CMS-Conduct R3/R5 Design Review | 2022-06-27 | 2023-12-07 | 528d | 2513%, 377d/15d | -3%, -1d/30d | FK-Complete Full kit - SGen5-1200A(118/55) Product Enhancement Phase 2 | 2022-04-26 16:51 |  |  | NA
R | V1 S06 169186 PMI-1! |  | 1155 | In Process | Inspection Complete | 2024-04-02 | 2024-09-27 | 178d | 2081%, 125d/6d | 2%, 0d/10d | P0: Pre-Induction | 2024-09-09 01:13 |  |  | NA
R | Smart PowerPack_05-09_07-06! |  | 1268 | In Process | CMS-Launch Ready | 2024-04-10 | 2024-09-13 | 156d | 2079%, 111d/5d | 76%, 11d/15d | Low load jig - Testing & Handover | 2024-05-08 22:11 |  |  | NA
R | V1 S07 169181 PMI-1_2024! |  | 1189 | In Process | P3: Inspection Complete | 2024-04-03 | 2024-09-30 | 180d | 2070%, 124d/6d | 0%, 0d/10d | FK- Pre-Induction | 2024-03-13 18:22 |  |  | NA
R | `MRO! |  | 1308 | In Process | Inspection Complete | 2024-04-02 | 2024-08-06 | 126d | 1738%, 87d/5d | 0%, 0d/10d | P0: Pre-Induction | 2024-07-17 10:33 |  |  | NA
R | PRA Project MAP! |  | 41 | On Hold | Completion Milestone - First Site and Subset Data Complete | 2022-02-03 | 2027-04-14 | 1896d | 1465%, 1376d/94d | 24%, 46d/188d | FK Clinical Equipment and Supplies | 2026-08-18 22:22 |  |  | NA
R | Chris Project 3! |  | 995 | In Process | Completion Milestone | 2023-09-28 | 2023-10-27 | 29d | 350%, 21d/6d | -14%, -2d/11d | Basic Design | 2023-09-05 14:10 |  |  | NA
R | Gantt Rel 17! |  | 1260 | In Process | UI - Project Status | 2024-08-16 | 2024-10-29 | 74d | 286%, 60d/21d | 40%, 16d/40d | UI Development - Project Status | 2024-09-09 01:16 |  |  | NA
R | TestNilesh2! |  | 1367 | In Process | Completion Milestone | 2024-11-01 | 2024-12-06 | 35d | 117%, 23d/20d | -8%, -3d/40d | t3 | 2024-08-28 03:09 |  |  | NA
Y | PRA Project PLAN! |  | 48 | On Hold | Project End | 2024-07-24 | 2024-09-05 | 43d | 18%, 56d/311d | 8%, 53d/621d | 2nd Draft Protocol Sponsor Review | 2021-11-17 09:11 |  |  | NA | -31d
G | ACE Demo detailed tasks 240822! |  | 414 | In Process | Project End | 2023-10-17 | 2023-10-17 | 0d | 0%, 0d/1d | 0%, 0d/196d |  | 2022-09-22 12:37 |  |  | NA | 0d
G | ACE Demo detailed tasks 240822 updated! |  | 543 | Committed, In Queue | Project End | 2023-10-17 | 2023-10-17 | 0d | 0%, 0d/1d | 0%, 0d/194d |  | 2022-11-07 14:05 |  |  | NA | 0d
G | Automation Project Checklist_FieldOps! |  | 2739 | In Process | Project End | 2026-07-23 | 2026-07-23 | 0d | 0%, 0d/2d | 0%, 0d/3d |  | 2026-07-22 07:21 |  |  | NA | 0d
G | Automation Project InlineEdit_DD2! |  | 2737 | In Process | Project End | 2026-07-28 | 2026-07-28 | 0d | 0%, 0d/3d | 0%, 0d/5d |  | 2026-07-29 01:49 |  |  | NA | -8d
G | Automation Project QuickAccess_RunBM_2! |  | 2742 | In Process | Project End | 2026-07-24 | 2026-07-24 | 0d | 0%, 0d/2d | 0%, 0d/3d |  | 2026-07-20 04:23 |  |  | NA | 0d
G | Automation Project Subtask_Structure! |  | 2731 | In Process | Project End | 2026-08-19 | 2026-08-18 | 0d | 0%, 0d/9d | 6%, 1d/17d |  | 2026-07-22 05:34 |  |  | NA | -25d
G | Automation Project_ErrorAndNotifications! |  | 2738 | In Process | Project End | 2026-07-23 | 2026-07-23 | 0d | 0%, 0d/2d | 0%, 0d/3d |  | 2026-07-17 05:42 |  |  | NA | -1d
G | Automation_Checklist_Test_FK! |  | 2747 | In Process | Project End | 2026-07-31 | 2026-07-30 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-09-20 21:39 |  |  | NA | 1d
G | Automation_Fk_Completion_Status! |  | 2752 | In Process | Project End | 2026-08-07 | 2026-08-07 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-07 04:08 |  |  | NA | 0d
G | Automation_LoggedInUserTest! |  | 2749 | In Process | Project End | 2026-08-04 | 2026-08-04 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-04 04:10 |  |  | NA | 0d
G | Automation_MilestonePanel! |  | 2766 | In Process | Project End | 2026-09-30 | 2026-09-30 | 0d | 0%, 0d/2d | 0%, 0d/3d |  | 2026-09-09 23:42 |  |  | Trend Unchanged | -23d
G | Automation_Test_101518! |  | 2745 | In Process | Project End | 2026-08-03 | 2026-08-03 | 0d | 0%, 0d/1d | 0%, 0d/2d |  | 2026-09-15 05:19 |  |  | NA | -7d
G | Automation_Test_101580! |  | 2733 | In Process | Project End | 2026-08-17 | 2026-08-17 | 0d | 0%, 0d/1d | -100%, -1d/1d |  | 2026-07-22 06:38 |  |  | NA | -24d
G | AutomationConcurreProject! |  | 2771 | In Process | Project End | 2027-01-04 | 2027-01-04 | 0d | 0%, 0d/1d | 0%, 0d/1d |  | 2026-08-31 00:44 |  |  | NA | -90d
G | AutomationCustomTestProject! |  | 2753 | In Process | Project End | 2026-08-10 | 2026-08-09 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-09 02:29 |  |  | NA | 0d
G | AutomationFilterConfigTestProject! |  | 2748 | In Process | Project End | 2026-08-03 | 2026-08-03 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-09-20 21:45 |  |  | NA | 0d
G | AutomationFilterPanelProjectTest! |  | 2754 | In Process | Project End | 2026-08-11 | 2026-08-10 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-10 23:27 |  |  | NA | 1d
G | AutomationGridPercentCompProject! |  | 2755 | In Process | Project End | 2026-08-13 | 2026-08-13 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-09-18 06:03 |  |  | NA | 0d
G | AutomationInlineGanttUpdateProject! |  | 2759 | In Process | Project End | 2026-10-06 | 2026-10-05 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-09-20 22:49 |  |  | Trend Unchanged | -33d
G | AutomationInlineUpdateProject! |  | 2756 | In Process | Project End | 2026-09-11 | 2026-09-10 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-20 21:01 |  |  | NA | -19d
G | AutomationNewPopUpProject! |  | 2762 | In Process | Project End | 2026-10-08 | 2026-10-08 | 0d | 0%, 0d/1d | 0%, 0d/1d |  | 2026-09-18 07:13 |  |  | NA | -33d
G | AutomationProjectDateFormat! |  | 2768 | In Process | Project End | 2026-10-13 | 2026-10-13 | 0d | 0%, 0d/1d | 0%, 0d/2d |  | 2026-08-28 02:38 |  |  | NA | -32d
G | AutomationTaskDocumentTestProject! |  | 2750 | In Process | Project End | 2026-08-06 | 2026-08-06 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-06 00:38 |  |  | NA | 0d
G | FK Automation Project! |  | 2729 | In Process | Project End | 2026-07-13 | 2026-07-13 | 0d | 0%, 0d/1d | 0%, 0d/1d |  | 2026-07-13 00:19 |  |  | NA | 0d
G | FK status Project! |  | 2720 | In Process | Project End | 2026-06-29 | 2026-06-29 | 0d | 0%, 0d/1d | 0%, 0d/1d |  | 2026-06-23 06:19 |  |  | NA | -3d
G | FK transitions Project! |  | 2721 | In Process | Project End | 2026-06-24 | 2026-06-23 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-06-23 06:27 |  |  | NA | 0d
G | Meta Project! |  | 206 | On Hold | Project End | 2022-07-01 | 2022-07-01 | 0d | 0%, 0d/28d | 0%, 0d/55d |  | 2022-02-02 09:29 |  |  | NA | 0d
G | Template! |  | 535 | On Hold | Project End | 2023-04-17 | 2023-04-17 | 0d | 0%, 0d/40d | 0%, 0d/79d |  | 2022-11-01 15:31 |  |  | NA | 0d
G | Test-pt! |  | 839 | In Process | Project End | 2023-07-21 | 2023-07-25 | 4d | 0%, 0d/20d | -10%, -4d/40d |  | 2023-04-13 07:53 |  |  | NA | -29d
G | Test_Automation_Project_Task_101577! |  | 2728 | In Process | Project End | 2026-08-25 | 2026-08-25 | 0d | 0%, 0d/1d | 0%, 0d/2d |  | 2026-07-13 23:20 |  |  | NA | -34d
G | TestPlaywrightMcpProject! |  | 2760 | In Process | Project End | 2026-08-20 | 2026-08-19 | 0d | 0%, 0d/1d | 100%, 0d/0d |  | 2026-08-19 22:30 |  |  | NA | 1d
G | TestSummary! |  | 1027 | In Process | Project End | 2023-11-14 | 2023-11-14 | 0d | 0%, 0d/10d | 0%, 0d/20d |  | 2023-10-04 03:32 |  |  | NA | 0d
G | PMI1 Template MANPOWER 5! |  | 912 | In Process | Completion Milestone - End of Inspection Phase | 2023-12-26 | 2023-12-21 | 0d | 24%, 2d/10d | 43%, 8d/18d | P2: Disassembly - Post Power Off | 2023-11-30 01:00 |  |  | NA
G | SPC Rollout! |  | 75 | On Hold | Complete new SPC charts | 2021-08-25 | 2021-08-24 | 0d | 0%, 0d/11d | 14%, 3d/22d |  | 2021-11-17 09:11 |  |  | NA
G | Test 9 Chris! |  | 1041 | Committed, In Queue | PV Validado | 2024-04-24 | 2024-04-24 | 0d | 0%, 0d/43d | 0%, 0d/85d |  | 2023-10-27 14:00 |  |  | NA
G | V1 S07 169181 PMI-1_2024_1_24_10_2_47! |  | 1184 | In Process | P3: Inspection Complete | 2024-02-22 | 2024-02-22 | 0d | 0%, 0d/5d | 0%, 0d/9d |  | 2024-02-01 10:53 |  |  | NA