## Task_List_14_2026-09-23_21_32_
Task List
Division |  |  | All
Portfolio |  |  | All
Customer |  |  | All
Task Manager |  |  | All
Projects |  |  | All
Resources |  |  | All
Horizon |  |  | 14
(Not Started:Y In Progress:Y Completed:N)
Color | Task Type | Constraint Date | Task Mgr | Project Name | UID | Description | Resources | Preds CO | Sugg Start | Participants | Status | Rem Dur | Actual Start Date | Actual End Date | Comments | Help Needed | Project Mgr | Suggested Rollup | Subtask Type | Auto RU Dur | CheckList
R |  |  | Efi | ACE Execution | 11 | Develop MC HLD | System Engineer(1) | Y | 2023-01-03 |  | IP | 2d | 2022-05-15 |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 34 | Develop FTER HLD | System Engineer(1) | Y | 2023-01-03 |  | IP | 2d | 2022-05-15 |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 374 | Develop GTER HLD | System Engineer(1) | Y | 2023-01-03 |  | IP | 2d | 2022-05-15 |  |  |  | Guy Brill |  | Network |  | 0
R | SNET |  |  | Chris Project 3 | 2 | Basic Design | Designer(1), Electrical Engineering(1), Mechanical Engineering(1) | Y | 2023-10-04 |  | IP | 2d | 2023-09-05 |  |  |  | Chris Timmer |  | Network |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 501 | P2: Disassembly - Post Power Off | ARTISAN(6) | Y | 2023-11-30 |  | IP | 2d 8.7h | 2023-11-13 |  |  |  | Concerto Admin | 2d 8.7h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 58 | P3: Inspection | ARTISAN(5) | N | 2024-01-16 |  | IP | 0d 1.2h | 2023-09-13 |  |  |  | Concerto Admin | 0d 1.8h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2024-01-16 |  | IP | 0d 3.3h | 2023-09-07 |  |  |  | Concerto Admin | 0d 5h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2024-01-16 |  | IP | 1d 5.4h | 2023-09-12 |  |  |  | Concerto Admin | 2d 1.5h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2024-01-16 |  | IP | 1d 2h | 2023-09-07 |  |  |  | Concerto Admin | 1d 9.5h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2024-01-17 |  | IP | 2d 5.4h | 2023-09-18 |  |  |  | Concerto Admin | 3d 8h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2024-01-17 |  | IP | 0d 10h | 2023-09-24 |  |  |  | Concerto Admin | 1d 2h | Volume of Work | 1 | 0
R |  |  |  | Test for Integration MRO | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2024-01-18 |  | IP | 1d 1.7h | 2023-09-14 |  |  |  | Concerto Admin | 1d 9h | Volume of Work | 1 | 0
R | SNET |  |  | Navy Cloud Pilot Deployment | 37 | Phase 1 - Planning | Government(1.7) | Y | 2024-04-10 |  | IP | 5d | 2023-12-12 |  |  |  | Michael Hamlin |  | Network |  | 0
R |  |  |  | `MRO | 1 | P0: Pre-Induction | ARTISAN(6) | Y | 2024-07-17 |  | IP | 1d 1.4h | 2023-12-01 |  |  |  | Deepak Jha | 1d 8.5h | Volume of Work | 0 | 0
R |  |  |  | Example MRO Project | 501 | P2: Disassembly - Post Power Off | ARTISAN(7) | Y | 2024-09-09 |  | IP | 0d 6.5h | 2023-06-08 |  |  |  | Concerto Admin | 0d 9.8h | Volume of Work | 1 | 0
R |  |  |  | V1 S06 169186 PMI-1 | 1 | P0: Pre-Induction | ARTISAN(6) | Y | 2024-09-09 |  | IP | 1d 1.4h | 2023-12-01 |  |  |  | Concerto Admin | 1d 8.5h | Volume of Work | 0 | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 1 | P0: Pre-Induction | ARTISAN(5.9) | N | 2024-09-09 |  | IP | 1d 2.3h | 2024-02-06 |  |  |  | Concerto Admin | 4d 8.1h | Network | 0 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 57 | P2: Disassembly - Pre Power Off | ARTISAN(6.3) | Y | 2024-09-09 |  | IP | 0d 9.9h | 2023-11-28 |  |  |  | Concerto Admin | 1d 1.7h | Volume of Work | 0 | 0
R |  |  | Task Team | 1+Task | 1 | T1 | Default(1) | Y | 2024-09-09 | Test Search | IP | 9d 7.9h | 2024-08-30 |  |  |  | PM2 | 10d | Network | 0 | 1
R |  |  | Task Team 1 | v2_22_DEV | 172 | E-Invoice | Dev SOA(1) | Y | 2024-09-09 | bscott, TaskParticipant | IP | 1d | 2022-07-28 |  |  |  | ProjectManager1 | 1d | Network | 0 | 2
R |  |  | TaskManager | v2_22_DEV | 4 | E-invoice | Dev Export/CMS(3) | Y | 2024-09-09 |  | IP | 7d 2h | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Uri_Z_T | v2_22_DEV | 157 | Report | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 3d | 2022-07-24 |  |  |  | ProjectManager1 | 1d | Network | 0 | 1
R |  |  | Zali_T | v2_22_DEV | 96 | Layout | Dev Layouts(1) | Y | 2024-09-09 |  | IP | 1d | 2022-07-20 |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | Wisam_T | v2_22_DEV | 136 | CRM-RQT439258 | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 0d 4h | 2022-07-24 |  |  |  | ProjectManager1 | 1d | Network | 0 | 1
R |  |  | Romi_T | v2_22_DEV | 181 | EQP | Dev SOA(1) | Y | 2024-09-09 |  | IP | 1d 2h | 2022-07-21 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Eitan_T | v2_22_DEV | 14 | Export 1 (+APIM)+SENDGRID | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 4d | 2022-07-20 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Romi_T | v2_22_DEV | 86 | TAS | Dev SOA(1) | Y | 2024-09-09 |  | IP | 5d | 2022-08-09 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Wisam_T | v2_22_DEV | 137 | ORBCOMM | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 1d | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Uri_Z_T | v2_22_DEV | 158 | Monitoring | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 3d | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Kobi_T | v2_22_DEV | 162 | ORBCOMM | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 5d | 2022-08-03 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Kobi_T | v2_22_DEV | 161 | ELK Monitoring | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 2d | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Hava_T | v2_22_DEV | 169 | POC | Dev Informatica(1) | Y | 2024-09-09 |  | IP | 4d 6h | 2022-07-25 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Zali_T | v2_22_DEV | 95 | Route restrictions | Dev Layouts(1) | Y | 2024-09-09 |  | IP | 4d | 2022-07-20 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Wisam_T | v2_22_DEV | 135 | CRM KAFKA-RQT441403,RQT436413 | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 4d | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Greg_T | v2_22_DEV | 34 | ORBCOMM-RQT434468 | Dev CCM/ETT/BIDZ(1) | Y | 2024-09-09 |  | IP | 3d | 2022-07-20 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Lior_T | v2_22_DEV | 6 | Australia placeholder | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 1d | 2023-01-10 |  |  |  | ProjectManager1 | 1d | Network | 0 | 2
R |  |  | Uri_Z_T | v2_22_DEV | 131 | LT | Dev ADBA(1) | Y | 2024-09-09 |  | IP | 0d 4h | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Hava_T | v2_22_DEV | 74 | SAP HR | Dev Informatica(1) | Y | 2024-09-09 |  | IP | 2d | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | YairA_T | v2_22_DEV | 124 | NTF | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 2d | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Hava_T | v2_22_DEV | 171 | Allocation | Dev Informatica(1) | Y | 2024-09-09 |  | IP | 2d | 2022-07-25 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Olga_T | v2_22_DEV | 22 | NTF (Integrative) | Dev Import(1) | Y | 2024-09-09 |  | IP | 0d 4h | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Romi_T | v2_22_DEV | 175 | B2A | Dev SOA(1) | Y | 2024-09-09 |  | IP | 3d | 2022-07-21 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Romi_T | v2_22_DEV | 83 | APIM | Dev SOA(1) | Y | 2024-09-09 |  | IP | 1d 2h | 2022-08-11 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Greg_T | v2_22_DEV | 32 | CCM | Dev CCM/ETT/BIDZ(1) | Y | 2024-09-09 |  | IP | 1d | 2022-07-21 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | YairA_T | v2_22_DEV | 153 | B2A | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 1d | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 2
R |  |  | Romi_T | v2_22_DEV | 92 | CRM | Dev SOA(1) | Y | 2024-09-09 |  | IP | 2d | 2022-07-21 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Eitan_T | v2_22_DEV | 151 | EBL | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 0d 6h | 2022-07-31 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Olga_T | v2_22_DEV | 29 | US Customs | Dev Import(1) | Y | 2024-09-09 |  | IP | 0d 6h | 2022-08-01 |  |  |  | ProjectManager1 |  | Network |  | 2
R |  |  | Eitan_T | v2_22_DEV | 16 | Screening | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 1d | 2022-07-20 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Gilbert_T | v2_22_DEV | 110 | CRM | ABAP Programmer(2) | Y | 2024-09-09 |  | IP | 1d | 2022-07-24 |  |  |  | ProjectManager1 |  | Network |  | 2
R |  |  | Lior_T | v2_22_DEV | 146 | Cyber | Dev Export/CMS(1) | Y | 2024-09-09 |  | IP | 1d | 2022-07-27 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Amnon_T | v2_22_DEV | 105 | FI | ABAP Programmer(2) | Y | 2024-09-09 | smoshe | IP | 0d 6h | 2022-07-27 |  |  | Waiting on Decision | ProjectManager1 |  | Network |  | 1
R |  |  |  | test-purchasing2 | 1 | Task-1 | Engineering(8), Finishing(10) | Y | 2024-09-09 |  | IP | 7d | 2024-02-15 |  |  |  | Concerto Admin | 10d | Network | 1 | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 3 | Precheck_Priority Tasks | MECHANICAL(2) | Y | 2024-09-09 |  | IP | 2d | 2023-11-27 |  |  |  | Manuel Rodriguez | 2d 3.7h | Volume of Work | 1 | 0
R |  |  |  | TestAutoRollup | 1 | T1 | Default(2) | Y | 2024-09-09 |  | IP | 14d | 2023-10-02 |  |  |  | Concerto Admin | 10d | Network | 0 | 0
R |  |  | t.carella | RZTest_AWL027177_20230912 | 4773 | Design and Detail - KG00003924 (-005) | Designer Group - Wichita and Mumbai(1) | Y | 2024-09-09 |  | IP | 1d 2.7h | 2023-08-31 |  | *Engineering Only Order. PCMK Drawings as they will be fabbed in future order |  | Concerto Admin | 2d | Network | 1 | 0
R |  |  | kpatil | RZTest_AWL027177_20230912 | 4784 | Design and Detail - KG00003924 (-001/-002/-003/-004) | Designer Group - Wichita and Mumbai(1.3) | Y | 2024-09-09 | p.prajapati, pawan.suthar | IP | 2d 4.1h | 2023-09-05 |  | *Engineering Only Order. PCMK Drawings as they will be fabbed in future order |  | Concerto Admin | 3d 6h | Network | 1 | 0
R |  |  | d.profit | RZTest_AWL027177_20230912 | 3616 | Design and Detail - KG00001787 | Designer Group - Wichita and Mumbai(1) | Y | 2024-09-09 |  | IP | 1d | 2023-08-16 |  | *Engineering Only Order. PCMK Drawings as they will be fabbed in future order |  | Concerto Admin | 1d 4h | Network | 1 | 0
R |  |  | s.rajwadi | RZTest_AWL027177_20230912 | 3832 | Design and Detail - KG00014889 | Designer Group - Wichita and Mumbai(1.8) | Y | 2024-09-09 | p.prajapati, sunil.prajapati | IP | 2d 2h | 2023-09-07 |  | *Engineering Only Order. PCMK Drawings as they will be fabbed in future order |  | Concerto Admin | 3d 3h | Network | 1 | 0
R |  |  | j.guo | RZTest_AWL027177_20230912 | 3939 | Equipment Engineering Review - KG00070783 | Default Resource(1) | Y | 2024-09-09 |  | IP | 1d 2.7h | 2023-09-12 |  | originally released by NN |  | Concerto Admin |  | Network |  | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 3 | Precheck_Priority Tasks | MECHANICAL(8) | Y | 2024-09-09 |  | IP | 2d | 2023-11-27 |  |  |  | Manuel Rodriguez | 1d 4.4h | Volume of Work | 1 | 0
R |  |  | steinerm | Test Part 1 | 7437 | Team Kick Off Meeting | ID_Design(1) | Y | 2024-09-09 |  | IP | 2d | 2023-11-27 |  |  | Waiting for Resources | George |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8870 | HW Design - from product and system + requierments (D1744A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 40d | 2023-01-28 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3709 | Layout completion (D1741A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 4d | 2023-02-12 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3659 | Layout completion (D1738A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 50d | 2023-03-09 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 51 | Layout completion (D1739A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 50d | 2023-01-24 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9056 | HW Design - from product and system + requierments (D1371B) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 50d | 2023-01-28 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tspielvogel | DP273 | 22 | Final Tests | ECF MECH LAB(1) | Y | 2024-09-09 |  | IP | 51d | 2024-01-14 |  | Microcleanliness retest Failed 2/29, EMT is reviewing |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11885 | Design (Enclosure Base plate) | Mechanics(1) | Y | 2024-09-09 | michael.ra | IP | 4d | 2023-03-07 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3559 | Layout completion (D1541B) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 36d | 2023-03-18 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8272 | MCU Hybrid HW readiness (D1277A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 1d | 2023-02-14 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3432 | BOM 100% (D1740A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 5d | 2023-03-26 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | WMS en RETAIL | 1 | Activaciones Iniciales | Experto IT(1) | Y | 2024-09-09 |  | IP | 8d | 2024-04-03 |  |  |  | Fiallos | 8d | Network | 1 | 1
R |  |  |  | Gantt Rel 17 | 124 | UI Development - Project Status | BE(0.6), FE(2) | Y | 2024-09-09 |  | IP | 24d 0.9h | 2024-05-09 |  |  |  | Concerto Admin | 36d | Network | 1 | 0
R |  |  |  | Glow Lab | 65 | Parallel run of MRP toolset | Contractor(0.5), Glow Lab(2) | Y | 2024-09-09 |  | IP | 9d | 2024-08-22 |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 62 | Configure and Test two-way integration between Odoo and MWE | Integration specialist(0.5), Wedoo team(1) | Y | 2024-09-09 |  | IP | 6d | 2024-07-28 |  |  |  | Jaco |  | Network |  | 1
R |  |  |  | Medifab - RFID implementation plan | 5 | Confirm quantity with customer and place RFID tag order | Customer Process Engineering(1), RFID Engineer(1) | Y | 2024-09-09 |  | IP | 2d | 2024-07-18 |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 32 | Delivery leadtime for gates | Fabricator(1) | Y | 2024-09-09 |  | IP | 7d | 2024-08-12 |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 33 | Installation of electrical and data hardware | Hardware and electrical installer(1) | Y | 2024-09-09 |  | IP | 6d | 2024-07-29 |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | TestNilesh2 | 3 | t3 | Default(1) | Y | 2024-09-09 |  | IP | 13d 2.6h | 2024-08-27 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10103 | Low load jig - Testing & Handover | R&D_Hardware(1) | Y | 2024-09-09 | johann.geldenhuys | IP | 2d 6h | 2024-05-05 |  |  |  | Christo Wentzel |  | Network |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9040 | HW Design - from product and system + requierments (D1732A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 60d | 2023-02-14 |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10032 | HW Design - from product and system + requierments (D1711B) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 40d | 2023-02-14 |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11551 | HW Design - from product and system + requirements (D1420A) | Utility(1) | Y | 2024-09-09 | shani.a | IP | 60d | 2023-02-19 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 501 | P2: Disassembly - Post Power Off | ARTISAN(6.3) | N | 2024-09-09 |  | IP | 0d 6.5h | 2023-11-29 |  |  |  | Concerto Admin | 0d 9.8h | Volume of Work | 0 | 0
R |  |  | Romi_T | v2_22_DEV | 91 | Email 2 Sales(L2A) | Dev SOA(1) | Y* | 2024-09-10 |  | IP | 0d 0.8h | 2022-08-03 |  |  |  | ProjectManager1 |  | Network |  | 2
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8260 | Design (D1740A Setup) | Utility(1) | N | 2024-09-10 | shani.a | IP | 15d | 2023-03-13 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 58 | P3: Inspection | ARTISAN(6.3) | N | 2024-09-10 |  | IP | 2d 1.3h | 2023-11-29 |  |  |  | Concerto Admin | 3d 1.8h | Volume of Work | 0 | 0
R |  |  | Romi_T | v2_22_DEV | 180 | Salesforce Ins. | Dev SOA(1) | N | 2024-09-10 |  | IP | 0d 0.8h | 2022-07-28 |  |  |  | ProjectManager1 |  | Network |  | 2
R |  |  | Lior_T | v2_22_DEV | 8 | ORBCOMM | Dev Export/CMS(2) | N | 2024-09-10 |  | IP | 2d 6h | 2022-07-27 |  |  |  | ProjectManager1 |  | Network |  | 1
G |  |  |  | Example MRO Project | 505 | P4: Repair - Zone 1B | ARTISAN(7) | N | 2024-09-11 |  | IP | 1d 0.2h | 2023-06-15 |  |  |  | Concerto Admin | 1d 6.7h | Volume of Work | 1 | 0
G |  |  |  | Example MRO Project | 508 | P4: Repair - Zone 2R | ARTISAN(7) | N | 2024-09-11 |  | IP | 1d 4.2h | 2023-06-08 |  |  |  | Concerto Admin | 1d 12.7h | Volume of Work | 1 | 0
G |  |  |  | Example MRO Project | 509 | P4: Repair - Zone 4 | ARTISAN(7) | N | 2024-09-11 |  | IP | 0d 6h | 2023-06-07 |  |  |  | Concerto Admin | 0d 9h | Volume of Work | 1 | 0
G |  |  |  | Example MRO Project | 604 | P4: Repair - Zone 5 | ARTISAN(7) | N | 2024-09-11 |  | IP | 0d 3h | 2023-06-07 |  |  |  | Concerto Admin | 0d 4.5h | Volume of Work | 1 | 0
R |  |  | Zina_T | v2_22_DEV | 52 | 310 EDI | Dev Quotation(1) | N | 2024-09-11 |  | IP | 4d | 2022-07-21 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Johny_T | v2_22_DEV | 56 | Salesforce Ins. | Dev AgentCloud(1) | N | 2024-09-11 |  | IP | 4d | 2022-07-19 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Johny_T | v2_22_DEV | 167 | AC report | Dev AgentCloud(1) | N | 2024-09-11 |  | IP | 1d 2h | 2022-07-19 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Olga_T | v2_22_DEV | 30 | Bug Fix Import | Dev Import(1) | N | 2024-09-11 |  | IP | 0d 4h | 2022-07-26 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Uri_Z_T | v2_22_DEV | 126 | LTT RQT430970 | Dev ADBA(1) | N | 2024-09-12 |  | IP | 2d | 2022-08-07 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | V1 S05 169185 PMI-1 R2 | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2024-09-12 |  | IP | 3d 10.4h | 2023-11-20 |  |  |  | Concerto Admin | 5d 8.7h | Volume of Work | 0 | 0
R |  |  | Lior_T | v2_22_DEV | 10 | B2A (Print BL) | Dev Export/CMS(1) | N | 2024-09-13 |  | IP | 3d | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Eitan_T | v2_22_DEV | 15 | CRM | Dev Export/CMS(2) | N | 2024-09-13 |  | IP | 3d | 2022-08-04 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Eitan_T | v2_22_DEV | 17 | Export 2 | Dev Export/CMS(1) | N | 2024-09-13 |  | IP | 1d 2h | 2022-08-04 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Romi_T | v2_22_DEV | 81 | P2P | Dev SOA(1) | N | 2024-09-16 |  | IP | 1d 2h | 2022-08-03 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Johny_T | v2_22_DEV | 57 | Bug fix | Dev AgentCloud(1) | N | 2024-09-17 |  | IP | 1d 2h | 2022-07-19 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | Medifab - RFID implementation plan | 73 | Testing of MWE off-site | Integration specialist(1), RFID Engineer(0.5) | Y* | 2024-09-17 |  | IP | 3d | 2024-08-26 |  |  |  | Jaco |  | Network |  | 0
R |  |  | Lior_T | v2_22_DEV | 5 | Export | Dev Export/CMS(2) | N | 2024-09-18 |  | IP | 3d | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Lior_T | v2_22_DEV | 147 | Depot | Dev Export/CMS(1) | N | 2024-09-18 |  | IP | 3d | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Hava_T | v2_22_DEV | 78 | Bug fix Informatica | Dev Informatica(1) | N | 2024-09-19 |  | IP | 1d 2h | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Lior_T | v2_22_DEV | 145 | Crystal | Dev Export/CMS(1) | N | 2024-09-20 |  | IP | 1d 2h | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Greg_T | v2_22_DEV | 38 | Bug Fix ETT/CCM | Dev CCM/ETT/BIDZ(1) | N | 2024-09-23 |  | IP | 1d 2h | 2022-08-02 |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | ERP en ABC | 1 | Activaciones Iniciales | Experto IT(1) | Y | 2026-06-23 |  | IP | 8d | 2024-04-03 |  |  |  | Fiallos | 8d | Network | 1 | 0
R |  |  | Aaron Martin | Test Automation Project 1 | 6 | Default Phase | CFD Group(1) | N | 2026-07-15 | Aaron Wilbur | IP | 1d | 2026-07-10 |  |  |  | ResAdmin1 | 1d | Network | 1 | 0
R |  |  | Aaron Martin | Test Automation Project 1 | 4 | Task1 | CFD Group(1) | N | 2026-07-15 | Aaron Wilbur | IP | 1d | 2026-05-28 |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project Subtask_Structure | 1 | Task 1 | Default(1) | Y | 2026-07-16 |  | IP | 2d | 2026-07-13 |  |  |  | ResAdmin1 | 2d | WIP | 1 | 0
R |  |  |  | Automation Project InlineEdit_DD1 | 2 | Task2 | Default(1) | N | 2026-07-20 |  | IP | 4d | 2026-07-15 |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project InlineEdit_DD2 | 2 | Task2 | Default(1) | N | 2026-07-20 |  | IP | 3d 2.6h | 2026-07-15 |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | automation_test_10158 | 1 | task | Default(1) | Y | 2026-07-23 |  | IP | 1d | 2026-07-14 |  |  |  | Concerto Admin | 1d | Network | 0 | 0
G |  |  | Tier1TaskManager | Automation Project Subtask_Structure | 22 | Task5 | Default(1) | Y* | 2026-07-24 |  | IP | 1d | 2026-07-14 |  |  |  | ResAdmin1 | 1d | Network | 1 | 0
G |  |  |  | Automation Project Subtask_Structure | 32 | Task8 | Default(1) | N | 2026-07-28 |  | IP | 1d | 2026-07-13 |  |  |  | ResAdmin1 | 1d | Network | 1 | 0
G |  |  |  | Automation_Test_101580 | 1 | Task | Default(1) | Y | 2026-08-13 |  | IP | 2d | 2026-07-22 |  |  |  | Concerto Admin | 2d | Network | 0 | 0
G |  |  |  | Test_Automation_Project_Task_101577 | 1 | Task | Default(1) | Y | 2026-08-21 |  | IP | 2d | 2026-07-09 |  |  |  | Concerto Admin | 2d | WIP | 0 | 0
R | PT |  |  | AutomationTaskEditingFieldProject | 5 | PT-Task | Default(1) | N | 2026-08-28 |  | IP | 2026-08-29 | 2026-08-27 |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | snelgrovep | MetaBook | 1 | Team | Unassigned(1) | Y | 2022-03-03 |  | NS | 0d 6h |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 2 | Tasks | Unassigned(1) | N | 2022-03-03 |  | NS | 10d |  |  |  |  | lockwoodj |  | Network |  | 0
G |  |  | snelgrovep | MetaBook | 11 | Concerto | Phil(1) | Y | 2022-03-09 |  | NS | 13d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 3 | Durations | Jono(1) | N | 2022-03-17 |  | NS | 7d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 4 | Dependancies | Jono(1) | N | 2022-03-28 |  | NS | 10d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 5 | Resources | Unassigned(1) | N | 2022-04-11 |  | NS | 4d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | snelgrovep | MetaBook | 6 | Complete | Unassigned(1) | N | 2022-04-15 |  | NS | 0d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | snelgrovep | MetaBook | 7 | Approved | Phil(1) | N | 2022-04-15 |  | NS | 1d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | snelgrovep | MetaBook | 12 | Users | Phil(1) | N | 2022-04-18 |  | NS | 20d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 8 | Loaded | Unassigned(1) | N | 2022-05-16 |  | NS | 7d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 9 | CCPlanning | Unassigned(1) | N | 2022-05-25 |  | NS | 7d |  |  |  |  | lockwoodj |  | Network |  | 0
R |  |  | lockwoodj | MetaBook | 10 | Live | Unassigned(1) | N | 2022-06-03 |  | NS | 2d |  |  |  |  | lockwoodj |  | Network |  | 0
R | PE |  |  | MetaBook | 14 | Project End |  | N | 2022-06-08 |  | NS | 0d |  |  |  |  | lockwoodj |  |  |  | 0
R |  |  |  | Integration Example Execution | 1 | B1 | Blue(1) | Y | 2022-07-18 |  | NS | 9d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | Integration Example Execution | 2 | B2 | Blue(1) | Y | 2022-07-18 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | Integration Example Execution | 3 | B3 | Blue(1) | Y | 2022-07-22 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | Integration Example Execution | 4 | B4 | Blue(1) | Y | 2022-07-28 |  | NS | 6d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Integration Example Execution | 5 | G1 | Green(1) | N | 2022-07-29 |  | NS | 8d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Integration Example Execution | 6 | G2 | Green(1) | N | 2022-08-10 |  | NS | 7d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Integration Example Execution | 7 | P1 | Purple(1) | N | 2022-08-19 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R | PE |  |  | Integration Example Execution | 9 | Project End |  | N | 2022-09-01 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  |  | ACE Execution | 54 | Develop IB ATP | System Engineer(1) | Y | 2023-01-03 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 73 | Develop Simulator HLD | System Engineer(1) | Y | 2023-01-03 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 9 | Develop System Test Strategy | INT Engineer(1), System Engineer(1) | Y | 2023-01-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 497 | Develop GTER ATP | System Engineer(1) | Y | 2023-01-03 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 232 | Dev. MC Appl SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 51 | Develop IB HLD | System Engineer(1) | N | 2023-01-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 228 | Design Concept of MC Chassis | mechanical Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 349 | Design Concept of FTER Chassis | mechanical Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 471 | Design Concept of FTER Chassis | mechanical Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 242 | Dev. MC Comm SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 246 | Dev. MC DispSW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 239 | Dev. MC Infra SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 331 | Design FTER PS schematics | HW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
G |  |  | Dov | ACE Execution | 360 | Dev. FTER Infra SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 363 | Dev. FTER Comm SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 367 | Dev. FTER Appl SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 370 | Dev. FTER DispSW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 452 | Design GTER PS schematics | HW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
G |  |  | Dov | ACE Execution | 482 | Dev. GTER Infra SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 486 | Dev. GTER Comm SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 490 | Dev. GTER DispSW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 494 | Dev. GTER Appl SW DROP 1 | SW Engineer(1) | N | 2023-01-05 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 37 | Develop FTER ATP | System Engineer(1) | N | 2023-01-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 537 | Receive GFE Radios | PM(1) | N | 2023-01-10 |  | NS | 40d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 538 | Purchase Accessories | PM(1) | N | 2023-01-10 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 518 | Design Concept of IB Chassis | mechanical Engineer(1) | N | 2023-01-12 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 60 | Develop Cables HLD | System Engineer(1) | N | 2023-01-12 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 500 | Design IB MB schematics | HW Engineer(1) | N | 2023-01-12 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 8 | Develop System HLD | System Engineer(1) | Y | 2023-01-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 530 | Purchase cable material | Operations(1) | N | 2023-01-19 |  | NS | 45d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 66 | Develop Cables ATP | HW Engineer(1) | N | 2023-01-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 529 | Design cables | HW Engineer(1) | N | 2023-01-19 |  | NS | 20d |  |  |  |  | Guy Brill | 4d | Network | 0 | 0
G |  |  | Efi | ACE Demo detailed tasks 240822 | 11 | Develop MC HLD | System Engineer(1) | N | 2023-01-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 10 | Develop System ATP | System Engineer(1) | N | 2023-01-24 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 12 | Develop MC ATP | System Engineer(1) | N | 2023-01-30 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 228 | Design Concept of MC Chassis | mechanical Engineer(1) | N | 2023-01-30 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 51 | Develop IB HLD | System Engineer(1) | N | 2023-02-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 234 | Dev. MC Appl SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 250 | Define DXF for MC Electronic cards | mechanical Engineer(1) | N | 2023-02-02 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 350 | Define DXF for FTER Electronic cards | mechanical Engineer(1) | N | 2023-02-02 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 472 | Define DXF for GTER Electronic cards | mechanical Engineer(1) | N | 2023-02-02 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 243 | Dev. MC Comml SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 247 | Dev. MC Disp SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 240 | Dev. MC Infra SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 337 | Design FTER PS PCB Layout | PCB layout sub contractor(1) | N | 2023-02-02 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Dov | ACE Execution | 361 | Dev.FTER Infra SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 364 | Dev. FTER Comm SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 368 | Dev. FTER Appl SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 371 | Dev. FTER Disp SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 458 | Design GTER PS PCB Layout | PCB layout sub contractor(1) | N | 2023-02-02 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Dov | ACE Execution | 483 | Dev. GTER Infra SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 487 | Dev. GTER Comm SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 491 | Dev. GTER Disp SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 495 | Dev. GTER Appl SW DROP 2 | SW Engineer(1) | N | 2023-02-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 34 | Develop FTER HLD | System Engineer(1) | N | 2023-02-02 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 992 | Develop GTER HLD | System Engineer(1) | N | 2023-02-02 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 518 | Design Concept of IB Chassis | mechanical Engineer(1) | N | 2023-02-08 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 519 | Define DXF for IB Electronic cards | mechanical Engineer(1) | N | 2023-02-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 277 | Design FTER MB schematics | HW Engineer(1) | N | 2023-02-09 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 295 | Design FTER Disp. Module schematics | HW Engineer(1) | N | 2023-02-09 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 313 | Design FTER KB schematics | HW Engineer(1) | N | 2023-02-09 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 259 | Design FTER Processor schematics | HW Engineer(1.4) | N | 2023-02-09 |  | NS | 19d |  |  |  |  | Guy Brill | 19d | Network | 1 | 0
G |  |  | Sergey | ACE Execution | 251 | Detail Design MC Chassis | mechanical Engineer(1) | N | 2023-02-09 |  | NS | 32d |  |  |  |  | Guy Brill | 33d | Network | 0 | 0
G |  |  | Sergey | ACE Execution | 351 | Detail Design FTER Chassis | mechanical Engineer(1) | N | 2023-02-09 |  | NS | 32d |  |  |  |  | Guy Brill | 33d | Network | 0 | 0
G |  |  | Sergey | ACE Execution | 473 | Detail Design GTER Chassis | mechanical Engineer(1) | N | 2023-02-09 |  | NS | 32d |  |  |  |  | Guy Brill | 33d | Network | 0 | 0
G |  |  | Jacob | ACE Execution | 506 | Design IB MB PCB Layout | PCB layout sub contractor(1) | N | 2023-02-09 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 28 | Design concept of FTER Chassis | mechanical Engineer(1.7) | N | 2023-02-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 71 | Develop Simulator ATP | System Engineer(1) | N | 2023-02-09 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1073 | Design concept of GTER Chassis | mechanical Engineer(1.7) | N | 2023-02-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 79 | Design MC Processor schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 100 | Design MC Display schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 119 | Design MC Comm computer schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 138 | Design MC MB schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 156 | Design MC Disp. Module schematics | HW Engineer(1.4) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 174 | Design MC LCD Module schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 192 | Design MC KB schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 210 | Design MC PS schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 395 | Design GTER MB schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 414 | Design GTER Disp. Module schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 433 | Design GTER KB schematics | HW Engineer(1) | N | 2023-02-16 |  | NS | 20d |  |  |  |  | Guy Brill | 19d | Network | 0 | 0
R |  |  | Jacob | ACE Execution | 376 | Design GTER Processor schematics | HW Engineer(1.4) | N | 2023-02-16 |  | NS | 19d |  |  |  |  | Guy Brill | 19d | Network | 1 | 0
R |  |  | Sergey | ACE Execution | 520 | Detail Design IB Chassis | mechanical Engineer(1) | N | 2023-02-16 |  | NS | 32d |  |  |  |  | Guy Brill | 33d | Network | 0 | 0
G |  |  | Jacob | ACE Execution | 342 | Produce FTER PS PCB | PCB production SC(1) | N | 2023-02-24 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Jacob | ACE Execution | 463 | Produce GTER PS PCB | PCB production SC(1) | N | 2023-02-24 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 250 | Define DXF for MC Electronic cards | mechanical Engineer(1.8) | N | 2023-02-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 235 | Dev. MC Appl SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 244 | Dev. MC Comm SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 248 | Dev. MCDisp SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 241 | Dev. MC Infra SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 362 | Dev. FTER Infra SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 365 | Dev. FTER Comm SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 369 | Dev. FTER Appl SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 372 | Dev. FTER Disp SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 484 | Dev. GTER Infra SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 488 | Dev. GTER Comm SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 492 | Dev. GTER Disp SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Execution | 496 | Dev. GTER Appl SW DROP 3 | SW Engineer(1) | N | 2023-03-02 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 511 | Produce IB MB PCB | PCB production SC(1) | N | 2023-03-03 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 80 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-06 |  | NS | 35d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 68 | Build BTN Network Env. | HW Engineer(1) | N | 2023-03-07 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 69 | Build BTY Network Env. | HW Engineer(1) | N | 2023-03-07 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 70 | Build FO Network Env. | HW Engineer(1) | N | 2023-03-07 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 265 | Design FTER Processor PCB Layout | PCB layout sub contractor(1) | N | 2023-03-08 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 519 | Define DXF for IB Electronic cards | mechanical Engineer(1) | N | 2023-03-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 283 | Design FTER MB PCB Layout | PCB layout sub contractor(1) | N | 2023-03-09 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 301 | Design FTER Disp. Module PCB Layout | PCB layout sub contractor(1) | N | 2023-03-09 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 319 | Design FTER KB PCB Layout | PCB layout sub contractor(1) | N | 2023-03-09 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 232 | Dev. MC Appl SW DROP 1 | SW Engineer(1) | N | 2023-03-09 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 350 | Define DXF for FTER Electronic cards | mechanical Engineer(1) | N | 2023-03-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1074 | Define DXF for GTER Electronic cards | mechanical Engineer(1) | N | 2023-03-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 382 | Design GTER Processor PCB Layout | PCB layout sub contractor(1) | N | 2023-03-15 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 501 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-15 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 86 | Design MC Processor PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 106 | Design MC Display PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 125 | Design MC Comm. computer PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 144 | Design MC MB PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 162 | Design MC Disp. Module PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 180 | Design MC LCD Module PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 198 | Design MC KB PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 216 | Design MC PS PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 401 | Design GTER MB PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 420 | Design GTER Disp. Module PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 439 | Design GTER KB PCB Layout | PCB layout sub contractor(1) | N | 2023-03-16 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 260 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-16 |  | NS | 25d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 994 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-16 |  | NS | 25d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Execution | 346 | Assemble FTER PS | Operations(1) | N | 2023-03-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Execution | 467 | Assemble GTER PS | Operations(1) | N | 2023-03-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 72 | Perform Simulator ATP | HW Engineer(1) | N | 2023-03-21 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G | IMS | 2022-12-05 |  | ACE Execution | 77 | Deliver Simulator to System ATP | PM(1) | N | 2023-03-22 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  |  | ACE Execution | 531 | Produce cables | Operations(1) | N | 2023-03-23 |  | NS | 20d |  |  |  |  | Guy Brill | 4d | Network | 0 | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 242 | Dev. MC Comm SW DROP 1 | SW Engineer(1) | N | 2023-03-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 246 | Dev. MC DispSW DROP 1 | SW Engineer(1) | N | 2023-03-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 256 | Produce MC Chassis parts | mechanical Engineer(1) | N | 2023-03-27 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 347 | Bring up FTER PS | HW Engineer(1) | N | 2023-03-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 356 | Produce FTER Chassis parts | mechanical Engineer(1) | N | 2023-03-27 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 468 | Bring up GTER PS | HW Engineer(1) | N | 2023-03-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 478 | Produce GTER Chassis parts | mechanical Engineer(1) | N | 2023-03-27 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Execution | 515 | Assemble IB MB | Operations(1) | N | 2023-03-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 236 | Dev. MC Appl SW DROP 4 | SW Engineer(1) | N | 2023-03-30 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 245 | Dev. MC Comm SW DROP 4 | SW Engineer(1) | N | 2023-03-30 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 249 | Dev. MC Disp SW DROP 4 | SW Engineer(1) | N | 2023-03-30 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 270 | Produce FTER Processor PCB | PCB production SC(1) | N | 2023-03-30 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 60 | Develop Cables HLD | System Engineer(1) | N | 2023-03-30 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 120 | Create a Schematic Design | HW Engineer(1) | Y | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 139 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 234 | Dev. MC Appl SW DROP 2 | SW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 637 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 652 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 667 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 682 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 696 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 711 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 726 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 741 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1010 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1026 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1042 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1058 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-30 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 288 | Produce FTER MB PCB | PCB production SC(1) | N | 2023-03-31 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 306 | Produce FTER Disp. Module PCB | PCB production SC(1) | N | 2023-03-31 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 324 | Produce FTER KB PCB | PCB production SC(1) | N | 2023-03-31 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 622 | Create a Schematic Design | HW Engineer(1) | N | 2023-03-31 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 525 | Produce IB Chassis parts | mechanical Engineer(1) | N | 2023-04-03 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 348 | Deliver FTER PS for FTER ATP | HW Engineer(1) | N | 2023-04-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 469 | Deliver GTER PS for FTER ATP | HW Engineer(1) | N | 2023-04-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 516 | Bring up IB MB | HW Engineer(1) | N | 2023-04-03 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 502 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-05 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 387 | Produce GTER Processor PCB | PCB production SC(1) | N | 2023-04-06 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 62 | Design MC Data Cable | HW Engineer(1) | N | 2023-04-06 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 63 | Design IB-Radio Cable | HW Engineer(1) | N | 2023-04-06 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 64 | Design TER Power Cable | HW Engineer(1) | N | 2023-04-06 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 65 | Design MC Power Cable | HW Engineer(1) | N | 2023-04-06 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 536 | Design TER Data Cable | HW Engineer(1) | N | 2023-04-06 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 92 | Produce MC Processor PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 111 | Produce MC Display PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 130 | Produce MC Comm. computer PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 149 | Produce MC MB PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 167 | Produce MC Disp. Module PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 185 | Produce MC LCD Module PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 203 | Produce MC KB PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 221 | Produce MC PS PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 406 | Produce GTER MB PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 425 | Produce GTER Disp. Module PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
R |  |  | Jacob | ACE Execution | 444 | Produce GTER KB PCB | PCB production SC(1) | N | 2023-04-07 |  | NS | 16d |  |  |  |  | Guy Brill | 16d | Network | 1 | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 503 | Prepare card CDR | HW Engineer(1) | N | 2023-04-07 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 257 | Assemble MC Chassis | mechanical Engineer(1) | N | 2023-04-10 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 357 | Assemble FTER Chassis | mechanical Engineer(1) | N | 2023-04-10 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 479 | Assemble GTER Chassis | mechanical Engineer(1) | N | 2023-04-10 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Execution | 517 | Deliver IB MB for IB ATP | HW Engineer(1) | N | 2023-04-10 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 239 | Dev. MC Infra SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 360 | Dev. FTER Infra SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 363 | Dev. FTER Comm SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 367 | Dev. FTER Appl SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 370 | Dev. FTER DispSW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1083 | Dev. GTER Infra SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1086 | Dev. GTER Comm SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1089 | Dev. GTER DispSW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1092 | Dev. GTER Appl SW DROP 1 | SW Engineer(1) | N | 2023-04-11 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 504 | Conduct card CDR | HW Engineer(1) | N | 2023-04-12 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 530 | Purchase cable material | Operations(1) | N | 2023-04-12 |  | NS | 45d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 258 | Deliver MC Chassis for MC ATP | mechanical Engineer(1) | N | 2023-04-13 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 358 | Deliver FTER Chassis for FTER ATP | mechanical Engineer(1) | N | 2023-04-13 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Execution | 480 | Deliver GTER Chassis for FTER ATP | mechanical Engineer(1) | N | 2023-04-13 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 505 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-13 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 521 | Detail Design the part | mechanical Engineer(1) | N | 2023-04-14 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 526 | Assemble GTER Chassis | mechanical Engineer(1) | N | 2023-04-17 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 73 | Develop Simulator HLD | System Engineer(1) | N | 2023-04-17 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 507 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-04-18 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Execution | 527 | Deliver IB Chassis for FTER ATP | mechanical Engineer(1) | N | 2023-04-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 67 | Perform Cables ATP | HW Engineer(1) | N | 2023-04-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 121 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 140 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 235 | Dev. MC Appl SW DROP 3 | SW Engineer(1) | N | 2023-04-20 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 243 | Dev. MC Comml SW DROP 2 | SW Engineer(1) | N | 2023-04-20 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 247 | Dev. MC Disp SW DROP 2 | SW Engineer(1) | N | 2023-04-20 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 261 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 638 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 653 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 668 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 683 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 697 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 712 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 727 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 742 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 995 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1011 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1027 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1043 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1059 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 55 | Perform IB ATP | HW Engineer(1) | N | 2023-04-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 274 | Assemble FTER Processor card | Operations(1) | N | 2023-04-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 623 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-21 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 292 | Assemble FTER MB | Operations(1) | N | 2023-04-24 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 310 | Assemble FTER Disp. Module | Operations(1) | N | 2023-04-24 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 328 | Assemble FTER KB | Operations(1) | N | 2023-04-24 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 81 | Release partial BOM (80%) | HW Engineer(1) | N | 2023-04-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 122 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 141 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 262 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 537 | Receive GFE Radios | PM(1) | N | 2023-04-24 |  | NS | 40d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 639 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 654 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 669 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 684 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 698 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 713 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 728 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 743 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 996 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1012 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1028 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1044 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1060 | Prepare card CDR | HW Engineer(1) | N | 2023-04-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | Test-pt | 8 | T3 | Default(1) | Y | 2023-04-25 |  | NS | 14d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 352 | Detail Design the part | mechanical Engineer(1) | N | 2023-04-25 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 624 | Prepare card CDR | HW Engineer(1) | N | 2023-04-25 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1076 | Detail Design the part | mechanical Engineer(1) | N | 2023-04-25 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 82 | Prepare card CDR | HW Engineer(1) | N | 2023-04-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 237 | Dev. MC Appl SW DROP 5 | SW Engineer(1) | N | 2023-04-27 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R | IMS | 2022-10-18 |  | ACE Execution | 76 | Deliver Cables to MC/FTER/GTER bring up | PM(1) | N | 2023-04-27 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 123 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 142 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 263 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 640 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 655 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 670 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 685 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 699 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 714 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 729 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 744 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 997 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1013 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1029 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1045 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1061 | Conduct card CDR | HW Engineer(1) | N | 2023-04-27 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R | IMS | 2022-10-20 |  | ACE Execution | 75 | Deliver IB to MC/FTER/GTER bring up | PM(1) | N | 2023-04-28 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | Elias | ACE Execution | 391 | Assemble GTER Processor card | Operations(1) | N | 2023-04-28 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 275 | Bring up FTER Processor card | HW Engineer(1) | N | 2023-04-28 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 124 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 143 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 252 | Detail Design the part | mechanical Engineer(1) | N | 2023-04-28 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 264 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 625 | Conduct card CDR | HW Engineer(1) | N | 2023-04-28 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 641 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 656 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 671 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 686 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 700 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 715 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 730 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 745 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 998 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1014 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1030 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1046 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1062 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-04-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 96 | Assemble MC Processor card | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 115 | Assemble MC Display computer | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 134 | Assemble MC Comm. computer card | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 153 | Assemble MC MB | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 171 | Assemble MC Disp. Module | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 189 | Assemble MC LCD Module | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 207 | Assemble MC KB | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 225 | Assemble MC PS | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 410 | Assemble GTER MB | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 429 | Assemble GTER Disp. Module | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Execution | 448 | Assemble GTER KB | Operations(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 293 | Bring up FTER MB | HW Engineer(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 311 | Bring up FTER Disp. Module | HW Engineer(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 329 | Bring up FTER KB | HW Engineer(1) | N | 2023-05-01 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 83 | Conduct card CDR | HW Engineer(1) | N | 2023-05-01 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 626 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-05-01 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 84 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2023-05-02 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 126 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 145 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 266 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 627 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 642 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 657 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 672 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 687 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 701 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 716 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 731 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 746 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 999 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1015 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1031 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1047 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1063 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-03 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 87 | Design PCB Layout | PCB layout sub contractor(1) | N | 2023-05-04 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 508 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-04 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 392 | Bring up GTER Processor card | HW Engineer(1) | N | 2023-05-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 276 | Deliver FTER Processor for FTER ATP | HW Engineer(1) | N | 2023-05-05 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 97 | Bring up MC Processor card | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 116 | Bring up MC Display Computer | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 135 | Bring up MC Comm. computer card | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 154 | Bring up MC MB | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 172 | Bring up MC Disp. Module | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 190 | Bring up MC LCD Module | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 208 | Bring up MC KB | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 226 | Bring up MC PS | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 411 | Bring up GTER MB | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 430 | Bring up GTER Disp. Module | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 449 | Bring up GTER KB | HW Engineer(1) | N | 2023-05-08 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 294 | Deliver FTER MB for FTER ATP | HW Engineer(1) | N | 2023-05-08 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 312 | Deliver FTER Disp. Module for FTER ATP | HW Engineer(1) | N | 2023-05-08 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 330 | Deliver FTER KB for FTER ATP | HW Engineer(1) | N | 2023-05-08 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 538 | Purchase Accessories | PM(1) | N | 2023-05-08 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 563 | FTER bring up | HW Engineer(1), SW Engineer(1) | N | 2023-05-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 240 | Dev. MC Infra SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 361 | Dev.FTER Infra SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 364 | Dev. FTER Comm SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 368 | Dev. FTER Appl SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 371 | Dev. FTER Disp SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 509 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-09 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1084 | Dev. GTER Infra SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1087 | Dev. GTER Comm SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1090 | Dev. GTER Disp SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1093 | Dev. GTER Appl SW DROP 2 | SW Engineer(1) | N | 2023-05-09 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 510 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-10 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 236 | Dev. MC Appl SW DROP 4 | SW Engineer(1) | N | 2023-05-11 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 393 | Deliver GTER Processor for GTER ATP | HW Engineer(1) | N | 2023-05-12 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 512 | Check Layout DFM | PCB production SC(1) | N | 2023-05-12 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 98 | Deliver MC Processor for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 117 | Deliver MC Display computer for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 136 | Deliver MC Comm. computer for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 155 | Deliver MC MB for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 173 | Deliver MC Disp. Module for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 191 | Deliver MC LCD Module for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 209 | Deliver MC KB for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 227 | Deliver MC PS for MC ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 412 | Deliver GTER MB for FTER ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 431 | Deliver GTER Disp. Module for FTER ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Execution | 450 | Deliver GTER KB for FTER ATP | HW Engineer(1) | N | 2023-05-15 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G | PT |  |  | Test-pt | 1 | pt | Default(1) | N | 2023-05-15 |  | NS | 2023-06-09 |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Execution | 583 | GTER bring up | HW Engineer(1), SW Engineer(1) | N | 2023-05-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 564 | FTER HW tests | HW Engineer(1) | N | 2023-05-16 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Execution | 38 | Perform FTER ATP | INT Engineer(1) | N | 2023-05-16 |  | NS | 15d |  |  |  |  | Guy Brill | 28d | Network | 0 | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 513 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-17 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 244 | Dev. MC Comm SW DROP 3 | SW Engineer(1) | N | 2023-05-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 248 | Dev. MCDisp SW DROP 3 | SW Engineer(1) | N | 2023-05-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 514 | PCB Production | PCB production SC(1) | N | 2023-05-19 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 88 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 127 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 146 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 267 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 628 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 643 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 658 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 673 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 688 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 702 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 717 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 732 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 747 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1000 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1016 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1032 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1048 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1064 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2023-05-22 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 584 | GTER HW tests | HW Engineer(1) | N | 2023-05-23 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 498 | Perform GTER ATP | INT Engineer(1) | N | 2023-05-23 |  | NS | 15d |  |  |  |  | Guy Brill | 26d | Network | 0 | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 522 | Prepare mechanical CDR | mechanical Engineer(1) | Y | 2023-05-23 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 129 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 148 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 269 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 630 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 645 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 660 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 675 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 690 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 704 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 719 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 734 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 749 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1002 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1018 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1034 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1050 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1066 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Execution | 238 | Dev. MC Appl SW DROP 6 | SW Engineer(1) | N | 2023-05-25 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 89 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 90 | Freeze electronic BOM | HW Engineer(1) | N | 2023-05-25 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 128 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 147 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 268 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 629 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 644 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 659 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 674 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 689 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 703 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 718 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 733 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 748 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1001 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1017 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1033 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1049 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1065 | Prepare Gerber files | HW Engineer(1) | N | 2023-05-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 131 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 150 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 271 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 523 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2023-05-26 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 631 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 646 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 661 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 676 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 691 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 705 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 720 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 735 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 750 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1003 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1019 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1035 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1051 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1067 | Check Layout DFM | PCB production SC(1) | N | 2023-05-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | Test-pt | 2 | T1 | Default(1) | N | 2023-05-29 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 93 | Check Layout DFM | PCB production SC(1) | N | 2023-05-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 524 | Freeze Chassis | mechanical Engineer(1) | N | 2023-05-30 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 132 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 151 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 272 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 525 | Produce IB Chassis parts | mechanical Engineer(1) | N | 2023-05-31 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 632 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 647 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 662 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 677 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 692 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 706 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 721 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 736 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 751 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1004 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1020 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1036 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1052 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1068 | Prepare panelization and masks | PCB production SC(1) | N | 2023-05-31 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 94 | Prepare panelization and masks | PCB production SC(1) | N | 2023-06-01 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 237 | Dev. MC Appl SW DROP 5 | SW Engineer(1) | N | 2023-06-01 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 133 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 152 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 273 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 633 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 648 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 663 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 678 | PCB Production | HW Engineer(0.5), Operations(0.5) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 693 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 707 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 722 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 737 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 752 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1005 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1021 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1037 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1053 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1069 | PCB Production | PCB production SC(1) | N | 2023-06-02 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 95 | PCB Production | PCB production SC(1) | N | 2023-06-05 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 515 | Assemble IB MB | Operations(1) | N | 2023-06-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G | IMS | 2022-12-15 |  | ACE Execution | 74 | Deliver FTER to System ATP | PM(1) | N | 2023-06-06 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 241 | Dev. MC Infra SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 253 | Prepare mechanical CDR | mechanical Engineer(1) | Y | 2023-06-06 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 353 | Prepare mechanical CDR | mechanical Engineer(1) | N | 2023-06-06 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 362 | Dev. FTER Infra SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 365 | Dev. FTER Comm SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 369 | Dev. FTER Appl SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 372 | Dev. FTER Disp SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1077 | Prepare mechanical CDR | mechanical Engineer(1) | N | 2023-06-06 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1085 | Dev. GTER Infra SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1088 | Dev. GTER Comm SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1091 | Dev. GTER Disp SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 1094 | Dev. GTER Appl SW DROP 3 | SW Engineer(1) | N | 2023-06-06 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 254 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2023-06-09 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 354 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2023-06-09 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1078 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2023-06-09 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | Test-pt | 3 | T2 | Default(1) | N | 2023-06-12 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 516 | Bring up IB MB | HW Engineer(1) | N | 2023-06-12 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R | IMS | 2022-12-27 |  | ACE Execution | 499 | Deliver GTER to System ATP | PM(1) | N | 2023-06-13 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 255 | Freeze MC Chassis | mechanical Engineer(1) | N | 2023-06-13 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 355 | Freeze FTER Chassis | mechanical Engineer(1) | N | 2023-06-13 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1079 | Freeze GTER Chassis | mechanical Engineer(1) | N | 2023-06-13 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 61 | Produce TER Data Cable | Operations(1) | N | 2023-06-14 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 256 | Produce MC Chassis parts | mechanical Engineer(1) | N | 2023-06-14 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 356 | Produce FTER Chassis parts | mechanical Engineer(1) | N | 2023-06-14 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 526 | Assemble IB Chassis | mechanical Engineer(1) | N | 2023-06-14 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 532 | Produce MC Power Cable | Operations(1) | N | 2023-06-14 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 533 | Produce TER Power Cable | Operations(1) | N | 2023-06-14 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 534 | Produce IB-Radio Cable | Operations(1) | N | 2023-06-14 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 535 | Produce MC Data Cable | Operations(1) | N | 2023-06-14 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1080 | Produce GTER Chassis parts | mechanical Engineer(1) | N | 2023-06-14 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 245 | Dev. MC Comm SW DROP 4 | SW Engineer(1) | N | 2023-06-15 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 249 | Dev. MC Disp SW DROP 4 | SW Engineer(1) | N | 2023-06-15 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 68 | Build BTN Network Env. | HW Engineer(1) | N | 2023-06-19 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 69 | Build BTY Network Env. | HW Engineer(1) | N | 2023-06-19 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 70 | Build FO Network Env. | HW Engineer(1) | N | 2023-06-19 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 134 | Assemble MC Comm. computer card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 153 | Assemble MC MB | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 207 | Assemble MC KB | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 225 | Assemble MC PS | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 274 | Assemble FTER Processor card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 517 | Deliver IB MB for IB ATP | HW Engineer(1) | N | 2023-06-19 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 527 | Deliver IB Chassis for IB ATP | mechanical Engineer(1) | N | 2023-06-19 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 634 | Assemble MC Display Computer card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 649 | Assemble MC Disp. Module | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 664 | Assemble MC LCD Module | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 708 | Assemble FTER MB card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 723 | Assemble FTER Disp. Module card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 738 | Assemble FTER Key Board | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 753 | Assemble FTER Power Supply | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 1006 | Assemble GTER Processor card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 1022 | Assemble GTER MB card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 1038 | Assemble GTER Disp. Module card | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 1054 | Assemble GTER Key Board | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 1070 | Assemble GTER Power Supply | Operations(1) | N | 2023-06-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 54 | Develop IB ATP | System Engineer(1) | N | 2023-06-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 66 | Develop Cables ATP | HW Engineer(1) | N | 2023-06-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Elias | ACE Demo detailed tasks 240822 | 96 | Assemble MC Processor card | Operations(1) | N | 2023-06-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1108 | IB bring up | HW Engineer(1), SW Engineer(1) | N | 2023-06-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1124 | Cables bring up | HW Engineer(1) | N | 2023-06-20 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 561 | MC bring up | HW Engineer(1), SW Engineer(1) | N | 2023-06-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Dov | ACE Demo detailed tasks 240822 | 238 | Dev. MC Appl SW DROP 6 | SW Engineer(1) | N | 2023-06-22 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 9 | Develop System Test Strategy | INT Engineer(1), System Engineer(1) | Y | 2023-06-26 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 135 | Bring up MC Comm. computer card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 154 | Bring up MC MB | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 208 | Bring up MC KB | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 226 | Bring up MC PS | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 275 | Bring up FTER Processor card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 635 | Bring up MC Display Computer card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 650 | Bring up MC Disp Module | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 665 | Bring up MC LCD Module | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 709 | Bring up FTER MB card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 724 | Bring up FTER Disp. Module card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 739 | Bring up FTER Key Board | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 754 | Bring up FTER Power Supply | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1007 | Bring up GTER Processor card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1023 | Bring up GTER MB card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1039 | Bring up GTER Disp. Module card | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1055 | Bring up GTER Key Board | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1071 | Bring up GTER Power Supply | HW Engineer(1) | N | 2023-06-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 55 | Perform IB ATP | HW Engineer(1) | N | 2023-06-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 67 | Perform Cables ATP | HW Engineer(1) | N | 2023-06-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 97 | Bring up MC Processor card | HW Engineer(1) | N | 2023-06-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 257 | Assemble MC Chassis | mechanical Engineer(1) | N | 2023-06-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 357 | Assemble FTER Chassis | mechanical Engineer(1) | N | 2023-06-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1081 | Assemble GTER Chassis | mechanical Engineer(1) | N | 2023-06-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | TM1 | testM | 1 | T1 | Buying(1) | Y | 2023-06-29 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Execution | 26 | Perform MC ATP | INT Engineer(2.4), SW Engineer(2.4) | N | 2023-06-29 |  | NS | 30d |  |  |  |  | Guy Brill | 26d | Network | 0 | 0
R |  |  |  | ACE Execution | 562 | MC HW tests | HW Engineer(1) | N | 2023-06-29 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 71 | Develop Simulator ATP | System Engineer(1) | N | 2023-06-29 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R | PE |  |  | testM | 3 | Project End |  | N | 2023-06-29 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 72 | Perform Simulator ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 136 | Deliver MC Comm. computer for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 155 | Deliver MC MB for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 209 | Deliver MC KB for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 227 | Deliver MC PS for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 258 | Deliver MC Chassis for MC ATP | mechanical Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 276 | Deliver FTER Processor for FTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 358 | Deliver FTER Chassis for FTER ATP | mechanical Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 636 | Deliver MC Display Computer for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 651 | Deliver MC Disp. Module for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 666 | Deliver MC LCD Module for MC ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 710 | Deliver FTER MB for FTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 725 | Deliver FTER Disp. Module for FTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 740 | Deliver FTER Key Board for FTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 755 | Deliver FTER Power Supply for FTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1008 | Deliver GTER Processor for GTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1024 | Deliver GTER MB for GTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1040 | Deliver GTER Disp. Module for GTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1056 | Deliver GTER Key Board for GTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 1072 | Deliver GTER Power Supply for GTER ATP | HW Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Sergey | ACE Demo detailed tasks 240822 | 1082 | Deliver GTER Chassis for GTER ATP | mechanical Engineer(1) | N | 2023-07-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G | IMS | 2022-10-20 |  | ACE Demo detailed tasks 240822 | 75 | Deliver IB to MC/FTER/GTER bring up | PM(1) | N | 2023-07-04 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G | IMS | 2022-10-18 |  | ACE Demo detailed tasks 240822 | 76 | Deliver Cables to MC/FTER/GTER bring up | PM(1) | N | 2023-07-04 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G | IMS | 2022-08-18 |  | ACE Demo detailed tasks 240822 | 77 | Deliver Simulator to MC/FTER/GTER Bring up | PM(1) | N | 2023-07-04 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  | Jacob | ACE Demo detailed tasks 240822 | 98 | Deliver MC Processor for MC ATP | HW Engineer(1) | N | 2023-07-04 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 563 | FTER bring up | HW Engineer(1), SW Engineer(1) | N | 2023-07-04 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1095 | GTER bring up | HW Engineer(1), SW Engineer(1) | N | 2023-07-04 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 561 | MC bring up | HW Engineer(1), SW Engineer(1) | N | 2023-07-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 12 | Develop MC ATP | System Engineer(1) | N | 2023-07-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 564 | FTER HW tests | HW Engineer(1) | N | 2023-07-11 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1096 | GTER HW tests | HW Engineer(1) | N | 2023-07-11 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1109 | IB HW tests | HW Engineer(1) | N | 2023-07-11 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1110 | Cables HW tests | HW Engineer(1) | N | 2023-07-11 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 562 | MC HW tests | HW Engineer(1) | N | 2023-07-12 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 37 | Develop FTER ATP | System Engineer(1) | N | 2023-07-12 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1097 | Develop GTER ATP | System Engineer(1) | N | 2023-07-12 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 554 | MC ATP Cycle 1 | INT Engineer(5) | N | 2023-07-13 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 10 | Develop System ATP | System Engineer(1) | N | 2023-07-17 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 566 | FTER ATP Cycle 1 | INT Engineer(5) | N | 2023-07-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1099 | GTER ATP Cycle 1 | INT Engineer(5) | N | 2023-07-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 555 | Bug fixes | SW Engineer(5) | N | 2023-07-20 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G | PE |  |  | Test-pt | 5 | Project End |  | N | 2023-07-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 567 | Bug fixes | SW Engineer(5) | N | 2023-07-26 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1100 | Bug fixes | SW Engineer(5) | N | 2023-07-26 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 556 | SW version freeze | SW Engineer(1) | N | 2023-08-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 557 | MC ATP Cycle 2 | INT Engineer(5) | N | 2023-08-04 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 568 | SW version freeze | SW Engineer(1) | N | 2023-08-09 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1101 | SW version freeze | SW Engineer(1) | N | 2023-08-09 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | gbrill | ACE Execution | 59 | Deliver MC to System ATP | PM(1) | N | 2023-08-10 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 569 | FTER ATP Cycle 2 | INT Engineer(5) | N | 2023-08-10 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1102 | GTER ATP Cycle 2 | INT Engineer(5) | N | 2023-08-10 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 56 | Perform System ATP | INT Engineer(5), SW Engineer(5) | N | 2023-08-11 |  | NS | 40d |  |  |  |  | Guy Brill | 26d | Network | 0 | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 558 | Bug fixes | SW Engineer(5) | N | 2023-08-11 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 570 | Bug fixes | SW Engineer(5) | N | 2023-08-17 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1103 | Bug fixes | SW Engineer(5) | N | 2023-08-17 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 565 | MC ATP 3 | INT Engineer(5) | N | 2023-08-18 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 572 | FTER ATP 3 | INT Engineer(2) | N | 2023-08-24 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1104 | GTER ATP 3 | INT Engineer(2) | N | 2023-08-24 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 560 | SW version release | SW Engineer(1) | N | 2023-08-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 573 | SW version release | SW Engineer(1) | N | 2023-08-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 1105 | SW version release | SW Engineer(1) | N | 2023-08-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G | IMS | 2022-07-11 | gbrill | ACE Demo detailed tasks 240822 | 59 | Deliver MC to System ATP | PM(1) | N | 2023-08-28 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G | IMS | 2022-12-15 |  | ACE Demo detailed tasks 240822 | 74 | Deliver FTER to System ATP | PM(1) | N | 2023-08-28 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 539 | System ATP Cycle 1 | INT Engineer(5) | N | 2023-08-28 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G | IMS | 2022-12-15 |  | ACE Demo detailed tasks 240822 | 1106 | Deliver GTER to System ATP | PM(1) | N | 2023-08-28 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 540 | Bug fixes | SW Engineer(5) | N | 2023-09-04 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Gama1 | 11 | Task1 | 2_2604_EM(1) | Y | 2023-09-06 |  | NS | 1d |  |  |  |  | Gama | 1d | Network | 1 | 0
R |  |  |  | Gama1 | 14 | T2 | 2_2604_EM(1) | N | 2023-09-07 |  | NS | 1d |  |  |  |  | Gama | 1d | Network | 1 | 0
R |  |  |  | Gama1 | 16 | T3 | 2_2604_EM(1) | N | 2023-09-08 |  | NS | 1d |  |  |  |  | Gama | 1d | Network | 1 | 0
R |  |  |  | Gama1 | 18 | T4 | 2_2604_EM(1) | N | 2023-09-11 |  | NS | 1d |  |  |  |  | Gama |  | Network |  | 0
R | IMS | 2023-08-31 |  | Gama1 | 19 | Internal Milestone | 2_2604_EM(1) | N | 2023-09-12 |  | NS | 0d |  |  |  |  | Gama |  |  |  | 0
R | PT |  |  | Gama1 | 22 | PT-Task | 2_2604_EM(1) | N | 2023-09-12 |  | NS | 2023-09-11 |  |  |  |  | Gama |  | Network |  | 0
R | PE |  |  | Gama1 | 24 | Project End |  | N | 2023-09-12 |  | NS | 0d |  |  |  |  | Gama |  |  |  | 0
R | CMS | 2023-08-31 |  | Gama1 | 20 | Completion Milestone |  | N | 2023-09-12 |  | NS | 0d |  |  |  |  | Gama |  |  |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 541 | SW version freeze | SW Engineer(1) | N | 2023-09-18 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 542 | System ATP Cycle 2 | INT Engineer(5) | N | 2023-09-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 543 | Bug fixes | SW Engineer(5) | N | 2023-09-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | GNM Stator AM | Chris_Product Enhancement | 4 | Define Product Maintainance Strategy | Project Engineer (GNF)(0.75) | N | 2023-10-04 | GNM Stator India | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator AM | Chris_Product Enhancement | 12 | Complete Core and End Winding Modeling - GN End Winding Challenge | Mechanical Stator Engineer (GNM)(1) | N | 2023-10-04 | GNM Stator India | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 14 | Remodel Blower Shroud | Acharya(1) | N | 2023-10-04 | GNM Stator AM | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator AM | Chris_Product Enhancement | 264 | SNET-Complete Core and End Winding Modeling - GN End Winding Challenge |  | Y | 2023-10-04 | GNM Stator India | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | TestSummary | 2 | Task1 | Civil(1) | Y | 2023-10-04 |  | NS | 10d |  |  |  |  | Concerto Admin | 1d | Network | 0 | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 574 | Perform System Customer ATP | INT Engineer(5) | N | 2023-10-04 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 545 | System Customer ATP | INT Engineer(5) | N | 2023-10-06 |  | NS | 6d |  |  |  |  | Guy Brill | 5d | Network | 0 | 0
R | SNET |  |  | Chris Project 3 | 3 | Detailed Design | Designer(1.4), Electrical Engineering(0.8), Mechanical Engineering(0.7) | N | 2023-10-06 |  | NS | 10d |  |  |  |  | Chris Timmer | 9d | Network | 0 | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 15 | Migrate and Model Bearing Assy | Acharya(1) | N | 2023-10-09 | GNM Stator AM | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 10 | Design and Create Product Definition - Main Lead Sub Assembly | Kulkami(1) | N | 2023-10-10 | GNM Stator AM | NS | 13d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 7 | Perform Frame Calculations | J(1) | N | 2023-10-10 | GNM Stator AM | NS | 13d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 8 | Design and Create Product Definition - Frame | Gupta S(1), Khan(1) | N | 2023-10-10 | GNM Stator AM | NS | 14d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator AM | Chris_Product Enhancement | 5 | Complete COE, Technical and Product Definition Support | Feeney(0.75), Flack(0.25), Holland(0.25), Project Engineer (GNF)(1) | N | 2023-10-10 | GNM Stator India | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | GNM Rotor India | Chris_Product Enhancement | 25 | Design and Complete Product Definition - RTW | Jain(0.7), Lutz(0.3) | N | 2023-10-10 | GNM Rotor AM, GNM Stator AM, GNM Stator India | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  |  | ACE Demo detailed tasks 240822 | 544 | SW version release | SW Engineer(1) | N | 2023-10-11 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detailed tasks 240822 | 553 | System packaging and delivery | PM(1) | N | 2023-10-12 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Execution | 553 | System packaging and delivery | PM(1) | N | 2023-10-16 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G | PE |  |  | ACE Demo detailed tasks 240822 | 593 | Project End |  | N | 2023-10-17 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  |  | TestSummary | 5 | Task2 | Civil(1) | N | 2023-10-18 |  | NS | 10d |  |  |  |  | Concerto Admin | 1d | Network | 0 | 0
R | PE |  |  | ACE Execution | 593 | Project End |  | N | 2023-10-18 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | CMS SNET | 2023-09-28 |  | Chris Project 3 | 12 | Completion Milestone |  | N | 2023-10-19 |  | NS | 0d |  |  |  |  | Chris Timmer |  |  |  | 0
R | PT |  |  | Chris Project 3 | 4 | Procurement & Manufacturing | Procurement Tech(1), Project Manager(1) | N | 2023-10-20 |  | NS | 2023-10-05 |  |  |  |  | Chris Timmer |  | Network |  | 0
R |  |  | GNM Rotor India | Chris_Product Enhancement | 26 | Design and Complete Product Definition - RTA | Jain(0.7), Lutz(0.3) | N | 2023-10-24 | GNM Rotor AM, GNM Stator AM, GNM Stator India | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 139 | Complete R5 Review - Main Lead Sub Assembly | Kulkami(1) | N | 2023-10-27 | GNM Stator AM | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator AM | Chris_Product Enhancement | 9 | Complete 118/55 ELD Support | Fu(1) | N | 2023-10-27 | GNM Stator India | NS | 12d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator AM | Chris_Product Enhancement | 17 | Design and Create Product Definition -Shipping Assembly | Yu(1) | N | 2023-10-27 | GNM Stator India | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 19 | Complete Stationary Excitation Assembly - Migrate | Khan(1) | N | 2023-10-27 | GNM Stator AM | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator AM | Chris_Product Enhancement | 16 | Design and Create Product Defintion - Instrumentation | Bansal I(1) | N | 2023-10-27 | GNM Stator India | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 231 | Conduct R3/R5 FTR - Frame | Khan(1) | N | 2023-10-30 | GNM Stator AM | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Rotor AM | Chris_Product Enhancement | 27 | Conduct R3/R5 Design Review | Feeney(0.25) | N | 2023-11-02 | GNM Rotor India, GNM Stator AM, GNM Stator India | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | SNET |  |  | Chris Project 3 | 5 | Build | Project Manager(1), Quality Tech(1) | N | 2023-11-03 |  | NS | 3d 2h |  |  |  |  | Chris Timmer |  | Network |  | 0
R | SNET |  |  | Chris Project 3 | 6 | Test | Automation Tech(1), Project Manager(1) | N | 2023-11-08 |  | NS | 2d |  |  |  |  | Chris Timmer |  | Network |  | 0
R | IMS SNET | 2023-10-26 |  | Chris Project 3 | 14 | Internal Milestone |  | N | 2023-11-08 |  | NS | 0d |  |  |  |  | Chris Timmer |  |  |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 21 | Complete Product Definition - Enclosure | Gupta S(1) | N | 2023-11-10 | GNM Stator AM | NS | 11d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | SNET |  |  | Chris Project 3 | 7 | Customer Acceptance | Procurement Tech(1), Project Manager(1) | N | 2023-11-10 |  | NS | 1d 2h |  |  |  |  | Chris Timmer |  | Network |  | 0
R | PE SNET |  |  | Chris Project 3 | 17 | Project End |  | N | 2023-11-13 |  | NS | 0d |  |  |  |  | Chris Timmer |  |  |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 13 | Complete Product Defintion - Stator Assembly | Dhiman(1) | N | 2023-11-14 | GNM Stator AM | NS | 6d |  |  |  |  | Concerto Admin |  | Network |  | 1
G | PE |  |  | TestSummary | 9 | Project End |  | N | 2023-11-14 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | CMS | 2022-06-27 | PMO PE | Chris_Product Enhancement | 75 | CMS-Conduct R3/R5 Design Review |  | N | 2023-11-15 | GNM Rotor AM | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 20 | Comlpete Shop Final Assembly | Dhiman(1) | N | 2023-11-22 | GNM Stator AM | NS | 11d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 22 | Complete Product Definiton -Cooler Cover | Khan(1) | N | 2023-11-27 | GNM Stator AM | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  |  | PMI1 Template MANPOWER 5 | 689 | P2: Disassembly - Interior | ARTISAN(4.7) | N | 2023-12-04 |  | NS | 4d 3.9h |  |  |  |  | Concerto Admin | 4d 3.9h | Volume of Work | 1 | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 23 | Complete Product Definition -Bearing Enclosure & Exciter Enclosure | Gupta S(1) | N | 2023-12-07 | GNM Stator AM | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 171 | Conduct R5 Review - Shop Final Assembly | Dhiman(1) | N | 2023-12-07 | GNM Stator AM | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  |  | PMI1 Template MANPOWER 5 | 58 | P3: Inspection | ARTISAN(4.7) | N | 2023-12-08 |  | NS | 3d 5.2h |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G | IMS | 2023-12-18 |  | PMI1 Template MANPOWER 5 | 634 | Disassembly Complete |  | N | 2023-12-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 616 | P4: Repair Placeholder | ARTISAN(4.7) | N | 2023-12-14 |  | NS | 10d |  |  |  |  | Concerto Admin | 24d 6.5h | Volume of Work | 0 | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2023-12-14 |  | NS | 7d 9h |  |  |  |  | Concerto Admin | 7d 9h | Volume of Work | 1 | 0
R | CMS | 2022-08-18 | PMO PE | Chris_Product Enhancement | 172 | CMS-Conduct R5 Review - Shop Final Assembly |  | N | 2023-12-20 | PMO PE | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 29 | Complete Enclosure Installation Field Drawing | Lotay(1) | N | 2023-12-21 | GNM Stator AM | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | GNM Stator India | Chris_Product Enhancement | 34 | Complete Transmittals | Kulkami(1) | N | 2023-12-21 | GNM Stator AM | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  |  | PMI1 Template MANPOWER 5 | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 503 | P4: Repair - Paint in repair | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 506 | P4: Repair - Zone 2T | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 507 | P4: Repair - Zone 2L | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2023-12-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 30 | Complete Cooler & Cooler Installation Drawing | Lotay(1) | N | 2023-12-26 | GNM Stator AM | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
G | CMS | 2023-12-26 |  | PMI1 Template MANPOWER 5 | 51 | Completion Milestone - End of Inspection Phase |  | N | 2023-12-26 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 31 | Complete Main Lead Field Assembly Drawing | Lotay(1) | N | 2023-12-29 | GNM Stator AM | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  |  | PMI1 Template MANPOWER 5 | 64 | P5: Assembly Phase | ARTISAN(4.7) | N | 2023-12-29 |  | NS | 2d 7.6h |  |  |  |  | Concerto Admin | 2d 7.6h | Volume of Work | 1 | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 32 | Complete Field Final Assembly Drawings | Lotay(1) | N | 2024-01-03 | GNM Stator AM | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  |  | PMI1 Template MANPOWER 5 | 710 | P5: Assembly Interiors | ARTISAN(4.7) | N | 2024-01-03 |  | NS | 7d 6.8h |  |  |  |  | Concerto Admin | 7d 6.8h | Volume of Work | 1 | 0
R |  |  | GNM Stator India | Chris_Product Enhancement | 33 | Conduct Field Final Assembly(FFA) R5 Review | Feeney(1) | N | 2024-01-08 | GNM Rotor AM, GNM Stator India | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | IMS | 2023-08-22 |  | Test for Integration MRO | 634 | Disassembly Complete |  | Y | 2024-01-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | CMS | 2023-08-29 |  | Test for Integration MRO | 51 | Completion Milestone - End of Inspection Phase |  | N | 2024-01-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 35 | P6: Post Ops Test Phase | ARTISAN(4.7) | N | 2024-01-16 |  | NS | 0d 11.7h |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G | IMS | 2024-02-08 |  | PMI1 Template MANPOWER 5 | 55 | Internal Milestone: Ready For Test |  | N | 2024-01-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | GNM Stator AM | Chris_Product Enhancement | 35 | Conduct Lessons Learned | Feeney(0.25), Sharma S(0.25) | N | 2024-01-17 | GNM Stator India | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 482 | P9: FCF Phase | ARTISAN(4.7) | N | 2024-01-17 |  | NS | 0d 5.2h |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R | PE |  | PMO PE | Chris_Product Enhancement | 592 | Project End |  | N | 2024-01-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 486 | P7: Paint | ARTISAN(3) | N | 2024-01-17 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G | IMS | 2024-02-09 |  | PMI1 Template MANPOWER 5 | 633 | Ready for Paint |  | N | 2024-01-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | PMO PE | Chris_Product Enhancement | 36 | Project End | Sharma S(1) | N | 2024-01-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Test for Integration MRO | 64 | P5: Assembly Phase | ARTISAN(5) | N | 2024-01-19 |  | NS | 8d 6.4h |  |  |  |  | Concerto Admin | 12d 8.8h | Volume of Work | 1 | 0
G |  |  |  | PMI1 Template MANPOWER 5 | 481 | P8: Final Processing | ARTISAN(3) | N | 2024-01-24 |  | NS | 1d 1.3h |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | Test for Integration MRO | 35 | P6: Post Ops Test Phase | ARTISAN(5) | N | 2024-02-01 |  | NS | 0d 7.9h |  |  |  |  | Concerto Admin | 0d 11.8h | Volume of Work | 1 | 0
R | IMS | 2023-10-25 |  | Test for Integration MRO | 55 | Internal Milestone: Ready For Test |  | N | 2024-02-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 1 | P0: Pre-Induction | ARTISAN(6.6) | N | 2024-02-01 |  | NS | 1d 0.6h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Test for Integration MRO | 482 | P9: FCF Phase | ARTISAN(5) | N | 2024-02-02 |  | NS | 0d 5.2h |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | Test for Integration MRO | 486 | P7: Paint | ARTISAN(2) | N | 2024-02-02 |  | NS | 1d 8.6h |  |  |  |  | Concerto Admin | 2d 6.2h | Volume of Work | 1 | 0
R | IMS | 2023-10-26 |  | Test for Integration MRO | 633 | Ready for Paint |  | N | 2024-02-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 71 | P1: Induction | ARTISAN(6.6) | N | 2024-02-02 |  | NS | 1d 4h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-02-05 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 904 | P0: Pre-Induction Complete |  | N | 2024-02-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test for Integration MRO | 481 | P8: Final Processing | ARTISAN(5) | N | 2024-02-06 |  | NS | 0d 4.4h |  |  |  |  | Concerto Admin | 0d 6.5h | Volume of Work | 1 | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 57 | P2: Disassembly - Pre Power Off | ARTISAN(6.6) | N | 2024-02-06 |  | NS | 3d 9.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-02-08 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 905 | P1: Induction Complete |  | N | 2024-02-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Test for Integration MRO | 630 | Project End |  | N | 2024-02-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 501 | P2: Disassembly - Post Power Off | ARTISAN(6.6) | N | 2024-02-09 |  | NS | 0d 10.4h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-02-15 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 906 | P2: Disassembly - Pre Power Off Complete |  | N | 2024-02-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 58 | P3: Inspection | ARTISAN(6.6) | N | 2024-02-12 |  | NS | 2d 1.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-02-16 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 634 | P2: Disassembly - Post Power Off Complete | ARTISAN(1) | N | 2024-02-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 616 | P4: Repair Placeholder | ARTISAN(6.6) | N | 2024-02-14 |  | NS | 11d 9.2h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | CMS | 2024-02-22 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 51 | P3: Inspection Complete |  | N | 2024-02-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | PMI1 Template MANPOWER 5 | 630 | Project End |  | N | 2024-02-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2024-02-29 |  | NS | 1d 5.2h |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(2) | N | 2024-02-29 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 503 | P4: Repair - Paint in repair | ARTISAN(2) | N | 2024-02-29 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d 5.5h |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 506 | P4: Repair - Zone 2T | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d 2h |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d 0.8h |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d 0.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 507 | P4: Repair - Zone 2L | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2024-03-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 64 | P5: Assembly Phase | ARTISAN(6.6) | N | 2024-03-04 |  | NS | 6d 0.2h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-03-19 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 844 | P4: Repair Complete | ARTISAN(1) | N | 2024-03-04 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 35 | P6: Post Ops Test Phase | ARTISAN(6.6) | N | 2024-03-12 |  | NS | 0d 9.4h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-04-01 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 55 | P5: Assembly Complete | ARTISAN(1) | N | 2024-03-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 486 | P7: Paint | ARTISAN(3) | N | 2024-03-13 |  | NS | 3d 6.5h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-04-02 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 907 | P6: Post Ops Test Phase Complete |  | N | 2024-03-13 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 481 | P8 and P9: Final Processing and FCF | ARTISAN(6.6) | N | 2024-03-18 |  | NS | 0d 2.4h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-04-09 |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 908 | P7: Paint Complete |  | N | 2024-03-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | V1 S07 169181 PMI-1_2024_1_24_10_2_47 | 630 | P8 and P9: Final Processing and FCF Complete |  | N | 2024-04-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | SNET |  |  | Navy Cloud Pilot Deployment | 11 | Phase 3 - Concerto Setup | Government(0.1), Realization(1.1) | Y | 2024-04-10 |  | NS | 15d |  |  |  |  | Michael Hamlin | 22d | Network | 1 | 0
R |  |  |  | Navy Cloud Pilot Deployment | 19 | Phase 4 - System Testing | Realization(2) | N | 2024-05-01 |  | NS | 3d |  |  |  |  | Michael Hamlin | 3d | Network | 0 | 0
R |  |  |  | Navy Cloud Pilot Deployment | 49 | NAVSEA 08 Approval for U-NNPI Data | Government(1) | N | 2024-05-01 |  | NS | 25d |  |  |  |  | Michael Hamlin | 25d | Network | 0 | 0
R | PE |  |  | Navy Cloud Pilot Deployment | 51 | Project End |  | N | 2024-05-03 |  | NS | 0d |  |  |  |  | Michael Hamlin |  |  |  | 0
R |  |  |  | Navy Cloud Pilot Deployment | 23 | Phase 5 - Government Testing | Government(1), Herdt(1), Realization(2) | N | 2024-06-05 |  | NS | 4d |  |  |  |  | Michael Hamlin | 5d | Network | 1 | 0
R | CMS | 2024-04-19 |  | Navy Cloud Pilot Deployment | 32 | GAT Complete |  | N | 2024-06-10 |  | NS | 0d |  |  |  |  | Michael Hamlin |  |  |  | 0
R |  |  |  | `MRO | 71 | P1: Induction | ARTISAN(6) | N | 2024-07-18 |  | NS | 1d 5.9h |  |  |  |  | Deepak Jha | 2d 2.2h | Volume of Work | 0 | 0
R |  |  |  | `MRO | 57 | P2: Disassembly - Pre Power Off | ARTISAN(6.3) | N | 2024-07-19 |  | NS | 3d 12.8h |  |  |  |  | Deepak Jha | 5d 12.4h | Volume of Work | 1 | 0
R |  |  |  | `MRO | 501 | P2: Disassembly - Post Power Off | ARTISAN(6) | N | 2024-07-25 |  | NS | 0d 11.5h |  |  |  |  | Deepak Jha | 1d 4.2h | Volume of Work | 0 | 0
R |  |  |  | `MRO | 58 | P3: Inspection | ARTISAN(6) | N | 2024-07-26 |  | NS | 2d 5.7h |  |  |  |  | Deepak Jha | 3d 8.4h | Volume of Work | 1 | 0
R | IMS | 2024-03-28 |  | `MRO | 634 | Disassembly Complete | ARTISAN(1) | N | 2024-07-26 |  | NS | 0d |  |  |  |  | Deepak Jha |  |  |  | 0
R |  |  |  | `MRO | 616 | P4: Repair Placeholder | ARTISAN(6) | N | 2024-07-30 |  | NS | 12d 5.9h |  |  |  |  | Deepak Jha | 18d 7.6h | Volume of Work | 1 | 0
R |  |  |  | `MRO | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 503 | P4: Repair - Paint in repair | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 506 | P4: Repair - Zone 2T | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 507 | P4: Repair - Zone 2L | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R |  |  |  | `MRO | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2024-07-30 |  | NS | 1d |  |  |  |  | Deepak Jha |  | Volume of Work |  | 0
R | CMS | 2024-04-02 |  | `MRO | 51 | Inspection Complete |  | N | 2024-07-30 |  | NS | 0d |  |  |  |  | Deepak Jha |  |  |  | 0
R |  |  |  | `MRO | 64 | P5: Assembly Phase | ARTISAN(6) | N | 2024-08-16 |  | NS | 6d 6.5h |  |  |  |  | Deepak Jha | 9d 9.1h | Volume of Work | 0 | 0
R | IMS | 2024-04-29 |  | `MRO | 844 | Repair Complete | ARTISAN(1) | N | 2024-08-16 |  | NS | 0d |  |  |  |  | Deepak Jha |  |  |  | 0
R |  |  |  | `MRO | 35 | P6: Post Ops Test Phase | ARTISAN(6) | N | 2024-08-26 |  | NS | 0d 10.8h |  |  |  |  | Deepak Jha | 1d 3.2h | Volume of Work | 0 | 0
R | IMS | 2024-05-13 |  | `MRO | 55 | Assembly Complete | ARTISAN(1) | N | 2024-08-26 |  | NS | 0d |  |  |  |  | Deepak Jha |  |  |  | 0
R |  |  |  | `MRO | 486 | P7: Paint | ARTISAN(3) | N | 2024-08-27 |  | NS | 5d |  |  |  |  | Deepak Jha | 1d 7.1h | Volume of Work | 0 | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 1904 | Induction, Preservation, Defuel | 629_ACM(1), 629_AE(1), 629_ASI(2), 629_E&E(1) | N | 2024-08-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | IMS | 2022-06-06 | PS | T44_February_2019 | 3292 | IMS-Release to A0=Induction |  | Y | 2024-08-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Disassembly | T44_February_2019 | 1905 | Pre-Strip | 629_ACM(3), 629_AE(1), 629_SMM(1) | N | 2024-09-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | IMS | 2022-06-08 | PS | T44_February_2019 | 2767 | IMS-Release to B0=Pre-Strip Disassembly |  | N | 2024-09-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  |  | `MRO | 481 | P8: Final Processing | ARTISAN(6) | N | 2024-09-04 |  | NS | 0d 3h |  |  |  |  | Deepak Jha | 0d 4.5h | Volume of Work | 0 | 0
R | PE |  |  | `MRO | 630 | PMI Complete |  | N | 2024-09-04 |  | NS | 0d |  |  |  |  | Deepak Jha |  |  |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 2653 | Remove Flight Control Surfcaces | 629_ACM(2) | N | 2024-09-05 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | Project 01 | 1 | T1 | COHU A(3) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | PT Testing | 1 | Kickoff | COHU A(1) | Y | 2024-09-09 |  | NS | 0d 23.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S06 1 86 | 1 | Pre Repair | ARTISAN(14) | Y | 2024-09-09 |  | NS | 23d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | TaskManager | V1 S08 1 82 | 1 | Pre Repair | ARTISAN(14) | Y | 2024-09-09 |  | NS | 23d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S09 1 87 | 1 | Pre Repair | ARTISAN(14) | Y | 2024-09-09 |  | NS | 23d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S11 1 89 | 1 | Pre Repair | ARTISAN(14) | Y | 2024-09-09 |  | NS | 23d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Strip_Shop | T44_February_2019 | 1906 | Strip A/C | Strip_Shop(2) | N | 2024-09-09 |  | NS | 12d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | IMS | 2022-06-14 | PS | T44_February_2019 | 2768 | IMS-Release to C0=Strip & Prime | Hold(1) | N | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | TaskManager | ACE Demo detiled tasks 240822_RZ | 8 | Develop System HLD | System Engineer(1) | Y | 2024-09-09 |  | NS | 1d |  |  |  |  | Guy Brill | 1d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 8 | Develop System HLD | System Engineer(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R | SNET |  |  | ACE Demo 240822 | 8 | Develop System HLD | System Engineer(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 522 | Prepare mechanical CDR | mechanical Engineer(1) | Y | 2024-09-09 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 253 | Prepare mechanical CDR | mechanical Engineer(1) | Y | 2024-09-09 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | REEL TEST | 1 | P&ID PTH 1 | Process Engineer #1(1) | Y | 2024-09-09 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | REEL TEST | 9 | P&IDs (PTH 1to 4) | Process Engineer #2(1) | Y | 2024-09-09 |  | NS | 5d 2.8h |  |  |  |  | Concerto Admin | 8d | Network | 1 | 0
R |  |  |  | Test-Chains | 1 | T1 | Default(1) | Y | 2024-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Test-Chains | 8 | T4 | Civil(1) | Y | 2024-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | 1+Task | 8 | T2 | A(1) | Y | 2024-09-09 |  | NS | 2d |  |  |  |  | PM2 | 2d | WIP | 1 | 1
R |  |  | Efi | ACE Demo 2-Tier | 11 | Develop MC HLD | System Engineer(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Test-Purchaing task | 1 | Task-1 | Engineering(2), Finishing(0) | Y | 2024-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 0 | 0
R |  |  |  | SUBTASK-RTS-NETWORK | 1 | Task-1 | Default(1) | Y | 2024-09-09 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d | Network | 1 | 0
R |  |  | TaskManager | v2_22_DEV | 42 | ELK | Dev ADBA(1) | Y | 2024-09-09 | bscott, ProjectParticipant | NS | 10d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | YairA_T | v2_22_DEV | 123 | Route Catalog | Dev Export/CMS(1) | Y | 2024-09-09 |  | NS | 10d |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | TaskManager | v2_22_DEV | 240 | US Customs Regulation | ABAP Programmer(2), Asher(1), Dev CCM/ETT/BIDZ(1), Zali(1) | Y | 2024-09-09 | ProjectParticipant, TaskParticipant | NS | 10d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | TaskManager | v2_22_DEV | 148 | FT | Dev Export/CMS(1) | Y | 2024-09-09 |  | NS | 1d 4h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Zina_T | v2_22_DEV | 51 | Route restrictions | Dev Quotation(1) | Y | 2024-09-09 |  | NS | 2d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Romi_T | v2_22_DEV | 80 | ORBCOMM | Dev SOA(1) | Y | 2024-09-09 |  | NS | 10d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Hava_T | v2_22_DEV | 170 | Maintenance | Dev Informatica(1) | Y | 2024-09-09 |  | NS | 8d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Eitan_T | v2_22_DEV | 13 | Crystal | Dev Crystal(1) | Y | 2024-09-09 |  | NS | 8d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Zina_T | v2_22_DEV | 155 | Email 2 Sales(L2A) | Dev Quotation(1) | Y | 2024-09-09 |  | NS | 7d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Johny_T | v2_22_DEV | 55 | Cyber Readiness | Dev AgentCloud(1) | Y | 2024-09-09 |  | NS | 2d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Lior_T | v2_22_DEV | 144 | Invoice | Dev Export/CMS(1) | Y | 2024-09-09 |  | NS | 4d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Hava_T | v2_22_DEV | 76 | CRM | Dev Informatica(1) | Y | 2024-09-09 |  | NS | 4d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | Romi_T | v2_22_DEV | 243 | SAP HR | Dev SOA(1) | Y | 2024-09-09 |  | NS | 4d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Zali_T | v2_22_DEV | 98 | Additional 1 | Dev Layouts(1) | Y | 2024-09-09 |  | NS | 0d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | Romi_T | v2_22_DEV | 88 | Demurrage | Dev SOA(1) | Y | 2024-09-09 |  | NS | 1d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Romi_T | v2_22_DEV | 186 | OKAPI | Dev SOA(1) | Y | 2024-09-09 |  | NS | 0d 0.8h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | Penchard v1 | 1 | Communication and buy in ready | Default(1) | Y | 2024-09-09 |  | NS | 4d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  |  | Penchard v1 | 11 | Elevate Capacity - Set the 3rd CNC up | Default(1) | Y | 2024-09-09 |  | NS | 14d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  |  | 169425 | 26 | Purge Fuel Cells | 1910(1), 8800(2), 8852(4) | Y | 2024-09-09 |  | NS | 2d |  |  |  |  | Concerto Admin | 3d 0.5h | Volume of Work | 0 | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 364 | Engineering - Select Design Engineer | Engineering Manager(1) | Y | 2024-09-09 | BillB | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | W9585 - 9917-11-100 2-Tier Example | 452 | Engineering | Customer(0.3), Engineering(0.9), Engineering Manager(0) | Y | 2024-09-09 |  | NS | 18d 0.1h |  |  |  |  | Concerto Admin | 18d 0.1h | Network | 1 | 0
R |  |  |  | Blank | 1 | T1 | HW Engineer(1) | Y | 2024-09-09 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3575 | Final Process Rating Sheets KG00001787 | Default Resource(1) | Y | 2024-09-09 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3683 | Final Process Rating Sheets KG00003924 | Default Resource(1) | Y | 2024-09-09 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3791 | Final Process Rating Sheets KG00014889 | Default Resource(1) | Y | 2024-09-09 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3899 | Final Process Rating Sheets KG00070783 | Default Resource(1) | Y | 2024-09-09 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jefe de Proyecto | EC-MRI | 2 | DISASSEMBLY/INSPECTION | Interior(2), Mechanical(20), Sheet Metal(2) | N | 2024-09-09 |  | NS | 8d |  |  |  |  | Manuel Alloza | 0d | WIP | 0 | 0
R |  |  | Jefe de Proyecto | EC-MRI | 24 | SERVICE BULLETIN |  | Y | 2024-09-09 |  | NS | 6d |  |  |  |  | Manuel Alloza | 0d | WIP | 0 | 0
R |  |  |  | EC-MRI | 32 | NONPHASE |  | Y | 2024-09-09 |  | NS | 2d |  |  |  |  | Manuel Alloza | 0d | Network | 0 | 0
R |  |  |  | Test11 | 1 | BE Main Equipment | DHD(1) | Y | 2024-09-09 |  | NS | 10d |  |  |  |  | Deepak Jha | 1d | Network | 0 | 1
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10394 | PCB140110V5_REV1 - Hardware verification | R&D_Hardware(1) | Y | 2024-09-09 | jaco.bester, robin.davis | NS | 4d 4h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8913 | HW Approval (D1679A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3609 | Layout completion (D1682A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 50d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8947 | HW Approval (D1682A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8954 | HW Approval (D1742A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11886 | Design (Enclosure Back plate) | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3604 | BOM Review Q&R (D1682A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10512 | Pre - Mechanical Requirement definition (Cell cabinet x2) | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8278 | MCU Hybrid SW readiness (D1277A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11994 | Mech fan procurement for Mech Batch | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | SNET |  | Noy.B | Majoris - 1 Mega INV_04-04_14-52 | 5212 | SNET - Transformer (Proto, 2 units) Production Complete | Utility(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11596 | Mech Batch - Transformer assembly to the 2 Prototypes | Mechanics(1) | N | 2024-09-09 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9419 | CDR | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11589 | Cell Standalone - block 1 development | SW(1) | Y | 2024-09-09 |  | NS | 50d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11475 | LV Digital Hybrid SW readiness (D1330B) | SW(1) | Y | 2024-09-09 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3433 | HW Bring Up Test plan review and approved (D1740A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11465 | MV Digital Hybrid SW readiness (D1330B) | SW(1) | Y | 2024-09-09 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3037 | Received ATP 90% (Cell level) | ATE(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3947 | Design (Connectivity - LV Unit) | ATE(1) | N | 2024-09-09 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | TestIMS | 1 | T1 | Default(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 24 | Procurement of brackets | Hardware and electrical installer(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | TestNilesh2 | 1 | t1 | Default(1) | Y | 2024-09-09 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Glow Lab | 61 | Handover of documentation and feedback | Glow Lab(1), Synergic - SME(1) | Y | 2024-09-09 |  | NS | 0d 4h |  |  |  |  | Jaco |  | Network |  | 0
G |  |  |  | ACE Demo detiled tasks 240822_RZ | 9 | Develop System Test Strategy | INT Engineer(1), System Engineer(1) | Y | 2024-09-09 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822_RZ | 9 | Develop System Test Strategy | INT Engineer(1), System Engineer(1) | Y | 2024-09-09 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822 | 9 | Develop System Test Strategy | INT Engineer(1), System Engineer(1) | Y | 2024-09-09 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Uri.Y | Majoris - 1 Mega INV_04-04_14-52 | 1194 | Preliminary Design Review (PDR) | Utility(1) | N | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 1625 | BOM Review Q&R (D1739A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Uri.Y | Majoris - 1 Mega INV_04-04_14-52 | 2699 | Product Requirements Document (PRD) | Utility(1) | N | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Uri.Y | Majoris - 1 Mega INV_04-04_14-52 | 2710 | Marketing Product Requirements Document (MPRD) | Utility(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Doron.yo | Majoris - 1 Mega INV_04-04_14-52 | 2796 | configuration (System Engineering) | Utility(1) | N | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Doron.yo | Majoris - 1 Mega INV_04-04_14-52 | 2797 | System missions (System Engineering) | Utility(1) | N | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2842 | Receiving samples and information from Mech (GPO3 parts) | Material(1) | N | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3268 | Specifications (Hilkar transformer) | Magnetic(1) | N | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3269 | New chock spec preparation (Elec & Mech) (Hilkar transformer) | Magnetic(1) | N | 2024-09-09 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3404 | BOM Review by Q&R (AP1740A-PB-01-LV) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3454 | BOM Review by Q&R (AP1680A-CP-01-LV) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3504 | BOM Review Q&R (D1742A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3554 | BOM Review Q&R (D1541B) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3654 | BOM Review Q&R (D1738A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3704 | BOM Review Q&R (D1741A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3754 | BOM Review by Q&R (D1679A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3804 | BOM Review by Q&R (D1940A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3930 | Design FT (B2B) | ATE(1) | Y | 2024-09-09 |  | NS | 45d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3939 | Design (Hipot - LV Unit) | ATE(1) | N | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.p | Majoris - 1 Mega INV_04-04_14-52 | 8850 | Potting process selection for trails | Material(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8907 | Component sampels (D1940A) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | SNET |  | Noy.B | Majoris - 1 Mega INV_04-04_14-52 | 9123 | SNET - (D1733A) work start | Utility(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9124 | HW Design - from product and system + requierments (D1733A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9147 | IGBTs TO-247 Assembly Jig (NPI Ops) (D1733A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | SNET |  | Noy.B | Majoris - 1 Mega INV_04-04_14-52 | 9163 | SNET - (D1737A) work start | Utility(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9187 | IGBTs TO-247 Assembly Jig (NPI Ops) (D1737A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | SNET |  | Noy.B | Majoris - 1 Mega INV_04-04_14-52 | 9203 | SNET - (D1715A) work start | Utility(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9204 | HW Design - from product and system + requirements (D1715A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9227 | IGBTs TO-247 Assembly Jig (NPI Ops) (D1715A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | SNET |  | Noy.B | Majoris - 1 Mega INV_04-04_14-52 | 9244 | SNET - (D1421B) work start | Utility(1) | Y | 2024-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9245 | HW Design - from product and system + requirements (D1421B) | Utility(1) | N | 2024-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9268 | IGBTs TO-247 Assembly Jig (NPI Ops) (D1421B) | Utility(1) | N | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9323 | CDR Approval (Transformer prototype) | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9324 | Packing Preparation (Transformer) | Mechanics(1) | N | 2024-09-09 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9326 | PO Preparation Process + Sending (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-09-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9447 | PCB automation testing (LV AC CAPS (D1680A)) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9460 | Pre - Mechanical Requirement definition (LV Cabinet x2) | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9485 | Pre - Mechanical Requirement definition (MV Cabinet x2) | Mechanics(1) | Y | 2024-09-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9895 | ATP Preparation 90% (D1976A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9900 | BOM 90% (D1976A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9901 | BOM Review by Q&R (D1976A) | QnR(1) | N | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9912 | HW Bring Up Test plan review and approved (D1976A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9948 | Design (Hipot) | ATE(1) | N | 2024-09-09 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9952 | Design (Connectivity) | ATE(1) | N | 2024-09-09 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9990 | Core design material review | Material(1) | N | 2024-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9992 | Review and approval of SE transformer design | Material(1) | N | 2024-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10227 | PD tests for Trasfor prototype | Utility(1) | N | 2024-09-09 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10250 | Design (Hipot - MV Unit) | ATE(1) | N | 2024-09-09 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10254 | Design (Connectivity - MV Unit) | ATE(1) | N | 2024-09-09 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | louis.loots | Smart PowerPack_05-09_07-06 | 10289 | PCB140110V3_REV3 - PCB Manufacturing Bosco & Delivery | External China(1) | Y | 2024-09-09 | tommy.mulder | NS | 12d |  |  |  |  | Christo Wentzel |  | Network |  | 0
G |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10344 | Update Solar Panel selection Excel file | R&D_Managers(1) | Y | 2024-09-09 | johann.geldenhuys | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 1
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 10475 | BOM Review Q&R (D1710B) | QnR(1) | Y | 2024-09-09 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10492 | Mech kit - Busbars (D1710B) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 10527 | Grid standart definition | Certification(1) | Y | 2024-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11160 | Specifications (Choke for ER caps (4081PQ2620)) | Magnetic(1) | Y | 2024-09-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11489 | Design Review (D1976A) | Utility(1) | Y | 2024-09-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11491 | ECO of PCB (D1976A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11522 | HW Design - from product and system + requierments (D1737A) | Utility(1) | N | 2024-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 425 | Engineering - Create Initial Design | Engineering(1) | N | 2024-09-09 | Designer | NS | 8d 6.2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Wisam_T | v2_22_DEV | 165 | Route Catalog | Dev ADBA(1) | N | 2024-09-09 |  | NS | 6d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | Olga_T | v2_22_DEV | 23 | EDI | Dev Import(1) | N | 2024-09-09 |  | NS | 2d |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | Example MRO Project | 58 | P3: Inspection | ARTISAN(7) | N | 2024-09-09 |  | NS | 1d 8h |  |  |  |  | Concerto Admin | 2d 5.3h | Volume of Work | 1 | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3542 | Transmit KG00001787 Final Drawings w/ Rating Sheet to Customer | Project Manager Group KG NA(1) | N | 2024-09-09 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Zali_T | v2_22_DEV | 99 | Additional 1 | Dev Layouts(1) | N | 2024-09-09 |  | NS | 0d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  |  | PT Testing | 2 | Material Booking | COHU A(1) | N | 2024-09-09 |  | NS | 0d 23.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 71 | P1: Induction | ARTISAN(6) | N | 2024-09-10 |  | NS | 1d 5.9h |  |  |  |  | Concerto Admin | 2d 2.2h | Volume of Work | 0 | 0
R |  |  |  | Test-Chains | 2 | T2 | Default(1) | N | 2024-09-10 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  |  | Test-Purchaing task | 4 | Task-2 | Default(1) | N | 2024-09-10 |  | NS | 2024-02-27 |  |  |  |  | Concerto Admin | 11d | Network |  | 0
R |  |  | Wisam_T | v2_22_DEV | 164 | ZimGuard | Dev ADBA(1) | N | 2024-09-10 |  | NS | 4d |  |  |  |  | ProjectManager1 |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9913 | Design (D1976A Setup) | Utility(1) | N | 2024-09-10 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9988 | Define core materials (adhesives) | Material(1) | N | 2024-09-10 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10017 | Mold design completed | Material(1) | N | 2024-09-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 10522 | Setup Design | Certification(1) | N | 2024-09-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | a.lee | RZTest_AWL027177_20230912 | 3615 | Equipment Engineering Review - KG00001787 | Default Resource(1) | N | 2024-09-10 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 71 | P1: Induction | ARTISAN(5.9) | N | 2024-09-10 |  | NS | 1d 6h |  |  |  |  | Concerto Admin | 6d 3h | Network | 0 | 0
R | IMS | 2024-03-14 |  | V1 S07 169181 PMI-1_2024 | 920 | P0: Pre-Induction Complete |  | N | 2024-09-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | IMS | 2024-03-14 |  | V1 S05 169185 PMI-1 R2 | 634 | Disassembly Complete |  | N | 2024-09-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Romi_T | v2_22_DEV | 84 | B2A (Print BL) | Dev SOA(1) | N | 2024-09-10 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | REEL TEST | 2 | P&ID PTH 2 | Process Engineer #1(1) | Y | 2024-09-10 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3936 | Customer Response and Markup Evaluation - KG00070783 Rev 0 Drawings | Default Resource(1) | N | 2024-09-10 |  | NS | 2023-07-27 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2023-09-12 | t.morris | RZTest_AWL027177_20230912 | 3938 | KG00070783 Rev 0 Drawing Submittal Milestone *CS 09/12/2023 |  | N | 2024-09-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | n.moyer | RZTest_AWL027177_20230912 | 4772 | Equipment Engineering Review - KG00003924 (-005) | Designer Group - Wichita and Mumbai(0.5), EQE Tray SME(0.5) | N | 2024-09-10 |  | NS | 2d 5.1h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3650 | Transmit KG00003924 Final Drawings w/ Rating Sheet to Customer | Project Manager Group KG NA(1) | N | 2024-09-10 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Romi_T | v2_22_DEV | 178 | P2P | Dev SOA(1) | N | 2024-09-10 |  | NS | 2d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Zali_T | v2_22_DEV | 100 | Additional 1 | Dev Layouts(1) | N | 2024-09-10 |  | NS | 0d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R | PT |  |  | PT Testing | 3 | Procurement 1 | COHU A(1) | N | 2024-09-10 |  | NS | 2024-09-04 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  |  | PT Testing | 7 | Procurement 2 | COHU A(1) | N | 2024-09-10 |  | NS | 2024-09-14 |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Example MRO Project | 616 | P4: Repair Placeholder | ARTISAN(7) | N | 2024-09-11 |  | NS | 11d 0.7h |  |  |  |  | Concerto Admin | 16d 6.5h | Volume of Work | 1 | 0
R | CMS | 2023-06-21 |  | Example MRO Project | 51 | Completion Milestone - End of Inspection Phase |  | N | 2024-09-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | Example MRO Project | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(7) | N | 2024-09-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | Example MRO Project | 503 | P4: Repair - Paint in repair | ARTISAN(7) | N | 2024-09-11 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
G |  |  |  | Example MRO Project | 504 | P4: Repair - Zone 1A | ARTISAN(7) | N | 2024-09-11 |  | NS | 0d 4.7h |  |  |  |  | Concerto Admin | 0d 7.1h | Volume of Work | 1 | 0
G |  |  |  | Example MRO Project | 506 | P4: Repair - Zone 2T | ARTISAN(7) | N | 2024-09-11 |  | NS | 0d 5.4h |  |  |  |  | Concerto Admin | 0d 8.1h | Volume of Work | 1 | 0
G |  |  |  | Example MRO Project | 507 | P4: Repair - Zone 2L | ARTISAN(7) | N | 2024-09-11 |  | NS | 1d 2.3h |  |  |  |  | Concerto Admin | 1d 9.8h | Volume of Work | 1 | 0
G |  |  |  | Example MRO Project | 605 | P4: Repair - Zone 3 | ARTISAN(7) | N | 2024-09-11 |  | NS | 0d 7.1h |  |  |  |  | Concerto Admin | 0d 10.7h | Volume of Work | 1 | 0
R |  |  |  | SUBTASK-RTS-WIP | 4 | Task-2 | Default(1) | Y | 2024-09-11 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d | WIP | 1 | 0
R |  |  |  | Test-Chains | 3 | T3 | Default(1) | N | 2024-09-11 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | 1+Task | 9 | T3 | A(1) | N | 2024-09-11 |  | NS | 2d 5.3h |  |  |  |  | PM2 | 2d | WIP | 0 | 2
R |  |  |  | SUBTASK-RTS-NETWORK | 6 | Task-2 | Default(1) | N | 2024-09-11 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d | Network | 1 | 0
R |  |  | Kobi_T | v2_22_DEV | 160 | CRM (placeholde) | Dev ADBA(1) | N | 2024-09-11 |  | NS | 2d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 4 | Interior: Disassembly/Inspection | MECHANICAL(6) | N | 2024-09-11 |  | NS | 3d |  |  |  |  | Manuel Rodriguez | 3d 5h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 5 | Fuselage: Disassembly/Inspection | MECHANICAL(12) | N | 2024-09-11 |  | NS | 3d |  |  |  |  | Manuel Rodriguez | 3d 4.6h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 6 | Empennage: Disassembly/Inspection | MECHANICAL(4) | N | 2024-09-11 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 1d 7.2h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 27 | Aircraft exterior safety check and tow aircraft for RVR Shoot | 8852(5) | N | 2024-09-11 |  | NS | 0d 2h |  |  |  |  | Concerto Admin | 0d 3.3h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 5 | Fuselage: Disassembly/Inspection | Interior(1) | N | 2024-09-11 |  | NS | 29d |  |  |  |  | Manuel Rodriguez | 42d 7.2h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 4 | Interior: Disassembly/Inspection | Interior(1) | N | 2024-09-11 |  | NS | 15d |  |  |  |  | Manuel Rodriguez | 21d 6.4h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 6 | Empennage: Disassembly/Inspection | MECHANICAL(2) | N | 2024-09-11 |  | NS | 3d |  |  |  |  | Manuel Rodriguez | 3d 6.5h | Volume of Work | 1 | 0
R |  |  | steinerm | Test Part 1 | 9 | Design concept (#1 of 3) | ID_Design(1) | N | 2024-09-11 |  | NS | 10d 6h |  |  |  |  | George |  |  |  | 1
G | PT |  |  | Medifab - RFID implementation plan | 31 | Delivery leadtime for RFID tags | Shipping(1) | N | 2024-09-11 |  | NS | 2024-08-19 |  |  |  |  | Jaco |  | Network |  | 0
G |  |  |  | ACE Demo 2-Tier | 572 | MC Infra drop 1-3 | SW Engineer(1) | Y | 2024-09-11 |  | NS | 60d |  |  |  |  | Guy Brill | 60d | Network | 1 | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3758 | Transmit KG00014889 Final Drawings w/ Rating Sheet to Customer | Project Manager Group KG NA(1) | N | 2024-09-11 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | 169425 | 28 | Inbound RVR Shoot | 2892(1), 4352(1), 6652(1), 8852(2) | N | 2024-09-11 |  | NS | 0d 6h |  |  |  |  | Concerto Admin | 1d 2.2h | Volume of Work | 1 | 0
R |  |  | j.brokar | RZTest_AWL027177_20230912 | 3831 | Equipment Engineering Review - KG00014889 | Default Resource(1) | N | 2024-09-11 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3612 | Customer Response and Markup Evaluation - KG00001787 Rev 0 Drawings | Default Resource(1) | N | 2024-09-11 |  | NS | 2023-08-01 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2023-09-12 | t.morris | RZTest_AWL027177_20230912 | 3614 | KG00001787 Rev 0 Drawing Submittal Milestone *CS 09/12/2023 |  | N | 2024-09-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | l.huang | RZTest_AWL027177_20230912 | 4783 | Equipment Engineering Review - KG00003924 (-001/-002/-003/-004) | Default Resource(1) | N | 2024-09-11 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10218 | High load jig - Final testing after FT getting ready for Final Testing | R&D_Hardware(1) | N | 2024-09-11 | christo.wentzel, johann.geldenhuys | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  |  | REEL TEST | 3 | P&ID PTH 3 | Process Engineer #1(1) | Y | 2024-09-11 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 57 | P2: Disassembly - Pre Power Off | ARTISAN(6.3) | N | 2024-09-11 |  | NS | 3d 12.8h |  |  |  |  | Concerto Admin | 5d 12.4h | Volume of Work | 1 | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 57 | P2: Disassembly - Pre Power Off | ARTISAN(5.9) | N | 2024-09-11 |  | NS | 4d 2h |  |  |  |  | Concerto Admin | 5d 9.6h | Network | 0 | 0
R | IMS | 2024-03-18 |  | V1 S07 169181 PMI-1_2024 | 921 | P1: Induction Complete |  | N | 2024-09-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Test-Chains | 5 | Project End |  | N | 2024-09-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Uri_Z_T | v2_22_DEV | 159 | CRM | Dev ADBA(1) | N | 2024-09-12 |  | NS | 5d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  |  | 169425 | 19 | Removals and open-ups required before power off | 2604(1), 8800(3), 8852(2) | N | 2024-09-12 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d 6.5h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 29 | LO Removals for all mods | 4352(8) | N | 2024-09-12 |  | NS | 5d 4h |  |  |  |  | Concerto Admin | 8d 1.1h | Volume of Work | 1 | 0
R | IMS | 2022-02-01 |  | 169425 | 78 | IMS-INDUCTION COMPLETE - Transfer to DISASSEMBLY |  | N | 2024-09-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | TestIMS | 3 | T3 | Default(1) | Y | 2024-09-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 616 | P4: Repair Placeholder | ARTISAN(6.3) | N | 2024-09-12 |  | NS | 12d 3.5h |  |  |  |  | Concerto Admin | 18d 4h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2024-09-12 |  | NS | 4d 12.8h |  |  |  |  | Concerto Admin | 7d 5.7h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2024-09-12 |  | NS | 3d 3.8h |  |  |  |  | Concerto Admin | 4d 12h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2024-09-12 |  | NS | 3d 2.8h |  |  |  |  | Concerto Admin | 4d 10.5h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 507 | P4: Repair - Zone 2L | ARTISAN(2) | N | 2024-09-12 |  | NS | 3d 1.8h |  |  |  |  | Concerto Admin | 4d 9h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2024-09-12 |  | NS | 2d 10.1h |  |  |  |  | Concerto Admin | 4d 2h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2024-09-12 |  | NS | 2d 12.5h |  |  |  |  | Concerto Admin | 4d 5.5h | Volume of Work | 1 | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(2) | N | 2024-09-12 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 503 | P4: Repair - Paint in repair | ARTISAN(2) | N | 2024-09-12 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 506 | P4: Repair - Zone 2T | ARTISAN(2) | N | 2024-09-12 |  | NS | 0d 0.8h |  |  |  |  | Concerto Admin | 0d 1.2h | Volume of Work | 1 | 0
R | CMS | 2024-03-20 |  | V1 S05 169185 PMI-1 R2 | 51 | Inspection Complete |  | N | 2024-09-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | CMS | 2024-04-10 | christo.wentzel | Smart PowerPack_05-09_07-06 | 10133 | CMS-Launch Ready |  | Y* | 2024-09-12 | corne.jansevanrensburg | NS | 0d |  |  | Cant marked C due to some predecessor tasks |  | Christo Wentzel |  |  |  | 0
G |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 83 | Golden Sample product (If needed) | R&D_Hardware(1) | Y* | 2024-09-12 |  | NS | 2d 6h |  |  |  |  | Christo Wentzel | 3d | Network | 0 | 1
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3828 | Customer Response and Markup Evaluation - KG00014889 Rev 0 Drawings | Default Resource(1) | N | 2024-09-12 |  | NS | 2023-08-02 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2023-09-12 | t.morris | RZTest_AWL027177_20230912 | 3830 | KG00014889 Rev 0 Drawing Submittal Milestone *CS 09/12/2023 |  | N | 2024-09-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3720 | Customer Response and Markup Evaluation - KG00003924 Rev 0 Drawings | Default Resource(1) | N | 2024-09-12 |  | NS | 2023-07-31 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2023-09-20 | t.morris | RZTest_AWL027177_20230912 | 3722 | KG00003924 Rev 0 Drawing Submittal Milestone *CS 09/12/2023 |  | N | 2024-09-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | SUBTASK-RTS-WIP | 8 | Project End |  | N | 2024-09-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | SUBTASK-RTS-NETWORK | 12 | Task-3 | Default(1) | N | 2024-09-13 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d | Network | 1 | 0
R |  |  | Zali_T | v2_22_DEV | 97 | Australia placeholder | Dev Layouts(1) | N | 2024-09-13 |  | NS | 3d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  |  | Penchard v1 | 3 | Roles and Responsibilties in place | Default(1) | N | 2024-09-13 |  | NS | 4d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 9 | Landing Gear: Disassembly/Inspection | MECHANICAL(2) | N | 2024-09-13 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 7d 0.9h | Network | 0 | 0
R |  |  |  | Penchard v1 | 2 | Measures estabilshed and visible | Default(1) | N | 2024-09-13 |  | NS | 4d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3759 | Layout completion (D1679A) | Utility(1) | N | 2024-09-13 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11278 | PO Preparation Process + Sending (Enclosure Base plate) | Mechanics(1) | N | 2024-09-13 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11298 | PO Preparation Process + Sending (Enclosure Back plate) | Mechanics(1) | N | 2024-09-13 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3733 | HW Bring Up Test plan review and approved (D1741A) | Utility(1) | N | 2024-09-13 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3710 | Final DR Layout end (D1741A) | Utility(1) | N | 2024-09-13 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9999 | Core parts review before samples order | Material(1) | N | 2024-09-13 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | REEL TEST | 4 | P&ID PTH 4 | Process Engineer #1(1) | Y | 2024-09-13 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Romi_T | v2_22_DEV | 177 | Route Catalog | Dev SOA(1) | N | 2024-09-13 |  | NS | 3d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | Lior_T | v2_22_DEV | 9 | Export(+B2A) | Dev Export/CMS(1) | N | 2024-09-13 |  | NS | 4d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10361 | PCB140110V5_REV1 - Full Test at iSert, (availability) | External SA(1) | N | 2024-09-13 | jaco.bester | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  |  | Project 01 | 2 | T2 | COHU B(0.3), COHU C(0.7) | N | 2024-09-13 |  | NS | 4d 0.4h |  |  |  |  | Concerto Admin | 6d | Network | 1 | 0
R |  |  | Efi | ACE Demo detiled tasks 240822_RZ | 11 | Develop MC HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Efi | ACE Demo 240822 | 11 | Develop MC HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Efi | ACE Demo 240822_RZ | 11 | Develop MC HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 51 | Develop IB HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 34 | Develop FTER HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 992 | Develop GTER HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 34 | Develop FTER HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 34 | Develop FTER HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 51 | Develop IB HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 51 | Develop IB HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 992 | Develop GTER HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 992 | Develop GTER HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 60 | Develop Cables HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 60 | Develop Cables HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 60 | Develop Cables HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 73 | Develop Simulator HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 73 | Develop Simulator HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 73 | Develop Simulator HLD | System Engineer(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 2-Tier | 13 | Develop MC Processor | HW Engineer(0.5), Operations(0), PCB layout sub contractor(0.1), PCB production SC(0.1), mechanical Engineer(0.3) | N | 2024-09-16 |  | NS | 110d |  |  |  |  | Guy Brill | 110d | Network | 1 | 0
R |  |  | Kobi_T | v2_22_DEV | 140 | Bug Fix ELK | Dev ADBA(1) | N | 2024-09-16 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 7 | Wings: Disassembly/Inspection | MECHANICAL(2) | N | 2024-09-16 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 1d 3.7h | Network | 0 | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 8 | Engines: Disassembly/Inspection | MECHANICAL(2) | N | 2024-09-16 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 9d 2.6h | Network | 0 | 0
R |  |  |  | 169425 | 5 | 7R Seed Removals: Remove for turn ins | 1910(1), 2892(2), 8800(5), 8852(2) | N | 2024-09-16 |  | NS | 3d 4h |  |  |  |  | Concerto Admin | 5d 2.2h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 9 | Landing Gear: Disassembly/Inspection | MECHANICAL(2) | N | 2024-09-16 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 7d 0.9h | Network | 0 | 0
R |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8948 | Component sampels (D1682A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10517 | PDR (Cell cabinet x2) | Mechanics(1) | N | 2024-09-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8340 | Design (D1741A Setup) | Utility(1) | N | 2024-09-16 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11409 | ECO of PCB approval (D1741A) | Utility(1) | N | 2024-09-16 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 3408 | Mechanics Approval (D1740A) | Mechanics(1) | N | 2024-09-16 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8862 | MP pilot PCBAs + shipment (50 units) (AP1740A-PB-01-LV) | Jabil(1) | N | 2024-09-16 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | TestIMS | 2 | T2 | Default(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | ACE Demo 2-Tier | 573 | Dev. MC Appl SW DROPS 1-3 | SW Engineer(1) | Y | 2024-09-16 |  | NS | 45d |  |  |  |  | Guy Brill | 45d | Network | 1 | 0
G |  |  | Doron.yo | Majoris - 1 Mega INV_04-04_14-52 | 2795 | Interfaces (System Engineering) | Utility(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2850 | Receiving requirements from mech | Material(1) | N | 2024-09-16 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3279 | ATP readiness (Batch -2 (30 Hilkar transformer)) | Utility(1) | N | 2024-09-16 | Reuven.Z, shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3940 | Production (Hipot - LV Unit) | ATE(1) | N | 2024-09-16 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 8848 | Provide potting requirements list to potting companies | Material(1) | N | 2024-09-16 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8855 | Component samples (AP1680A-CP-01-LV) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8858 | Component sampels (D1740A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8864 | Mech kit - Heat sinks (AP1740A-PB-01-LV) | Utility(1) | N | 2024-09-16 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8912 | Component sampels (D1679A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8919 | Component sampels (D1741A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8931 | Component sampels (D1738A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8939 | Component sampels (D1541B) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8953 | Component sampels (D1742A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8964 | Component sampels (D1739A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9327 | Sending PO (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-09-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9461 | PDR (LV Cabinet x2) | Mechanics(1) | N | 2024-09-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9486 | PDR (MV Cabinet x2) | Mechanics(1) | N | 2024-09-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9903 | Component sampels (D1976A) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10036 | Electromagnetic approval (NikolayT) | Material(1) | N | 2024-09-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10037 | Mechanical approval (YuvalK/MichaelR) | Material(1) | N | 2024-09-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10038 | Ops approval (RoyR) | Material(1) | N | 2024-09-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10039 | Potting process selection for trails | Material(1) | N | 2024-09-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 10477 | Component sampels (D1710B) | QnR(1) | N | 2024-09-16 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11161 | New chock spec preparation (Elec & Mech) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2024-09-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | Test-Purchaing task | 8 | Project End |  | N | 2024-09-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | REEL TEST | 12 | Project End |  | N | 2024-09-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | SUBTASK-RTS-NETWORK | 15 | Task-4 | Default(1) | N | 2024-09-17 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R |  |  | Zina_T | v2_22_DEV | 154 | Logistic - "4" | Dev Quotation(1) | N | 2024-09-17 |  | NS | 2d 6h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3732 | BOM 100% (D1741A) | Utility(1) | N | 2024-09-17 | shani.a | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9328 | PO Approved & Send to Production (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-09-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9904 | Component Evaluation (D1976A) | QnR(1) | N | 2024-09-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9987 | Litz wire serving selection | Material(1) | N | 2024-09-17 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10364 | PCB140110V5_REV2 - Relay out PCB if EMI / EMC fails | R&D_Hardware(1) | N | 2024-09-17 | jaco.bester | NS | 3d 5h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10362 | PCB140110V5_REV1 - Release all documentation for full build BOMs Gerbers SAP Numbers etc. | R&D_Hardware(1) | N | 2024-09-17 | jaco.bester | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 501 | P2: Disassembly - Post Power Off | ARTISAN(6) | N | 2024-09-17 |  | NS | 0d 11.5h |  |  |  |  | Concerto Admin | 1d 4.2h | Volume of Work | 0 | 0
R | PE |  |  | SUBTASK-RTS-NETWORK | 19 | Project End |  | N | 2024-09-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 501 | P2: Disassembly - Post Power Off | ARTISAN(5.9) | N | 2024-09-17 |  | NS | 0d 11.6h |  |  |  |  | Concerto Admin | 7d 5h | Network | 0 | 0
R | IMS | 2024-03-27 |  | V1 S07 169181 PMI-1_2024 | 922 | P2: Disassembly - Pre Power Off Complete |  | N | 2024-09-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Project 01 | 7 | Project End |  | N | 2024-09-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PT |  |  | test-purchasing2 | 4 | Task-2 | Default(1) | N | 2024-09-18 |  | NS | 2024-03-06 |  |  |  |  | Concerto Admin | 14d | Network |  | 0
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 13 | Repair/Installation/Test | MECHANICAL(12) | N | 2024-09-18 |  | NS | 5d |  |  |  |  | Manuel Rodriguez | 16d 3.5h | Network | 0 | 0
R | IMS | 2023-12-12 |  | Test 2_Airnostrum | 24 | Internal Milestone |  | N | 2024-09-18 |  | NS | 0d |  |  |  |  | Manuel Rodriguez |  |  |  | 0
R |  |  |  | Blank | 2 | T2 | HW Engineer(1) | N | 2024-09-18 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jefe de Proyecto | EC-MRI | 12 | REPAIR/INSTALLATION/TEST | Interior(2), Mechanical(15), Sheet Metal(2) | N | 2024-09-18 |  | NS | 8d |  |  |  |  | Manuel Alloza | 0d | WIP | 0 | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2841 | Material Design (Material Selection) | Material(1) | N | 2024-09-18 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2024-04-12 | christo.wentzel | Smart PowerPack_05-09_07-06 | 10379 | IMS - PCB140110V5_REV1 - Done |  | N | 2024-09-18 |  | NS | 0d |  |  |  |  | Christo Wentzel |  |  |  | 0
R |  |  | Zali_T | v2_22_DEV | 101 | Bug Fix Layout | Dev Layouts(1) | N | 2024-09-18 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Wisam_T | v2_22_DEV | 133 | Bug Fix Kafak | Dev ADBA(1) | N | 2024-09-18 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  |  | V1 S06 169186 PMI-1 | 58 | P3: Inspection | ARTISAN(6) | N | 2024-09-18 |  | NS | 2d 5.7h |  |  |  |  | Concerto Admin | 3d 8.4h | Volume of Work | 1 | 0
R | IMS | 2024-03-28 |  | V1 S06 169186 PMI-1 | 634 | Disassembly Complete | ARTISAN(1) | N | 2024-09-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 58 | P3: Inspection | ARTISAN(5.9) | N | 2024-09-18 |  | NS | 2d 6.9h |  |  |  |  | Concerto Admin | 4d 4.9h | Network | 0 | 0
R | IMS | 2024-03-28 |  | V1 S07 169181 PMI-1_2024 | 634 | P2: Disassembly - Post Power Off Complete |  | N | 2024-09-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Penchard v1 | 4 | Programmer is subordinating to the needs of the CNC | Default(1) | N | 2024-09-19 |  | NS | 6d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  |  | WMS en RETAIL | 16 | Modelamiento de COMPRAS & INVENTARIO | Experto de Procesos(1) | N | 2024-09-19 |  | NS | 11d |  |  |  |  | Fiallos | 11d | Network | 1 | 0
G |  |  |  | TestIMS | 4 | 5 | Default(1) | N | 2024-09-19 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Uri_Z_T | v2_22_DEV | 125 | Bug Fix Apps | Dev ADBA(1) | N | 2024-09-19 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R | IMS | 2022-02-11 |  | 169425 | 24 | IMS-DISASSEMBLYCOMPLETE - Transfer to Mod Phase | Default(1) | N | 2024-09-19 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | 169425 | 20 | Outboard Wing Stations 1 and 11: Removals: Door 6318, Panels and Seals ; Door 5317, Panels and Seals; Aileron LH/RH, Leading Edge Flap LH/RH, Outboard Wing LH/RH; Torque Shaft No. 2 | 2892(1), 3806(4), 4352(3), 8852(5) | N | 2024-09-19 |  | NS | 5d 4h |  |  |  |  | Concerto Admin | 8d 2h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 30 | F3 Fuel Tanks to Add T32 Check Valves: Panel Removals: 3310, 3332, 3331 | 1910(1), 2892(1), 3806(1), 8852(2) | N | 2024-09-19 |  | NS | 2d 2h |  |  |  |  | Concerto Admin | 3d 2.2h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 37 | MOD.CR-028852 270 Vdc Battery Mod | 1910(1), 2892(1), 8800(1) | N | 2024-09-19 |  | NS | 0d 4h |  |  |  |  | Concerto Admin | 0d 6h | Volume of Work | 1 | 0
R |  |  | Zina_T | v2_22_DEV | 53 | Bug fix Quotation | Dev Quotation(1) | N | 2024-09-19 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 426 | Engineering - Engineering Review of Initial Design | Engineering Manager(1) | N | 2024-09-19 | BillB | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | 1+Task | 5 | Project End |  | N | 2024-09-19 |  | NS | 0d |  |  |  |  | PM2 |  |  |  | 0
R | PE |  |  | test-purchasing2 | 8 | Project End |  | N | 2024-09-19 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test11 | 2 | DE Main Equipment | DHD(1) | N | 2024-09-20 |  | NS | 20d |  |  |  |  | Deepak Jha | 26d | Volume of Work | 0 | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11279 | Sending PO (Enclosure Base plate) | Mechanics(1) | N | 2024-09-20 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11299 | Sending PO (Enclosure Back plate) | Mechanics(1) | N | 2024-09-20 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Glow Lab | 67 | Hand-over and sign-off of MRP toolset | Contractor(1), Glow Lab(1), Synergic - BA(1), Synergic - SME(1) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 84 | Performance testing MWE and AWS | Integration specialist(1), RFID Engineer(0.5) | N | 2024-09-20 |  | NS | 4d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 427 | Engineering - Customer Approval Process | Customer(1) | N | 2024-09-20 | Cust | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | louis.loots | Smart PowerPack_05-09_07-06 | 10365 | PCB140110V5_REV2 - BOSCO manufacturing | External SA(1) | N | 2024-09-20 |  | NS | 4d 4h |  |  |  |  | Christo Wentzel |  | Network |  | 0
G |  |  | tommy.mulder | Smart PowerPack_05-09_07-06 | 102 | Update and link RoHS Datasheets to BOM parts | Buying(1) | N | 2024-09-20 | thokozile.ncala | NS | 6d 2h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R | PE |  |  | TestIMS | 8 | Project End |  | N | 2024-09-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Glow Lab | 71 | Project End |  | N | 2024-09-20 |  | NS | 0d |  |  |  |  | Jaco |  |  |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 616 | P4: Repair Placeholder | ARTISAN(6) | N | 2024-09-20 |  | NS | 12d 5.9h |  |  |  |  | Concerto Admin | 18d 7.6h | Volume of Work | 1 | 0
R |  |  |  | V1 S06 169186 PMI-1 | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 503 | P4: Repair - Paint in repair | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 506 | P4: Repair - Zone 2T | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 507 | P4: Repair - Zone 2L | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2024-09-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Volume of Work |  | 0
R | CMS | 2024-04-02 |  | V1 S06 169186 PMI-1 | 51 | Inspection Complete |  | N | 2024-09-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 228 | Design Concept of MC Chassis | mechanical Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 228 | Design Concept of MC Chassis | mechanical Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 228 | Design Concept of MC Chassis | mechanical Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 518 | Design Concept of IB Chassis | mechanical Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 28 | Design concept of FTER Chassis | mechanical Engineer(1.7) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1073 | Design concept of GTER Chassis | mechanical Engineer(1.7) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 28 | Design concept of FTER Chassis | mechanical Engineer(1.7) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 28 | Design concept of FTER Chassis | mechanical Engineer(1.7) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 518 | Design Concept of IB Chassis | mechanical Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 518 | Design Concept of IB Chassis | mechanical Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1073 | Design concept of GTER Chassis | mechanical Engineer(1.7) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1073 | Design concept of GTER Chassis | mechanical Engineer(1.7) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 232 | Dev. MC Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 232 | Dev. MC Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 232 | Dev. MC Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 242 | Dev. MC Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 246 | Dev. MC DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 242 | Dev. MC Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 242 | Dev. MC Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 246 | Dev. MC DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 246 | Dev. MC DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 62 | Design MC Data Cable | HW Engineer(1) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 63 | Design IB-Radio Cable | HW Engineer(1) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 64 | Design TER Power Cable | HW Engineer(1) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 65 | Design MC Power Cable | HW Engineer(1) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 536 | Design TER Data Cable | HW Engineer(1) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 239 | Dev. MC Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 360 | Dev. FTER Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 363 | Dev. FTER Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 367 | Dev. FTER Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 370 | Dev. FTER DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1083 | Dev. GTER Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1086 | Dev. GTER Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1089 | Dev. GTER DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1092 | Dev. GTER Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 239 | Dev. MC Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 239 | Dev. MC Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 360 | Dev. FTER Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 360 | Dev. FTER Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 363 | Dev. FTER Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 363 | Dev. FTER Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 367 | Dev. FTER Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 367 | Dev. FTER Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 370 | Dev. FTER DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 370 | Dev. FTER DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1083 | Dev. GTER Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1083 | Dev. GTER Infra SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1086 | Dev. GTER Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1086 | Dev. GTER Comm SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1089 | Dev. GTER DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1089 | Dev. GTER DispSW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1092 | Dev. GTER Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1092 | Dev. GTER Appl SW DROP 1 | SW Engineer(1) | N | 2024-09-23 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 530 | Purchase cable material | Operations(1) | N | 2024-09-23 |  | NS | 45d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 530 | Purchase cable material | Operations(1) | N | 2024-09-23 |  | NS | 45d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 537 | Receive GFE Radios | PM(1) | N | 2024-09-23 |  | NS | 40d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 537 | Receive GFE Radios | PM(1) | N | 2024-09-23 |  | NS | 40d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 537 | Receive GFE Radios | PM(1) | N | 2024-09-23 |  | NS | 40d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 538 | Purchase Accessories | PM(1) | N | 2024-09-23 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 538 | Purchase Accessories | PM(1) | N | 2024-09-23 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 538 | Purchase Accessories | PM(1) | N | 2024-09-23 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 529 | Design cables | HW Engineer(5) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill | 4d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 529 | Design cables | HW Engineer(5) | N | 2024-09-23 |  | NS | 4d |  |  |  |  | Guy Brill | 4d | Network | 1 | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 54 | Develop IB ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 66 | Develop Cables ATP | HW Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 54 | Develop IB ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 54 | Develop IB ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 66 | Develop Cables ATP | HW Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 66 | Develop Cables ATP | HW Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Barak_T | v2_22_DEV | 47 | Bug Fix ADBA | Dev ADBA(1) | N | 2024-09-23 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | YairA_T | v2_22_DEV | 121 | Bug fix B2A/NTF | Dev Export/CMS(1) | N | 2024-09-23 |  | NS | 1d 2h |  |  |  |  | ProjectManager1 |  | Network |  | 1
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11280 | PO Approved & Send to Production (Enclosure Base plate) | Mechanics(1) | N | 2024-09-23 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11300 | PO Approved & Send to Production (Enclosure Back plate) | Mechanics(1) | N | 2024-09-23 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | ACE Demo 240822_RZ | 12 | Develop MC ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detiled tasks 240822_RZ | 12 | Develop MC ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822 | 12 | Develop MC ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822_RZ | 37 | Develop FTER ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detiled tasks 240822_RZ | 37 | Develop FTER ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822 | 37 | Develop FTER ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822 | 71 | Develop Simulator ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822_RZ | 71 | Develop Simulator ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detiled tasks 240822_RZ | 71 | Develop Simulator ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detiled tasks 240822_RZ | 1097 | Develop GTER ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822_RZ | 1097 | Develop GTER ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822 | 1097 | Develop GTER ATP | System Engineer(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Doron.yo | Majoris - 1 Mega INV_04-04_14-52 | 2798 | Requirements (System Engineering) | Utility(1) | N | 2024-09-23 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3806 | Component Evaluation (D1940A) | QnR(1) | N | 2024-09-23 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5215 | Transformer Ready For Batch RnD | Utility(1) | N | 2024-09-23 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9898 | ATE Design Review (ATP 100%) (D1976A) | Utility(1) | N | 2024-09-23 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10251 | Production (Hipot - MV Unit) | ATE(1) | N | 2024-09-23 |  | NS | 35d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10291 | PCB140110V3_REV3 - Assembly missing parts | R&D_Hardware(1) | N | 2024-09-23 | robin.davis | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11163 | Core , coil , winding , bonding jig, other items/tools availability (RnD batch (up to 5 units)) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2024-09-23 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 616 | P4: Repair Placeholder | ARTISAN(5.9) | N | 2024-09-23 |  | NS | 13d 1.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 505 | P4: Repair - Zone 1B | ARTISAN(2) | N | 2024-09-23 |  | NS | 1d 5.2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 63 | P4: Repair - Off AIRCRAFT | ARTISAN(2) | N | 2024-09-23 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 503 | P4: Repair - Paint in repair | ARTISAN(2) | N | 2024-09-23 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 504 | P4: Repair - Zone 1A | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d 5.5h |  |  |  |  | Concerto Admin | 1d 7h | Network | 0 | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 506 | P4: Repair - Zone 2T | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d 4h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 507 | P4: Repair - Zone 2L | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 508 | P4: Repair - Zone 2R | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 509 | P4: Repair - Zone 4 | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d 0.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 604 | P4: Repair - Zone 5 | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 605 | P4: Repair - Zone 3 | ARTISAN(2) | N | 2024-09-23 |  | NS | 0d 1.6h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2024-04-03 |  | V1 S07 169181 PMI-1_2024 | 51 | P3: Inspection Complete |  | N | 2024-09-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | 169425 | 14 | MOD UNIT LEVEL.CR-027845 Replacement of Supply No. 2 OBIGGS Wash Check Valve | 1910(1), 2892(1), 8800(1) | N | 2024-09-23 |  | NS | 2d |  |  |  |  | Concerto Admin | 3d | Volume of Work | 1 | 0
R |  |  |  | v2_22_DEV | 116 | DEV Freeze |  | N | 2024-09-24 |  | NS | 0d |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  |  | v2_22_DEV | 118 | Project End MS |  | N | 2024-09-24 |  | NS | 0d |  |  |  |  | ProjectManager1 |  | Network |  | 0
R |  |  |  | v2_22_DEV | 119 | Project End |  | N | 2024-09-24 |  | NS | 0d |  |  |  |  | ProjectManager1 |  | Network |  | 0
R | PE |  |  | v2_22_DEV | 195 | Project End |  | N | 2024-09-24 |  | NS | 0d |  |  |  |  | ProjectManager1 |  |  |  | 0
R |  |  | Painter AC | T44_February_2019 | 1907 | Prime A/C | Painters_A/C(4) | N | 2024-09-25 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Jefe de Equipo | Test 2_Airnostrum | 19 | Operational Tests | MECHANICAL(2.5) | N | 2024-09-25 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 3d 2.7h | Network | 0 | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2843 | preliminary test before aging (GPO3 parts) | Material(1) | N | 2024-09-25 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | steinerm | Test Part 1 | 8129 | Technical Design review of design concept (# 1 of 3) | ID_Design(1) | N | 2024-09-25 |  | NS | 4d |  |  |  |  | George |  |  |  | 0
G |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10292 | PCB140110V3_REV3 - Testing and review | R&D_Hardware(1) | N | 2024-09-25 | robin.davis | NS | 2d 6h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | Yuval.k | Majoris - 1 Mega INV_04-04_14-52 | 3708 | Mechanics Approval (D1741A) | Mechanics(1) | N | 2024-09-26 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8924 | MP pilot PCBAs + shipment (25 units) (D1741A) | Jabil(1) | N | 2024-09-26 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 85 | Software is ready and we can ship hardware to site | Integration specialist(1) | N | 2024-09-26 |  | NS | 1d |  |  |  |  | Jaco |  | Network |  | 0
G | IMS | 2024-10-02 |  | TestIMS | 5 | Internal Milestone |  | N | 2024-09-26 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8923 | Mech kit - Heat sinks (D1741A) | Utility(1) | N | 2024-09-26 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Example MRO Project | 64 | P5: Assembly Phase | ARTISAN(7) | Y* | 2024-09-26 |  | NS | 5d 3.9h |  |  |  |  | Concerto Admin | 7d 11.8h | Volume of Work | 1 | 0
R |  |  |  | TestNilesh2 | 4 | t4 | Default(1) | N | 2024-09-26 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  | Jefe de Proyecto | Test 2_Airnostrum | 21 | Project End |  | N | 2024-09-26 |  | NS | 0d |  |  |  |  | Manuel Rodriguez |  |  |  | 0
R | PE |  |  | TestAutoRollup | 9 | Project End |  | N | 2024-09-26 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  | Jefe de Proyecto | EC-MRI | 21 | Project End |  | N | 2024-09-26 |  | NS | 0d |  |  |  |  | Manuel Alloza |  |  |  | 0
R | IMS | 2022-07-04 | PS | T44_February_2019 | 1954 | IMS-Release to D0=Post Strip Disassembly | Hold(1) | N | 2024-09-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Disassembly | T44_February_2019 | 2658 | Incoming Cabin Pressurization | 629_ACM(2), 629_AE(1) | N | 2024-09-27 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Disassembly | T44_February_2019 | 2659 | Test De-Ice Boots | 629_ACM(2), 629_AE(1) | N | 2024-09-27 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 530 | Purchase cable material | Operations(1) | N | 2024-09-27 |  | NS | 45d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Penchard v1 | 5 | Full Kits in place and visible. Program Handovers are happening | Default(1) | N | 2024-09-27 |  | NS | 6d |  |  |  |  | johnsonb |  | Network |  | 1
R |  |  |  | 169425 | 8 | MOD Wing Retrofit Removal LH/RH.CR-029698 Modification of the Outboard Wing Stations 1 and 11 | 1910(1), 2892(2), 3806(6), 8800(3) | N | 2024-09-27 |  | NS | 5d 6h |  |  |  |  | Concerto Admin | 8d 5.3h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 9 | MOD.CR-027845 Modification of the F3 Fuel Tanks to Add T32 Check Valves | 1910(1), 8800(1) | N | 2024-09-27 |  | NS | 0d 4h |  |  |  |  | Concerto Admin | 0d 5h | Volume of Work | 1 | 0
R |  |  |  | Blank | 3 | T3 | Engineering(2) | N | 2024-09-27 |  | NS | 11d |  |  |  |  | Concerto Admin | 15d | Volume of Work | 1 | 0
R |  |  |  | Medifab - RFID implementation plan | 30 | All equipment and software received, checked and site is ready for installation | Customer Process Engineering(0.33), Customer System Engineering(0.33), RFID Engineer(0.33) | N | 2024-09-27 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 429 | Engineering - Drafting Phase | Engineering(1) | N | 2024-09-27 | Designer | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 428 | Engineering - Develop APO and Submit to Purchasing | Engineering(1) | N | 2024-09-27 | Designer | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11281 | Samples Production & shipment (Enclosure Base plate) | Jabil(1) | N | 2024-09-30 | michael.ra | NS | 14d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11301 | Samples Production & shipment (Enclosure Back plate) | Jabil(1) | N | 2024-09-30 | michael.ra | NS | 14d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3606 | Component Evaluation (D1682A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | ACE Demo 240822_RZ | 10 | Develop System ATP | System Engineer(1) | N | 2024-09-30 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo detiled tasks 240822_RZ | 10 | Develop System ATP | System Engineer(1) | N | 2024-09-30 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 240822 | 10 | Develop System ATP | System Engineer(1) | N | 2024-09-30 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | gal.k | Majoris - 1 Mega INV_04-04_14-52 | 97 | Learning | Integration(1) | N | 2024-09-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 2231 | Component Evaluation (D1739A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Doron.yo | Majoris - 1 Mega INV_04-04_14-52 | 2559 | System Test Plan (System Engineering) | Utility(1) | N | 2024-09-30 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Uri.Y | Majoris - 1 Mega INV_04-04_14-52 | 2601 | System Requirement Review (SRR) | Utility(1) | N | 2024-09-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3406 | Component Evaluation (D1740A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3456 | Component Evaluation (AP1680A-CP-01-LV) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3506 | Component Evaluation (D1742A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3556 | Component Evaluation (D1541B) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3656 | Component Evaluation (D1738A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3706 | Component Evaluation (D1741A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3756 | Component Evaluation (D1679A) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 10478 | Component Evaluation (D1710B) | QnR(1) | N | 2024-09-30 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 10504 | winding, Bobin (before potting) other items/tools availability (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-09-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11045 | production line design (5 Hilkar transformer) | Magnetic(1) | N | 2024-09-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 273 | APO Parts - Make and Deliver Long Lead Items | Vendors(1) | N | 2024-09-30 | VendBuy | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | apie.pieterse | Smart PowerPack_05-09_07-06 | 10366 | PCB140110V5_REV2 - Build prototype Apie:- can he fit it in otherwise manual build | Production_SMT(1) | N | 2024-09-30 | jaco.bester, tony.baia | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
G |  |  | christo.wentzel | Smart PowerPack_05-09_07-06 | 10293 | PCB140110V3_REV3- iSert warm fuzy testing (Not needed) | R&D_Hardware(1) | N | 2024-09-30 | robin.davis | NS | 0d 1h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | j.guo | RZTest_AWL027177_20230912 | 3935 | EQE Revised Release - KG00070783 | Equipment Engineering EQE Group KG NA(1) | N | 2024-09-30 |  | NS | 2d |  |  | originally released by NN |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 64 | P5: Assembly Phase | ARTISAN(6.3) | N | 2024-09-30 |  | NS | 6d 3.1h |  |  |  |  | Concerto Admin | 9d 4h | Volume of Work | 0 | 0
R | IMS | 2024-04-15 |  | V1 S05 169185 PMI-1 R2 | 955 | Repair Complete |  | N | 2024-09-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 2598 | Outer Wing Removal | 629_ACM(4), 629_AE(1) | N | 2024-10-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Disassembly | T44_February_2019 | 2599 | Remove Vertical and Horizontal Stabilizers | 629_ACM(3), 629_AE(1) | N | 2024-10-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8262 | Production (D1740A Setup) | Utility(1) | N | 2024-10-01 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 36 | Installation of RFID and printer in R24 | Hardware and electrical installer(1) | N | 2024-10-01 |  | NS | 5d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 37 | Installation of RFID in R22 | Hardware and electrical installer(1) | N | 2024-10-01 |  | NS | 3d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 35 | Installation of RFID and printer in R32 | Hardware and electrical installer(1) | N | 2024-10-01 |  | NS | 6d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9329 | DFM approval (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-10-01 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9330 | Mold/Tool Design (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-10-01 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9914 | Production (D1976A Setup) | Utility(1) | N | 2024-10-01 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9986 | Materials review and approval of potting suggestions | Material(1) | N | 2024-10-01 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9998 | Core prototype assembly with magnetic team | Material(1) | N | 2024-10-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10018 | receive samples from mech | Material(1) | N | 2024-10-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 431 | Engineering - Create Certified Drawings | Engineering(1) | N | 2024-10-01 | Designer | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 432 | Create Spare Parts List and Submit to Sales | Engineering(1) | N | 2024-10-01 | Designer | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 430 | Engineering - Release to Production Control | Engineering(1) | N | 2024-10-01 | Designer | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | a.lee | RZTest_AWL027177_20230912 | 3611 | EQE Revised Release - KG00001787 | Equipment Engineering EQE Group KG NA(1) | N | 2024-10-01 |  | NS | 6d 4.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 3 | Team review of design concept (#1 of 3) | Team(1) | N | 2024-10-01 |  | NS | 1d |  |  |  |  | George |  |  |  | 0
R |  |  |  | V1 S06 1 86 | 6 | Repair | ARTISAN(14) | N | 2024-10-02 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S08 1 82 | 6 | Repair | ARTISAN(14) | N | 2024-10-02 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S09 1 87 | 6 | Repair | ARTISAN(14) | N | 2024-10-02 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S11 1 89 | 6 | Repair | ARTISAN(14) | N | 2024-10-02 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 7 | Wings: Disassembly/Inspection | MECHANICAL(2) | N | 2024-10-02 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 1d 3.7h | Network | 0 | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10395 | PCB140110V5_REV2 - Hardware verification | R&D_Hardware(1) | N | 2024-10-02 | jaco.bester, robin.davis | NS | 4d 4h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10368 | PCB140110V5_REV2 - Do Radiated and Conducted (iSert availability) | External SA(1) | N | 2024-10-02 | jaco.bester | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
G |  |  | christo.wentzel | Smart PowerPack_05-09_07-06 | 52 | Create UKCA, RCM tick and Local Product DOC, and TCF in SAP | Certification Officer(1) | N | 2024-10-02 | corne.jansevanrensburg | NS | 4d 4h |  |  |  |  | Christo Wentzel |  | Network |  | 1
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2845 | intermediate test mid-aging (GPO3 parts) | Material(1) | N | 2024-10-02 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | KG Design Team | RZTest_AWL027177_20230912 | 3904 | Design & Detail Revision - KG00070783 | Designer Group - Wichita and Mumbai(1.9) | N | 2024-10-02 |  | NS | 2d 2h |  |  |  |  | Concerto Admin | 3d 3h | Network | 1 | 0
R | SNET |  | Lead Engineer | Test Part 1 | 8102 | Build and Evaluate Concept Prototype | Engineering(1) | N | 2024-10-02 | engr | NS | 20d |  |  |  |  | George |  |  |  | 0
R |  |  | j.brokar | RZTest_AWL027177_20230912 | 3827 | EQE Revised Release - KG00014889 | Equipment Engineering EQE Group KG NA(1) | N | 2024-10-02 |  | NS | 2d 2h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | CMS | 2024-10-02 |  | TestIMS | 6 | Completion Milestone |  | N | 2024-10-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 2657 | Interior Removal | 629_ACM(2), 629_AE(1) | N | 2024-10-03 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Disassembly | T44_February_2019 | 3500 | Electrical Removals | 629_ACM(2), 629_AE(1) | N | 2024-10-03 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Disassembly | T44_February_2019 | 2595 | Heat Exchanger Removal | 629_ACM(1) | N | 2024-10-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 2652 | Exterior Panels | 629_ACM(2) | N | 2024-10-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 3503 | Remove 44 Gallon Fuel Cell and Liners | 629_ACM(1) | N | 2024-10-03 |  | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9997 | Core assembly process definition | Material(1) | N | 2024-10-03 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 45 | Download Solid Works Model and Create WO | Planning(1) | N | 2024-10-03 | Planner | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | W9585 - 9917-11-100 2-Tier Example | 454 | Manufacturing | Fab-Food(1.4), Glass Beading(0.3), Laser(0.1), Laser Progammer(0), Lathe(0.1), Material Handling(0.3), Mill(0.5), Planning(0), Press Break(0.1), Saw(0.1), Steel Shop(0), Vendors(1.4) | N | 2024-10-03 |  | NS | 22d 4.8h |  |  |  |  | Concerto Admin | 22d 4.8h | Network | 1 | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 355 | Production Control - Stock Check, Operations, Subcontract Development | Planning(1) | N | 2024-10-03 | Planner | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | n.moyer | RZTest_AWL027177_20230912 | 4803 | EQE Revised Release - KG00003924 (-005) | Equipment Engineering EQE Group KG NA(1) | N | 2024-10-03 |  | NS | 1d 7.1h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | l.huang | RZTest_AWL027177_20230912 | 4813 | EQE Revised Release - KG00003924 (-001/-002/-003/-004) | Equipment Engineering EQE Group KG NA(1) | N | 2024-10-03 |  | NS | 1d 0.5h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | n.moyer | RZTest_AWL027177_20230912 | 3719 | EQE Revised Release - KG00003924 (-006/-007/-009/-010) | Equipment Engineering EQE Group KG NA(1) | N | 2024-10-03 |  | NS | 0d 5.6h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 33 | In-House Laser - Create Program | Laser Progammer(1) | N | 2024-10-03 | LaserPro | NS | 0d 2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 42 | Sub-Laser - Process PO and Make and Deliver Parts | Vendors(1) | N | 2024-10-03 | VendSub | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 29 | Stock Check - Shaped Steel | Material Handling(1) | N | 2024-10-03 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 351 | Sub-Water - Process PO and Make and Deliver Parts | Vendors(1) | N | 2024-10-03 | VendSub | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 34 | Stock Check - Stock Check Buy-Outs and MTS Parts | Material Handling(1) | N | 2024-10-03 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 27 | Shaped Steel - Procure Shaped Steel | Vendors(1) | N | 2024-10-03 | VendSteel | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 36 | Buyouts - Procure Buyouts | Vendors(1) | N | 2024-10-03 | VendBuy | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 356 | MTS - Open WO for MTS Shortages | Planning(1) | N | 2024-10-03 | Planner | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Example MRO Project | 35 | P6: Post Ops Test Phase | ARTISAN(7), PAINT(1) | N | 2024-10-03 |  | NS | 0d 5.6h |  |  |  |  | Concerto Admin | 0d 8.4h | Volume of Work | 1 | 0
R | IMS | 2023-07-26 |  | Example MRO Project | 55 | Internal Milestone: Ready For Test | ARTISAN(1) | N | 2024-10-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 32 | In-House Laser - Stock Check Sheet Steel | Material Handling(1) | N | 2024-10-03 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 31 | In-House Laser - Process PO and Deliver Sheet Steel | Vendors(1) | N | 2024-10-03 | VendSteel | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | KG Design Team | RZTest_AWL027177_20230912 | 3688 | Design & Detail Revision - KG00003924 (-006/-007/-009/-010) | Designer Group - Wichita and Mumbai(1.7) | N | 2024-10-03 |  | NS | 1d 6.4h |  |  |  |  | Concerto Admin | 2d 5.5h | Network | 1 | 0
R |  |  |  | Example MRO Project | 481 | P8: Final Processing | ARTISAN(7) | N | 2024-10-03 |  | NS | 0d 3.1h |  |  |  |  | Concerto Admin | 0d 4.7h | Volume of Work | 1 | 0
R |  |  |  | WMS en RETAIL | 17 | Datos Maestros de COMPRAS & INVENTARIO | Experto de Procesos(1) | N | 2024-10-04 |  | NS | 36d |  |  |  |  | Fiallos | 36d | Network | 1 | 1
R |  |  |  | Medifab - RFID implementation plan | 44 | System testing in R22 | Customer Process Engineering(1), Customer System Engineering(1), Hardware and electrical installer(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-04 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Example MRO Project | 482 | P9: FCF Phase | ARTISAN(7) | N | 2024-10-04 |  | NS | 0d 3.2h |  |  |  |  | Concerto Admin | 0d 4.8h | Volume of Work | 1 | 0
R |  |  | KG Design Team | RZTest_AWL027177_20230912 | 4805 | Design & Detail Revision - KG00003924 (-001/-002/-003/-004) | Designer Group - Wichita and Mumbai(1.5) | N | 2024-10-04 |  | NS | 2d 2.7h |  |  |  |  | Concerto Admin | 3d 4h | Network | 1 | 0
R |  |  |  | Example MRO Project | 486 | P7: Paint | ARTISAN(3) | N | 2024-10-04 |  | NS | 3d 5.7h |  |  |  |  | Concerto Admin | 5d 1.8h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 12 | MOD Wing Retrofit Install LH/RH.CR-029698 Modification of the Outboard Wing Stations 1 and 11 | 3806(5), 4352(3) | N | 2024-10-04 |  | NS | 8d |  |  |  |  | Concerto Admin | 12d | Volume of Work | 1 | 0
R |  |  | j.guo | RZTest_AWL027177_20230912 | 3903 | EQE Revision Review - KG00070783 | Default Resource(1) | N | 2024-10-04 |  | NS | 1d 2.7h |  |  | originally released by NN |  | Concerto Admin |  | Network |  | 0
R |  |  |  | PT Testing | 5 | Material Releasing | COHU A(1) | N | 2024-10-06 |  | NS | 0d 23.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Penchard v1 | 6 | Constraint Obsession in place and visible. Top 3 CNC stoppages resolved | Default(1) | N | 2024-10-07 |  | NS | 6d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9418 | CDR Approval | Mechanics(1) | N | 2024-10-07 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8339 | Production (D1741A Setup) | Utility(1) | N | 2024-10-07 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3948 | Production (Connectivity - LV Unit) | ATE(1) | N | 2024-10-07 |  | NS | 35d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | TestNilesh2 | 2 | t2 | Default(1) | N | 2024-10-07 |  | NS | 14d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3271 | Core , coil, bonding jig, other items/tools availability (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-10-07 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9924 | SW Basic Version (D1976A) | SW(1) | N | 2024-10-07 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9949 | Production (Hipot) | ATE(1) | N | 2024-10-07 |  | NS | 35d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9953 | Production (Connectivity) | ATE(1) | N | 2024-10-07 |  | NS | 35d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10255 | Production (Connectivity - MV Unit) | ATE(1) | N | 2024-10-07 |  | NS | 35d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | KG Design Team | RZTest_AWL027177_20230912 | 3796 | Design & Detail Revision - KG00014889 | Designer Group - Wichita and Mumbai(2.3) | N | 2024-10-07 |  | NS | 2d 2.4h |  |  |  |  | Concerto Admin | 3d 3.5h | Network | 1 | 0
R |  |  | KG Design Team | RZTest_AWL027177_20230912 | 4795 | Design & Detail Revision - KG00003924 (-005) | Designer Group - Wichita and Mumbai(1) | N | 2024-10-07 |  | NS | 6d 7.9h |  |  |  |  | Concerto Admin | 10d 3.5h | Network | 1 | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 26 | Recieve - Receive Shaped Steel from Vendor | Material Handling(1) | N | 2024-10-07 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 23 | Saw - Saw Parts for Fabrication | Saw(1) | N | 2024-10-07 | Saw | NS | 1d 7.1h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 433 | Saw - Saw Parts for Assembly | Saw(1) | N | 2024-10-07 | Saw | NS | 0d 4.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 30 | Receive -Receive Sheet Steel | Material Handling(1) | N | 2024-10-07 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | n.moyer | RZTest_AWL027177_20230912 | 3687 | EQE Revision Review - KG00003924 (-006/-007/-009/-010) | Default Resource(1) | N | 2024-10-07 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 25 | Laser - Perform In-House Laser Operations | Laser(1) | N | 2024-10-07 | Laser | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | PT Testing | 6 | Final Assembly | COHU A(1) | N | 2024-10-07 |  | NS | 6d 23.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10536 | Production Drawings (before Batch RnD (10 Cells)) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 43 | System testing in R24 | Customer System Engineering(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-08 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9331 | Tool/Mold production (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9334 | ECO STP (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9417 | Packing Preparation | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9745 | PO Preperation Process + Sending (Rack Shelves) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9757 | PO Preperation Process + Sending (Rack Metal legs) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9770 | PO Preperation Process + Sending (Rack Isolated legs) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9784 | PO Preperation Process + Sending (Rack Shelf holder) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9797 | PO Preperation Process + Sending (Rack Legs base) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9811 | PO Preperation Process + Sending (Air core reactor Holder) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9823 | PO Preperation Process + Sending (Air core reactor Coil) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9837 | PO Preperation Process + Sending (MV busbars) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9850 | PO Preperation Process + Sending (LV busbars - busbars) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9862 | PO Preperation Process + Sending (LV busbars - holder) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9985 | Potting materials order for preliminary tests | Material(1) | N | 2024-10-08 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9991 | Review and approval of Mold design | Material(1) | N | 2024-10-08 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10015 | Rogowski experiment | Material(1) | N | 2024-10-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10019 | Electromagnetic approval (NikolayT) | Utility(1) | N | 2024-10-08 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10020 | Mechanical approval (YuvalK/MichaelR) | Mechanics(1) | N | 2024-10-08 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10021 | Ops approval (RoyR) | Ops(1) | N | 2024-10-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.p | Majoris - 1 Mega INV_04-04_14-52 | 10022 | Env. Spproval (TalR) | Material(1) | N | 2024-10-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.z | Majoris - 1 Mega INV_04-04_14-52 | 10023 | Certification approval (AviadY) | Certification(1) | N | 2024-10-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 10523 | Setup prepration | Certification(1) | N | 2024-10-08 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 434 | Steel Shop - Perform Misc Steel Shop Activities | Steel Shop(1) | N | 2024-10-08 | Steel | NS | 0d 2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3900 | Customer Response and Markup Evaluation - KG00070783 Rev 1 Drawings | Default Resource(1) | N | 2024-10-08 |  | NS | 2023-09-01 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-08-04 | t.morris | RZTest_AWL027177_20230912 | 3902 | KG00070783 Preplanned Resubmit Milestone |  | N | 2024-10-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 435 | Lathe - Lathe Parts for Assembly | Lathe(1) | N | 2024-10-08 | Lathe | NS | 2d 4h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10367 | PCB140110V5_REV2 - Do Surge Testing at iSert | External SA(1) | N | 2024-10-08 | jaco.bester | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  | l.huang | RZTest_AWL027177_20230912 | 4804 | EQE Revision Review - KG00003924 (-001/-002/-003/-004) | Default Resource(1) | N | 2024-10-08 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 35 | P6: Post Ops Test Phase | ARTISAN(6.3) | N | 2024-10-08 |  | NS | 0d 10.3h |  |  |  |  | Concerto Admin | 1d 2.5h | Volume of Work | 0 | 0
R | IMS | 2024-04-26 |  | V1 S05 169185 PMI-1 R2 | 55 | Assembly Complete |  | N | 2024-10-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 64 | P5: Assembly Phase | ARTISAN(6) | N | 2024-10-09 |  | NS | 6d 6.5h |  |  |  |  | Concerto Admin | 9d 9.1h | Volume of Work | 0 | 0
R | IMS | 2024-04-29 |  | V1 S06 169186 PMI-1 | 844 | Repair Complete | ARTISAN(1) | N | 2024-10-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | j.brokar | RZTest_AWL027177_20230912 | 3795 | EQE Revision Review - KG00014889 | Default Resource(1) | N | 2024-10-09 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10369 | PCB140110V5_REV2 - If Surge, Radiated and Conducted PASS, do Full Test | External SA(1) | N | 2024-10-09 | jaco.bester | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 274 | Steel Shop - Perform Misc Steel Shop Activities | Steel Shop(1) | N | 2024-10-09 | Steel | NS | 0d 2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 349 | Lathe - Lathe Parts for Fabrication | Lathe(1) | N | 2024-10-09 | Lathe | NS | 0d 5h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 486 | P7: Paint | ARTISAN(3) | N | 2024-10-09 |  | NS | 5d |  |  |  |  | Concerto Admin | 5d 5.5h | Volume of Work | 0 | 0
R | PE |  |  | Example MRO Project | 630 | Project End |  | N | 2024-10-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 2654 | Remove Heaters | 629_ACM(1), 629_AE(1) | N | 2024-10-10 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 46 | Super user training | Customer Process Engineering(1), Integration specialist(1), RFID Engineer(1) | N | 2024-10-10 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9996 | Core assembly aging test | Material(1) | N | 2024-10-10 |  | NS | 45d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10033 | Core receive samples | Material(1) | N | 2024-10-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | KG Design Team | RZTest_AWL027177_20230912 | 3580 | Design & Detail Revision - KG00001787 | Designer Group - Wichita and Mumbai(4.2) | N | 2024-10-10 |  | NS | 3d 1.7h |  |  |  |  | Concerto Admin | 4d 6.5h | Network | 1 | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 43 | Receive - Receive Sub Laser | Material Handling(1) | N | 2024-10-10 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 345 | Mill - Machine Parts for Fabrication | Mill(1) | N | 2024-10-10 | Mill | NS | 0d 5h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 64 | P5: Assembly Phase | ARTISAN(5.9) | N | 2024-10-10 |  | NS | 6d 9.5h |  |  |  |  | Concerto Admin | 10d 1.5h | Network | 0 | 0
R | IMS | 2024-04-30 |  | V1 S07 169181 PMI-1_2024 | 844 | P4: Repair Complete |  | N | 2024-10-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 37 | Receive - Receive Buyouts | Material Handling(1) | N | 2024-10-10 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 357 | MTS - Process MTS Shortages | Material Handling(1) | N | 2024-10-10 | Handl | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3792 | Customer Response and Markup Evaluation - KG00014889 Rev 1 Drawings | Default Resource(1) | N | 2024-10-10 |  | NS | 2023-09-08 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-08-10 | t.morris | RZTest_AWL027177_20230912 | 3794 | KG00014889 Preplanned Resubmit Milestone |  | N | 2024-10-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 24 | Press Brake - Perform Press Brake Operations | Press Break(1) | N | 2024-10-10 | PressB | NS | 2d 6.1h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Gantt Rel 17 | 197 | Gantt Rel 17 - OCT 15th | BE(2), FE(2) | N | 2024-10-11 |  | NS | 25d |  |  |  |  | Concerto Admin | 30d | Volume of Work | 0 | 0
R | CMS | 2024-08-16 |  | Gantt Rel 17 | 181 | UI - Project Status |  | N | 2024-10-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10370 | PCB140110V5_REV2 - Release all documentation for full build BOMs Gerbers SAP Numbers etc. | R&D_Hardware(1) | N | 2024-10-11 | robin.davis | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R | PE |  |  | Blank | 8 | Project End |  | N | 2024-10-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 2655 | Remove Air Conditioner | 629_ACM(1), 629_AE(1) | N | 2024-10-14 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 234 | Dev. MC Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-14 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 234 | Dev. MC Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-14 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 234 | Dev. MC Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-14 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Test11 | 3 | Civil Drawings Main Equipment Foundation | DHD(1) | N | 2024-10-14 |  | NS | 15d |  |  |  |  | Deepak Jha |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10371 | PCB140110V5_REV3 - Plan and decide on the best way forward | R&D_Hardware(1) | N | 2024-10-14 | robin.davis | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R | IMS | 2024-05-09 | christo.wentzel | Smart PowerPack_05-09_07-06 | 10380 | IMS - PCB140110V5_REV2 - Done |  | N | 2024-10-14 |  | NS | 0d |  |  |  |  | Christo Wentzel |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10516 | CDR (Cell cabinet x2) | Mechanics(1) | N | 2024-10-14 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 39 | System testing in R32 | Customer Process Engineering(1), Customer System Engineering(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-14 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | gal.k | Majoris - 1 Mega INV_04-04_14-52 | 2830 | Test Plan Design | Integration(1) | N | 2024-10-14 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3941 | Tester Validation (Hipot - LV Unit) | ATE(1) | N | 2024-10-14 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9462 | CDR (LV Cabinet x2) | Mechanics(1) | N | 2024-10-14 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9487 | CDR (MV Cabinet x2) | Mechanics(1) | N | 2024-10-14 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11165 | Magnetics RnD batch assembly (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2024-10-14 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 352 | Receive - Receive Water Jet | Material Handling(1) | N | 2024-10-14 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | DennisG | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 436 | Mill - Mill Parts for Assembly | Mill(1) | N | 2024-10-14 | Mill | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10372 | PCB140110V5_REV3 - Relay out PCB to pass HOW???? | R&D_Hardware(1) | N | 2024-10-14 | robin.davis | NS | 6d 2h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  |  | PT Testing | 8 | Final Test 1 | COHU A(1) | N | 2024-10-14 |  | NS | 6d 23.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Penchard v1 | 7 | Road Runner behaviour is in place on the shop floor. (positive feedback) | Default(1) | N | 2024-10-15 |  | NS | 6d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8261 | Tester Validation (D1740A Setup) | Utility(1) | N | 2024-10-15 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9746 | Sending PO (Rack Shelves) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9758 | Sending PO (Rack Metal legs) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9771 | Sending PO (Rack Isolated legs) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9785 | Sending PO (Rack Shelf holder) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9798 | Sending PO (Rack Legs base) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9812 | Sending PO (Air core reactor Holder) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9824 | Sending PO (Air core reactor Coil) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9838 | Sending PO (MV busbars) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9851 | Sending PO (LV busbars - busbars) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9863 | Sending PO (LV busbars - holder) | Mechanics(1) | N | 2024-10-15 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | a.lee | RZTest_AWL027177_20230912 | 3579 | EQE Revision Review - KG00001787 | Default Resource(1) | N | 2024-10-15 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | KellyS | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 20 | Fab-Food - Fabrication | Fab-Food(4) | N | 2024-10-15 | Fab-Food | NS | 7d 5.5h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 40 | Process testing in R32 | Customer System Engineering(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-16 |  | NS | 1d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 176 | Everything ready to start commissioning | Customer Process Engineering(1), Customer System Engineering(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-16 |  | NS | 0d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9747 | PO Approved & Send to Production (Rack Shelves) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9759 | PO Approved & Send to Production (Rack Metal legs) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9772 | PO Approved & Send to Production (Rack Isolated legs) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9786 | PO Approved & Send to Production (Rack Shelf holder) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9799 | PO Approved & Send to Production (Rack Legs base) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9813 | PO Approved & Send to Production (Air core reactor Holder) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9825 | PO Approved & Send to Production (Air core reactor Coil) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9839 | PO Approved & Send to Production (MV busbars) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9852 | PO Approved & Send to Production (LV busbars - busbars) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9864 | PO Approved & Send to Production (LV busbars - holder) | Mechanics(1) | N | 2024-10-16 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | n.moyer | RZTest_AWL027177_20230912 | 4794 | EQE Revision Review - KG00003924 (-005) | Default Resource(1) | N | 2024-10-16 |  | NS | 1d 2.7h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3576 | Customer Response and Markup Evaluation - KG00001787 Rev 1 Drawings | Default Resource(1) | N | 2024-10-16 |  | NS | 2023-09-19 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-08-22 | t.morris | RZTest_AWL027177_20230912 | 3578 | KG00001787 Preplanned Resubmit Milestone |  | N | 2024-10-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | 169425 | 16 | 270 Vdc Battery and Installation: Assembly | 1910(1), 2892(1), 3705(1), 3806(2), 8800(1) | N | 2024-10-16 |  | NS | 4d 6h |  |  |  |  | Concerto Admin | 7d | Volume of Work | 1 | 0
R | IMS | 2022-03-23 |  | 169425 | 21 | IMS-MOD PHASE COMPLETE | Default(1) | N | 2024-10-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | 169425 | 31 | Outboard Wing Stations 1 and 11 Assembly: Installs: Door 6318, Panels and Seals ; Door 5317, Panels and Seals; Aileron LH/RH, Leading Edge Flap LH/RH, Outboard Wing LH/RH; Torque Shaft No. 2 | 1910(3), 3806(1), 8852(4) | N | 2024-10-16 |  | NS | 3d 2h |  |  |  |  | Concerto Admin | 4d 5.3h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 33 | All Mods Assembly | 1910(1), 2892(2), 8800(1), 8852(4) | N | 2024-10-16 |  | NS | 3d |  |  |  |  | Concerto Admin | 4d 4.2h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 32 | F3 Fuel Tanks to Add T32 Check Valves(Assembly): Panel Installs: 3310, 3332, 3331 | 1910(1), 8852(2) | N | 2024-10-16 |  | NS | 1d 4h |  |  |  |  | Concerto Admin | 2d 1h | Volume of Work | 1 | 0
R |  |  | 629 E&E | T44_February_2019 | 1911 | E&E ACM | 629_E&E(4) | N | 2024-10-17 |  | NS | 15d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 E&E | T44_February_2019 | 1956 | E&E Electrical/ Avionics | 629_E&E(3) | N | 2024-10-17 |  | NS | 15d |  |  |  |  | Concerto Admin |  |  |  | 1
R | IMS | 2022-07-22 | PS | T44_February_2019 | 2769 | IMS-Release to E0=E&E 2nd Check Insp | Hold(1) | N | 2024-10-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 E&E | T44_February_2019 | 3358 | E&E SMM | 629_E&E(3) | N | 2024-10-17 |  | NS | 15d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 E&E | T44_February_2019 | 3755 | E&E Kits | 629_E&E(3) | N | 2024-10-17 |  | NS | 15d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  |  | Medifab - RFID implementation plan | 41 | Process testing in R24 | Customer System Engineering(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-17 |  | NS | 1d |  |  |  |  | Jaco |  | Network |  | 0
R | PT |  | t.morris | RZTest_AWL027177_20230912 | 3684 | Customer Response and Markup Evaluation - KG00003924 Rev 1 Drawings | Default Resource(1) | N | 2024-10-17 |  | NS | 2023-09-15 |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-08-22 | t.morris | RZTest_AWL027177_20230912 | 3686 | KG00003924 Preplanned Resubmit Milestone |  | N | 2024-10-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 48 | APO Parts - Receive APO Parts | Material Handling(1) | N | 2024-10-17 | Handl | NS | 0d 0.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 46 | Final Kitting - Make sure all parts are avialable for Assembly | Material Handling(1) | N | 2024-10-17 | Handl | NS | 0d 2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S05 169185 PMI-1 R2 | 481 | P8: Final Processing | ARTISAN(6.3) | N | 2024-10-17 |  | NS | 0d 2.8h |  |  |  |  | Concerto Admin | 0d 4.2h | Volume of Work | 0 | 0
R | CMS | 2023-03-16 |  | Majoris - 1 Mega INV_04-04_14-52 | 11681 | Mech Batch (2 Prototypes assembly with STUB + Samples) |  | N | 2024-10-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | V1 S05 169185 PMI-1 R2 | 630 | PMI Complete |  | N | 2024-10-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11230 | Mech Batch (2 Prototypes assembly with STUB + Samples) | Mechanics(1) | N | 2024-10-18 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-03-16 |  | Majoris - 1 Mega INV_04-04_14-52 | 11680 | Mech Batch (2 Prototypes assembly with STUB + Samples) |  | N | 2024-10-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Medifab - RFID implementation plan | 42 | Process testing in R22 | Customer Process Engineering(1), Customer System Engineering(1), Hardware and electrical installer(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-18 |  | NS | 1d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 35 | P6: Post Ops Test Phase | ARTISAN(6) | N | 2024-10-18 |  | NS | 0d 10.8h |  |  |  |  | Concerto Admin | 1d 3.2h | Volume of Work | 0 | 0
R | IMS | 2024-05-13 |  | V1 S06 169186 PMI-1 | 55 | Assembly Complete | ARTISAN(1) | N | 2024-10-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 250 | Define DXF for MC Electronic cards | mechanical Engineer(1.8) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 250 | Define DXF for MC Electronic cards | mechanical Engineer(1.8) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 250 | Define DXF for MC Electronic cards | mechanical Engineer(1.8) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 519 | Define DXF for IB Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 350 | Define DXF for FTER Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1074 | Define DXF for GTER Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 350 | Define DXF for FTER Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 350 | Define DXF for FTER Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 519 | Define DXF for IB Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 519 | Define DXF for IB Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 1074 | Define DXF for GTER Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 1074 | Define DXF for GTER Electronic cards | mechanical Engineer(1) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 243 | Dev. MC Comml SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 247 | Dev. MC Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 243 | Dev. MC Comml SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 243 | Dev. MC Comml SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 247 | Dev. MC Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 247 | Dev. MC Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 240 | Dev. MC Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 361 | Dev.FTER Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 364 | Dev. FTER Comm SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 368 | Dev. FTER Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 371 | Dev. FTER Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1084 | Dev. GTER Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1087 | Dev. GTER Comm SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1090 | Dev. GTER Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1093 | Dev. GTER Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 240 | Dev. MC Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 240 | Dev. MC Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 361 | Dev.FTER Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 361 | Dev.FTER Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 364 | Dev. FTER Comm SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 364 | Dev. FTER Comm SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 368 | Dev. FTER Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 368 | Dev. FTER Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 371 | Dev. FTER Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 371 | Dev. FTER Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1084 | Dev. GTER Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1084 | Dev. GTER Infra SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1087 | Dev. GTER Comm SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1087 | Dev. GTER Comm SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1090 | Dev. GTER Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1090 | Dev. GTER Disp SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1093 | Dev. GTER Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1093 | Dev. GTER Appl SW DROP 2 | SW Engineer(1) | N | 2024-10-21 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8338 | Tester Validation (D1741A Setup) | Utility(1) | N | 2024-10-21 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 50 | DILO with test cases and validation | Customer Process Engineering(1), Customer System Engineering(1), Hardware and electrical installer(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-21 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11166 | Magnetics RnD batch approved (final yield approve) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2024-10-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11170 | Core , coil , winding , bonding jig, other items/tools availability (proto batch (up to 30 units)) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2024-10-21 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S06 169186 PMI-1 | 486 | P7: Paint | ARTISAN(3) | N | 2024-10-21 |  | NS | 5d |  |  |  |  | Concerto Admin | 1d 7.1h | Volume of Work | 0 | 0
R |  |  |  | PT Testing | 9 | Final Test 2 | COHU A(1) | N | 2024-10-21 |  | NS | 4d 23.9h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 35 | P6: Post Ops Test Phase | ARTISAN(5.9) | N | 2024-10-22 |  | NS | 0d 10.5h |  |  |  |  | Concerto Admin | 2d 0.7h | Network | 0 | 0
R | IMS | 2024-05-15 |  | V1 S07 169181 PMI-1_2024 | 55 | P5: Assembly Phase Complete |  | N | 2024-10-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 8 | Engines: Disassembly/Inspection | MECHANICAL(2) | N | 2024-10-22 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 9d 2.6h | Network | 0 | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9915 | Tester Validation (D1976A Setup) | Utility(1) | N | 2024-10-22 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 486 | P7: Paint | ARTISAN(3) | N | 2024-10-22 |  | NS | 6d |  |  |  |  | Concerto Admin | 3d 11h | Network | 0 | 0
R | IMS | 2024-05-16 |  | V1 S07 169181 PMI-1_2024 | 924 | P6: Post Ops Test Phase Complete |  | N | 2024-10-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Penchard v1 | 8 | Managed Buffers and Release Process is in place | Default(1) | N | 2024-10-23 |  | NS | 6d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 49 | Super user training to end users | Customer Process Engineering(1) | N | 2024-10-23 |  | NS | 3d |  |  |  |  | Jaco |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 52 | Commissioning | Customer System Engineering(1), Hardware and electrical installer(1), Integration specialist(1), RFID Engineer(1), Wedoo team(1) | N | 2024-10-23 |  | NS | 2d |  |  |  |  | Jaco |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2846 | final test after aging (GPO3 parts) | Material(1) | N | 2024-10-23 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | louis.loots | Smart PowerPack_05-09_07-06 | 10373 | PCB140110V5_REV3 - BOSCO manufacturing | External SA(1) | N | 2024-10-23 |  | NS | 4d 4h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R | IMS | 2022-04-04 |  | 169425 | 22 | IMS-ASSEMBLY COMPLETE - Transfer to Ops Checks | Default(1) | N | 2024-10-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | 169425 | 38 | POWER ON and Battery (28VDC) - Op Test | 2892(2) | N | 2024-10-23 |  | NS | 0d 2h |  |  |  |  | Concerto Admin | 0d 4h | Volume of Work | 1 | 0
R |  |  |  | 169425 | 17 | HANGAR OPS CHECKS.CF-33 | 1910(1), 2604(2), 2892(3), 8800(2), 8852(6) | N | 2024-10-23 |  | NS | 3d 4h |  |  |  |  | Concerto Admin | 5d 2.6h | Volume of Work | 1 | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 13 | Repair/Installation/Test | MECHANICAL(4.8) | N | 2024-10-24 |  | NS | 5d |  |  |  |  | Manuel Rodriguez | 16d 3.5h | Network | 0 | 0
R | IMS | 2024-01-18 |  | TEST_Airnostrum | 24 | Internal Milestone |  | N | 2024-10-24 |  | NS | 0d |  |  |  |  | Manuel Rodriguez |  |  |  | 0
R |  |  |  | RZTest_AWL027177_20230912 | 3867 | Incorporate Comments and Fab Prep - KG00070783 | Designer Group - Wichita and Mumbai(1.4), Project Manager Group KG NA(0.3) | N | 2024-10-24 |  | NS | 2d 4.7h |  |  |  |  | Concerto Admin | 3d 7h | Network | 1 | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11565 | Cell thermal tests (2 Prototypes) | Mechanics(1) | N | 2024-10-25 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | TestNilesh2 | 6 | t5 | Default(1) | N | 2024-10-25 |  | NS | 15d |  |  |  | Awaiting Funding/Disposition (M9) | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 260 | Glass Bead Blast | Glass Beading(1) | N | 2024-10-25 | GlassB | NS | 6d 3.2h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | PT Testing | 11 | Project End |  | N | 2024-10-26 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 80 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 35d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 13 | Develop MC Processor | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 87d |  |  |  |  | Guy Brill | 87d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 13 | Develop MC Processor | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 87d |  |  |  |  | Guy Brill | 87d | Network | 1 | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 501 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 260 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 25d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 994 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 25d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 33 | Develop FTER Processor | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 73d |  |  |  |  | Guy Brill | 73d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 33 | Develop FTER Processor | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 73d |  |  |  |  | Guy Brill | 73d | Network | 1 | 0
R |  |  | Jacob | ACE Demo 240822_RZ | 500 | Develop IB Mother Board | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  | Jacob | ACE Demo 240822 | 500 | Develop IB Mother Board | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 993 | Develop GTER Processor | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 73d |  |  |  |  | Guy Brill | 73d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 993 | Develop GTER Processor | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 73d |  |  |  |  | Guy Brill | 73d | Network | 1 | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 120 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 139 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 637 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 652 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 667 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 682 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 696 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 711 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 726 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 741 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1010 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1026 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1042 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1058 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 16 | Develop MC LCD Module | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 16 | Develop MC LCD Module | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 17 | Develop MC Display Module | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 17 | Develop MC Display Module | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 18 | Develop MC Mother Board | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 18 | Develop MC Mother Board | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 19 | Develop MC Comm. Computer | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 19 | Develop MC Comm. Computer | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 22 | Develop MC Power Supply | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 22 | Develop MC Power Supply | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 622 | Create a Schematic Design | HW Engineer(1) | N | 2024-10-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 679 | Develop MC Key Board | HW Engineer(0.6), Operations(0.2), PCB layout sub contractor(0.2), PCB production SC(0.1) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 679 | Develop MC Key Board | HW Engineer(0.6), Operations(0.2), PCB layout sub contractor(0.2), PCB production SC(0.1) | N | 2024-10-28 |  | NS | 68d |  |  |  |  | Guy Brill | 68d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 621 | Develop MC Display Computer | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 67d |  |  |  |  | Guy Brill | 67d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 621 | Develop MC Display Computer | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 67d |  |  |  |  | Guy Brill | 67d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 29 | Develop FTER Power Supply | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 66d |  |  |  |  | Guy Brill | 66d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 29 | Develop FTER Power Supply | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 66d |  |  |  |  | Guy Brill | 66d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 1057 | Develop GTER Power Supply | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 66d |  |  |  |  | Guy Brill | 66d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 1057 | Develop GTER Power Supply | HW Engineer(0.5), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.2) | N | 2024-10-28 |  | NS | 66d |  |  |  |  | Guy Brill | 66d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 30 | Develop FTER Key Board | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 30 | Develop FTER Key Board | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 31 | Develop FTER Display Module | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 31 | Develop FTER Display Module | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  | Jacob | ACE Demo 240822 | 277 | Develop FTER MB | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  | Jacob | ACE Demo 240822_RZ | 277 | Develop FTER MB | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  | Jacob | ACE Demo 240822_RZ | 1009 | Develop GTER MB | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  | Jacob | ACE Demo 240822 | 1009 | Develop GTER MB | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 1025 | Develop GTER Display Module | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 1025 | Develop GTER Display Module | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 1041 | Develop GTER Key Board | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 1041 | Develop GTER Key Board | HW Engineer(0.6), Operations(0.1), PCB layout sub contractor(0.2), PCB production SC(0.3) | N | 2024-10-28 |  | NS | 63d |  |  |  |  | Guy Brill | 63d | Network | 1 | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 521 | Detail Design the part | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 520 | Detail Design IB Chassis | mechanical Engineer(1.1) | N | 2024-10-28 |  | NS | 47d |  |  |  |  | Guy Brill | 47d | Network | 1 | 0
R |  |  | Sergey | ACE Demo 240822 | 520 | Detail Design IB Chassis | mechanical Engineer(1.1) | N | 2024-10-28 |  | NS | 47d |  |  |  |  | Guy Brill | 47d | Network | 1 | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 352 | Detail Design the part | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1076 | Detail Design the part | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo 240822 | 351 | Detail Design FTER Chassis | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 50d |  |  |  |  | Guy Brill | 50d | Network | 1 | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 351 | Detail Design FTER Chassis | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 50d |  |  |  |  | Guy Brill | 50d | Network | 1 | 0
R |  |  | Sergey | ACE Demo 240822_RZ | 1075 | Detail Design GTER Chassis | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 50d |  |  |  |  | Guy Brill | 50d | Network | 1 | 0
R |  |  | Sergey | ACE Demo 240822 | 1075 | Detail Design GTER Chassis | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 50d |  |  |  |  | Guy Brill | 50d | Network | 1 | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 252 | Detail Design the part | mechanical Engineer(1) | N | 2024-10-28 |  | NS | 30d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 694 | Develop MC Chassis | mechanical Engineer(1.1) | N | 2024-10-28 |  | NS | 47d |  |  |  |  | Guy Brill | 47d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 694 | Develop MC Chassis | mechanical Engineer(1.1) | N | 2024-10-28 |  | NS | 47d |  |  |  |  | Guy Brill | 47d | Network | 1 | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10515 | CDR Approval (Cell cabinet x2) | Mechanics(1) | N | 2024-10-28 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Medifab - RFID implementation plan | 54 | Handover | RFID Engineer(1) | N | 2024-10-28 |  | NS | 1d |  |  |  |  | Jaco |  | Network |  | 0
G | SNET |  | Noy.B | Majoris - 1 Mega INV_04-04_14-52 | 9972 | SNET - Labs readiness for operation (Full INV) | Utility(1) | Y | 2024-10-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | RZTest_AWL027177_20230912 | 3759 | Incorporate Comments and Fab Prep - KG00014889 | Designer Group - Wichita and Mumbai(1.7), Project Manager Group KG NA(0.3) | N | 2024-10-28 |  | NS | 2d 5.4h |  |  |  |  | Concerto Admin | 4d | Network | 1 | 0
R |  |  |  | V1 S06 169186 PMI-1 | 481 | P8: Final Processing | ARTISAN(6) | N | 2024-10-28 |  | NS | 0d 3h |  |  |  |  | Concerto Admin | 0d 4.5h | Volume of Work | 0 | 0
R |  |  | t.morris | RZTest_AWL027177_20230912 | 3866 | Transmit KG00070783 Final Drawings w/ Rating Sheet to Customer | Project Manager Group KG NA(1) | N | 2024-10-28 |  | NS | 0d 5.3h |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | Medifab - RFID implementation plan | 87 | Project End |  | N | 2024-10-28 |  | NS | 0d |  |  |  |  | Jaco |  |  |  | 0
R | PE |  |  | V1 S06 169186 PMI-1 | 630 | PMI Complete |  | N | 2024-10-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9849 | Rapid units production (RFQ,PO,Production,Shipment) (LV busbars - busbars) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8944 | HW Bring Up Test plan review and approved (D1541B) | Utility(1) | N | 2024-10-29 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3560 | Final DR Layout end (D1541B) | Utility(1) | N | 2024-10-29 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9744 | Rapid units production (RFQ,PO,Production,Shipment) (Rack Shelves) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9756 | Rapid units production (RFQ,PO,Production,Shipment) (Rack Metal legs) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9769 | Rapid units production (RFQ,PO,Production,Shipment) (Rack Isolated legs) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9783 | Rapid units production (RFQ,PO,Production,Shipment) (Rack Shelf holder) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9796 | Rapid units production (RFQ,PO,Production,Shipment) (Rack Legs base) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9810 | Rapid units production (RFQ,PO,Production,Shipment) (Air core reactor Holder) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9822 | Rapid units production (RFQ,PO,Production,Shipment) (Air core reactor Coil) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9836 | Rapid units production (RFQ,PO,Production,Shipment) (MV busbars) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9861 | Rapid units production (RFQ,PO,Production,Shipment) (LV busbars - holder) | Mechanics(1) | N | 2024-10-29 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9905 | DR Elec. By Q&R (D1976A) | QnR(1) | N | 2024-10-29 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | 169425 | 18 | Flightline Operational Checks All Mods | 1910(1), 2604(1), 8852(4) | N | 2024-10-29 |  | NS | 4d |  |  |  |  | Concerto Admin | 6d | Volume of Work | 1 | 0
R | IMS | 2022-04-12 |  | 169425 | 23 | IMS-OPSCHECKSCOMPLETE - Transfer to Flightline | Default(1) | N | 2024-10-29 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | apie.pieterse | Smart PowerPack_05-09_07-06 | 10374 | PCB140110V5_REV3 - Build prototype Apie:- can he fit it in otherwise manual build | Production_SMT(1) | N | 2024-10-29 | robin.davis, tony.baia | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8352 | Design (D1541B Setup) | Utility(1) | N | 2024-10-30 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9748 | DFM approval (Rack Shelves) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9749 | Mold/Tool Design (Rack Shelves) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9760 | DFM approval (Rack Metal legs) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9761 | Mold/Tool Design (Rack Metal legs) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9773 | DFM approval (Rack Isolated legs) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9774 | Mold/Tool Design (Rack Isolated legs) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9787 | DFM approval (Rack Shelf holder) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9788 | Mold/Tool Design (Rack Shelf holder) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9800 | DFM approval (Rack Legs base) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9801 | Mold/Tool Design (Rack Legs base) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9814 | DFM approval (Air core reactor Holder) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9815 | Mold/Tool Design (Air core reactor Holder) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9826 | DFM approval (Air core reactor Coil) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9827 | Mold/Tool Design (Air core reactor Coil) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9840 | DFM approval (MV busbars) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9841 | Mold/Tool Design (MV busbars) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9853 | DFM approval (LV busbars - busbars) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9854 | Mold/Tool Design (LV busbars - busbars) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9865 | DFM approval (LV busbars - holder) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9866 | Mold/Tool Design (LV busbars - holder) | Mechanics(1) | N | 2024-10-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11413 | ECO of PCB approval (D1541B) | Utility(1) | N | 2024-10-30 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | steinerm | Test Part 1 | 11 | Create preliminary designs (#2 of 3) (multiple solutions) | ID_Design(1) | N | 2024-10-30 |  | NS | 5d |  |  |  |  | George |  |  |  | 0
R |  |  |  | V1 S07 169181 PMI-1_2024 | 481 | P8 and P9: Final Processing and FCF | ARTISAN(5.9) | N | 2024-10-30 |  | NS | 0d 2.6h |  |  |  |  | Concerto Admin | 2d 4h | Network | 0 | 0
R | IMS | 2024-05-30 |  | V1 S07 169181 PMI-1_2024 | 925 | P7: Paint Complete |  | N | 2024-10-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | V1 S07 169181 PMI-1_2024 | 630 | P8 and P9: Final Processing and FCF Complete |  | N | 2024-10-31 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Penchard v1 | 9 | Sales Behaviours ready | Default(1) | N | 2024-10-31 |  | NS | 4d |  |  |  |  | johnsonb |  | Network |  | 0
R |  |  | Jefe de Equipo | TEST_Airnostrum | 19 | Operational Tests | MECHANICAL(2.5) | N | 2024-10-31 |  | NS | 2d |  |  |  |  | Manuel Rodriguez | 3d 2.7h | Network | 0 | 0
R |  |  |  | Test11 | 4 | Civil Foundation | DHD(1) | N | 2024-10-31 |  | NS | 25d |  |  |  |  | Deepak Jha |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3582 | BOM 100% (D1541B) | Utility(1) | N | 2024-10-31 | shani.a | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10396 | PCB140110V5_REV3 - Hardware verification | R&D_Hardware(1) | N | 2024-10-31 |  | NS | 4d 4h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10376 | PCB140110V5_REV3 - Do Radiated and Conducted (iSert availability) | External SA(1) | N | 2024-10-31 | robin.davis | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10377 | PCB140110V5_REV3 - If Surge, Radiated and Conducted PASS, do Full Test | External SA(1) | N | 2024-10-31 | robin.davis | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  |  | V1 S06 1 86 | 7 | Post Repair | ARTISAN(14) | N | 2024-11-01 |  | NS | 26d 4.8h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S08 1 82 | 7 | Post Repair | ARTISAN(14) | N | 2024-11-01 |  | NS | 26d 4.8h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S09 1 87 | 7 | Post Repair | ARTISAN(14) | N | 2024-11-01 |  | NS | 26d 4.8h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | V1 S11 1 89 | 7 | Post Repair | ARTISAN(14) | N | 2024-11-01 |  | NS | 26d 4.8h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | RZTest_AWL027177_20230912 | 3543 | Incorporate Comments and Fab Prep - KG00001787 | Designer Group - Wichita and Mumbai(3.4), Project Manager Group KG NA(0.2) | N | 2024-11-01 |  | NS | 3d 3.4h |  |  |  |  | Concerto Admin | 5d 1h | Network | 1 | 0
R | PE |  | Jefe de Proyecto | TEST_Airnostrum | 21 | Project End |  | N | 2024-11-01 |  | NS | 0d |  |  |  |  | Manuel Rodriguez |  |  |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 235 | Dev. MC Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-04 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 235 | Dev. MC Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-04 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 235 | Dev. MC Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-04 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8869 | Mechanics Design (D1744A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11455 | ATP Preparation 90% (D1744A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4462 | Elec. Design Review (HW + Embedded + System) (D1744A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9030 | MCU Hybrid Integration (D1277A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3807 | DR Elec. By Q&R (D1940A) | QnR(1) | N | 2024-11-04 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9095 | ATP Preparation 90% (D1711B) | Utility(1) | N | 2024-11-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10031 | Mechanics Design (D1711B) | Utility(1) | N | 2024-11-04 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11509 | Elec. Design Review (HW + Embedded + System) (D1733A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11510 | ATP Preparation 90% (D1733A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11511 | Mechanics Design (D1733A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11519 | Elec. Design Review (HW + Embedded + System) (D1737A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11520 | ATP Preparation 90% (D1737A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11521 | Mechanics Design (D1737A) | Mechanics(1) | N | 2024-11-04 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11530 | Elec. Design Review (HW + Embedded + System) (D1715A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11531 | ATP Preparation 90% (D1715A) | Utility(1) | N | 2024-11-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11532 | Mechanics Design (D1715A) | Mechanics(1) | N | 2024-11-04 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11539 | Elec. Design Review (HW + Embedded + System) (D1421B) | Utility(1) | N | 2024-11-04 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11540 | ATP Preparation 90% (D1421B) | Utility(1) | N | 2024-11-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11541 | Mechanics Design (D1421B) | Mechanics(1) | N | 2024-11-04 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | 169425 | 34 | LO | 2892(1), 4102(3), 4352(8), 8852(1) | N | 2024-11-04 |  | NS | 6d 2h |  |  |  |  | Concerto Admin | 9d 3.5h | Volume of Work | 1 | 0
R |  |  |  | RZTest_AWL027177_20230912 | 3651 | Incorporate Comments and Fab Prep - KG00003924 | Designer Group - Wichita and Mumbai(1.6), Project Manager Group KG NA(0.1) | N | 2024-11-04 |  | NS | 5d 0.8h |  |  |  |  | Concerto Admin | 7d 5h | Network | 1 | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 18 | Assembly - Final Assembly and Test | AssyFood(3) | N | 2024-11-04 | AssyFood | NS | 2d 4h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | W9585 - 9917-11-100 2-Tier Example | 455 | Assembly and Test | AssyFood(1.9), Engineering(0.1), Queue(0.2) | N | 2024-11-04 |  | NS | 4d |  |  |  |  | Concerto Admin | 4d | Network | 1 | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3912 | PCB automation testing (LV POWER (D1740A)) | Utility(1) | N | 2024-11-05 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9332 | Samples Production & shipment - for Batch -2 (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-11-05 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10528 | RnD Automation infrastructure preparation | Utility(1) | N | 2024-11-05 | shani.a | NS | 120d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Penchard v1 | 10 | Priorities for Release and Production are clear to all | Default(1) | N | 2024-11-06 |  | NS | 4d |  |  |  |  | johnsonb |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9750 | Tool/Mold production (Rack Shelves) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9753 | ECO STP (Rack Shelves) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9762 | Tool/Mold production (Rack Metal legs) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9765 | ECO STP (Rack Metal legs) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9775 | Tool/Mold production (Rack Isolated legs) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9778 | ECO STP (Rack Isolated legs) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9789 | Tool/Mold production (Rack Shelf holder) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9792 | ECO STP (Rack Shelf holder) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9802 | Tool/Mold production (Rack Legs base) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9805 | ECO STP (Rack Legs base) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9816 | Tool/Mold production (Air core reactor Holder) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9819 | ECO STP (Air core reactor Holder) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9828 | Tool/Mold production (Air core reactor Coil) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9831 | ECO STP (Air core reactor Coil) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9842 | Tool/Mold production (MV busbars) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9845 | ECO STP (MV busbars) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9855 | Tool/Mold production (LV busbars - busbars) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9858 | ECO STP (LV busbars - busbars) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9867 | Tool/Mold production (LV busbars - holder) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9870 | ECO STP (LV busbars - holder) | Mechanics(1) | N | 2024-11-06 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | steinerm | Test Part 1 | 8131 | Technical Design review of design concept (# 2 of 3) | ID_Design(1) | N | 2024-11-06 |  | NS | 4d |  |  |  |  | George |  |  |  | 0
R |  |  | 629 Disassembly | T44_February_2019 | 1913 | Select Disassembly | 629_ACM(2), 629_AE(2) | N | 2024-11-07 |  | NS | 3d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | tspielvogel | DP273 | 23 | Final Saw Both Ends | NAF(1) | N | 2024-11-07 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 437 | Machine Run Time | Queue(1) | N | 2024-11-07 | AssyFood | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | TestNilesh2 | 8 | t7 | Default(1) | N | 2024-11-07 |  | NS | 19d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2024-11-01 |  | TestNilesh2 | 12 | Completion Milestone |  | N | 2024-11-07 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10375 | PCB140110V5_REV3 - Do Surge Testing at iSert | External SA(1) | N | 2024-11-07 | robin.davis | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3509 | Layout completion (D1742A) | Utility(1) | N | 2024-11-08 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8917 | HW Bring Up Test plan review and approved (D1679A) | Utility(1) | N | 2024-11-08 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3760 | Final DR Layout end (D1679A) | Utility(1) | N | 2024-11-08 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | BillB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 17 | QC - Engineering QC Check | Engineering(1) | N | 2024-11-08 | Designer | NS | 0d 4h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | JoshT | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 15 | Shipping - Arrange Shipping | Material Handling(1) | N | 2024-11-08 | Handl | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | GaryH | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 439 | Ensure Prior to Ship Payment Received | Production Control(1) | N | 2024-11-08 | LorrisaB | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | W9585 - 9917-11-100 2-Tier Example | 463 | Shipping | AssyFood(0.3), Material Handling(0.3), Planning(0.3), Production Control(0.3) | N | 2024-11-08 |  | NS | 3d |  |  |  |  | Concerto Admin | 3d | Network | 1 | 0
R |  |  | tony.baia | Smart PowerPack_05-09_07-06 | 10378 | PCB140110V5_REV3 - Release all documentation for full build BOMs Gerbers SAP Numbers etc. | R&D_Hardware(1) | N | 2024-11-08 | robin.davis | NS | 0d 8h |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | tspielvogel | DP273 | 24 | Certification | ECF QUAL(1) | N | 2024-11-11 |  | NS | 0d 4h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3607 | DR Elec. By Q&R (D1682A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8336 | Design (D1679A Setup) | Utility(1) | N | 2024-11-11 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11411 | ECO of PCB approval (D1679A) | Utility(1) | N | 2024-11-11 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4386 | PCB automation testing (LV ER CAPS (D1741A)) | Utility(1) | N | 2024-11-11 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 2216 | DR Elec. By Q&R (D1739A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3407 | DR Elec. By Q&R (D1740A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3457 | DR Elec. By Q&R (AP1680A-CP-01-LV) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3507 | DR Elec. By Q&R (D1742A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3557 | DR Elec. By Q&R (D1541B) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 3558 | Mechanics Approval (D1541B) | Mechanics(1) | N | 2024-11-11 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3583 | IGBTs TO-247 Assembly Jig (NPI Ops) (D1541B) | Utility(1) | N | 2024-11-11 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3657 | DR Elec. By Q&R (D1738A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3707 | DR Elec. By Q&R (D1741A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3757 | DR Elec. By Q&R (D1679A) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3931 | Production FT (B2B) | ATE(1) | N | 2024-11-11 |  | NS | 50d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8942 | Mech kit - Heat sinks (D1541B) | Utility(1) | N | 2024-11-11 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10252 | Tester Validation (Hipot - MV Unit) | ATE(1) | N | 2024-11-11 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 10479 | DR Elec. By Q&R (D1710B) | QnR(1) | N | 2024-11-11 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11173 | Magnetics Proto batch assembly (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2024-11-11 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | christo.wentzel | Smart PowerPack_05-09_07-06 | 10209 | Update plan with Certification plan of action | Project Manager(1) | N | 2024-11-11 |  | NS | 0d 2h |  |  | As per HW Standup no need to update plan. |  | Christo Wentzel |  | Network |  | 2
R | IMS | 2024-06-12 | christo.wentzel | Smart PowerPack_05-09_07-06 | 10381 | IMS - PCB140110V5_REV3 - Done |  | N | 2024-11-11 |  | NS | 0d |  |  |  |  | Christo Wentzel |  |  |  | 0
R |  |  | tspielvogel | DP273 | 26 | ECF to ENF Shipment | JB HUNT(1) | N | 2024-11-11 |  | NS | 6d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2024-07-01 | christo.wentzel | Smart PowerPack_05-09_07-06 | 10382 | CMS-Hardware Released |  | N | 2024-11-11 |  | NS | 0d |  |  |  |  | Christo Wentzel |  |  |  | 0
G |  |  | jacintha.rule | Smart PowerPack_05-09_07-06 | 10079 | Roll up BOM costs to enable product pricing | Finance(1) | N | 2024-11-11 | rakesh.ramdeyal | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 1
G |  |  | jacintha.rule | Smart PowerPack_05-09_07-06 | 60 | Close off AUC Code/s | Finance(1) | N | 2024-11-11 | rakesh.ramdeyal | NS | 1d |  |  |  |  | Christo Wentzel |  | Network |  | 1
R |  |  | RobW | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 438 | Prepare Equipment for Shipping | AssyFood(1) | N | 2024-11-11 | Handl | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  | t.morris | RZTest_AWL027177_20230912 | 97 | Engineering & Design Complete |  | N | 2024-11-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | corne.jansevanrensburg | Smart PowerPack_05-09_07-06 | 249 | NRCS LOA Application processing time | External SA(1) | N | 2024-11-11 | christo.wentzel | NS | 53d 3h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R | PE |  |  | Penchard v1 | 13 | Project End |  | N | 2024-11-11 |  | NS | 0d |  |  |  |  | johnsonb |  |  |  | 0
R | IMS | 2022-08-17 | PS | T44_February_2019 | 1914 | IMS-Release to F0=Airframe Repair | Hold(1) | N | 2024-11-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Metals | T44_February_2019 | 3479 | 1.4 LH Wing Center Inspect/ Open-Ups/ Evals | 629_SMM(2) | N | 2024-11-12 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals | T44_February_2019 | 3487 | 1.4 RH Wing Center Inspect/ Open-Ups/ Evals | 629_SMM(2) | N | 2024-11-12 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals | T44_February_2019 | 3458 | 3.3 Window Removal | 629_SMM(1) | N | 2024-11-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3582 | 1.1 RH Wing Inspection | 629_SMM(2) | N | 2024-11-12 |  | NS | 16d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3590 | 1.1 LH Wing Inspection | 629_SMM(2) | N | 2024-11-12 |  | NS | 16d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals | T44_February_2019 | 3453 | 3.2 Window Removal | 629_SMM(1) | N | 2024-11-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3448 | 3.1 TFC Work | 629_SMM(2) | N | 2024-11-12 |  | NS | 10d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3583 | 1.1 RH Fuel Cell Inspection | 629_ACM(1), 629_AE(2), 629_SMM(1) | N | 2024-11-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3591 | 1.1 LH Fuel Cell Inspection | 629_ACM(1), 629_AE(2), 629_SMM(1) | N | 2024-11-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals | T44_February_2019 | 3384 | 3.4 AFT Fuselage Internal | 629_SMM(1) | N | 2024-11-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3782 | BOM 100% (D1679A) | Utility(1) | N | 2024-11-12 | shani.a | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8943 | MP pilot PCBAs + shipment (100 units) (D1541B) | Jabil(1) | N | 2024-11-12 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | 169425 | 35 | Functional Check Flight | 2604(1), 8800(1), 8852(3) | N | 2024-11-12 |  | NS | 3d 2h |  |  |  |  | Concerto Admin | 4d 6.6h | Volume of Work | 1 | 0
G |  |  | christo.wentzel | Smart PowerPack_05-09_07-06 | 61 | Label all Assets with final Asset number | Project Manager(1) | N | 2024-11-12 | corne.jansevanrensburg | NS | 5d |  |  |  |  | Christo Wentzel | 1d | Network | 0 | 1
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 121 | Close Production Order in TRAVERSE | Planning(1) | N | 2024-11-12 | Planner | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Product Manager | Test Part 1 | 5700 | Team review of preliminary designs (#2 of 3) (multiple solutions) | Team(1) | N | 2024-11-12 |  | NS | 1d |  |  |  |  | George |  |  |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2847 | preliminary test before aging (GPO3 parts) | Material(1) | N | 2024-11-13 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | helene.keyser | Smart PowerPack_05-09_07-06 | 10080 | Update SAP Product costing | Group_Sales&Marketing(1) | N | 2024-11-13 |  | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  | LorrisaB | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 359 | Project Complete | Planning(1) | N | 2024-11-13 | Planner | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | W9585 - 9917-11-100 - 2405 IN x 604 IN RAPID RETURN DISTRIBUTION CONVEYOR - POPCOR - 1 EA | 442 | Project End |  | N | 2024-11-13 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | W9585 - 9917-11-100 2-Tier Example | 442 | Project End |  | N | 2024-11-13 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Lead Engineer | Test Part 1 | 12 | Prepare & send out quote package (#1 of 2) | Purchasing(1) | N | 2024-11-13 | engr | NS | 2d |  |  |  |  | George |  |  |  | 1
R |  |  | steinerm | Test Part 1 | 217 | Create 3D evaluation model (form study model) | Model_Shop(1) | N | 2024-11-13 |  | NS | 5d |  |  |  |  | George |  |  |  | 0
R |  |  | Product Manager | Test Part 1 | 7728 | Consumer Research | Service_Provider(1) | N | 2024-11-13 |  | NS | 5d |  |  |  |  | George |  |  |  | 0
R |  |  |  | TestNilesh2 | 7 | t6 | Default(1) | N | 2024-11-15 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9333 | Mold Re-design (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-11-15 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Gantt Rel 17 | 211 | QA Gantt Release 17 |  | N | 2024-11-15 |  | NS | 2d 5.4h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | IMS | 2024-04-04 | christo.wentzel | Smart PowerPack_05-09_07-06 | 10211 | IMS-SAP BOM updated |  | N | 2024-11-15 |  | NS | 0d |  |  |  |  | Christo Wentzel |  |  |  | 1
R | PE |  |  | 169425 | 39 | Project End |  | N | 2024-11-15 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | buyer | Test Part 1 | 13 | Prepare preliminary quotes | Supplier(1) | N | 2024-11-15 | buyer | NS | 15d |  |  |  |  | George |  |  |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 502 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 121 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 140 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 638 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 653 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 668 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 683 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 697 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 712 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 727 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 742 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1011 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1027 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1043 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1059 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 623 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-11-18 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 244 | Dev. MC Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 248 | Dev. MCDisp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 244 | Dev. MC Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 244 | Dev. MC Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 248 | Dev. MCDisp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 248 | Dev. MCDisp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 241 | Dev. MC Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 362 | Dev. FTER Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 365 | Dev. FTER Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 369 | Dev. FTER Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 372 | Dev. FTER Disp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1085 | Dev. GTER Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1088 | Dev. GTER Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1091 | Dev. GTER Disp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 1094 | Dev. GTER Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 241 | Dev. MC Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 241 | Dev. MC Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 362 | Dev. FTER Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 362 | Dev. FTER Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 365 | Dev. FTER Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 365 | Dev. FTER Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 369 | Dev. FTER Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 369 | Dev. FTER Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 372 | Dev. FTER Disp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 372 | Dev. FTER Disp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1085 | Dev. GTER Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1085 | Dev. GTER Infra SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1088 | Dev. GTER Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1088 | Dev. GTER Comm SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1091 | Dev. GTER Disp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1091 | Dev. GTER Disp SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 1094 | Dev. GTER Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 1094 | Dev. GTER Appl SW DROP 3 | SW Engineer(1) | N | 2024-11-18 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 68 | Build BTN Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 69 | Build BTY Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 70 | Build FO Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 68 | Build BTN Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 68 | Build BTN Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 69 | Build BTY Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 69 | Build BTY Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 70 | Build FO Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 70 | Build FO Network Env. | HW Engineer(1) | N | 2024-11-18 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3660 | Final DR Layout end (D1738A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2700 | Final DR Layout end (D1739A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9057 | Mechanics Design (D1371B) | Utility(1) | N | 2024-11-18 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3610 | Final DR Layout end (D1682A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8937 | HW Bring Up Test plan review and approved (D1738A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11497 | Elec. Design Review (HW + Embedded + System) (D1371B) | Utility(1) | N | 2024-11-18 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11498 | ATP Preparation 90% (D1371B) | Utility(1) | N | 2024-11-18 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8951 | HW Bring Up Test plan & RnD Automation review and approved (D1682A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8965 | HW Bring Up Test plan review and approved (D1739A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | ACE Demo 2-Tier | 574 | Dev. MC Appl SW DROP 4-6 | SW Engineer(1) | N | 2024-11-18 |  | NS | 45d |  |  |  |  | Guy Brill | 45d | Network | 1 | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3272 | Hot crimp terminal (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-11-18 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3430 | Design (D1740A) | ATE(1) | Y | 2024-11-18 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3953 | Design (D1679A) | ATE(1) | N | 2024-11-18 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3957 | Design (D1541B) | ATE(1) | N | 2024-11-18 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4890 | Design (D1741A) | ATE(1) | N | 2024-11-18 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9096 | ATE Design Review (ATP 100%) (D1711B) | Utility(1) | N | 2024-11-18 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9167 | ATE Design Review (ATP 100%) (D1737A) | Utility(1) | N | 2024-11-18 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10494 | Design (D1710B) | ATE(1) | Y | 2024-11-18 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11050 | Core assembly (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-11-18 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11177 | QnR tests (Choke for ER caps (4081PQ2620)) | QnR(1) | N | 2024-11-18 | Dana.h, Elianna.z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | mmassa | DP273 | 27 | Turn for Sonic & Sonic | Bore_Warren(1) | N | 2024-11-18 |  | NS | 254d 6.5h |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3457 | 3.3 TFC Window Frame | 629_SMM(1) | N | 2024-11-19 |  | NS | 10d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3452 | 3.2 TFC Window Frame | 629_SMM(1) | N | 2024-11-19 |  | NS | 10d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11412 | ECO of PCB approval (D1738A) | Utility(1) | N | 2024-11-19 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11416 | ECO of PCB approval (D1739A) | Utility(1) | N | 2024-11-19 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11414 | ECO of PCB approval (D1682A) | Utility(1) | N | 2024-11-19 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11833 | Cell & Busbar integration (2 Prototypes) | Mechanics(1) | N | 2024-11-19 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11834 | Cell locking mechanism integration (2 Prototypes) | Mechanics(1) | N | 2024-11-19 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8344 | Design (D1738A Setup) | Utility(1) | N | 2024-11-19 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8348 | Design (D1682A Setup) | Utility(1) | N | 2024-11-19 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8360 | Design (D1739A Setup) | Utility(1) | N | 2024-11-19 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3955 | Design (D1738A) | ATE(1) | N | 2024-11-19 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4897 | Design (D1739A) | ATE(1) | N | 2024-11-19 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9984 | Potting materials preliminary tests before aging | Material(1) | N | 2024-11-19 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | Gantt Rel 17 | 214 | Gantt Release 17 |  | N | 2024-11-19 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 503 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 122 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 141 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 639 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 654 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 669 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 684 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 698 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 713 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 728 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 743 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1012 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1028 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1044 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1060 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 624 | Prepare card CDR | HW Engineer(1) | N | 2024-11-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3682 | BOM 100% (D1738A) | Utility(1) | N | 2024-11-20 | shani.a | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 61 | BOM 100% (D1739A) | Utility(1) | N | 2024-11-20 | shani.a | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3632 | BOM 100% (D1682A) | Utility(1) | N | 2024-11-20 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2848 | intermediate test mid-aging (GPO3 parts) | Material(1) | N | 2024-11-20 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | steinerm | Test Part 1 | 8030 | Univeral Design Review | ID_Design(1) | N | 2024-11-20 |  | NS | 1d |  |  |  |  | George |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 3758 | Mechanics Approval (D1679A) | Mechanics(1) | N | 2024-11-21 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8916 | MP pilot PCBAs + shipment (25 units) (D1679A) | Jabil(1) | N | 2024-11-21 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8915 | Mech kit - busbars (D1679A) | Utility(1) | N | 2024-11-21 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 5701 | Team review of form model & universal design evaluation | Team(1) | N | 2024-11-21 |  | NS | 2d |  |  |  |  | George |  |  |  | 1
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11567 | Vibration tests (2 Prototypes) | Mechanics(1) | N | 2024-11-22 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 504 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 123 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 142 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 640 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 655 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 670 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 685 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 699 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 714 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 729 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 744 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1013 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1029 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1045 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1061 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 625 | Conduct card CDR | HW Engineer(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 236 | Dev. MC Appl SW DROP 4 | SW Engineer(1) | N | 2024-11-25 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 236 | Dev. MC Appl SW DROP 4 | SW Engineer(1) | N | 2024-11-25 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 236 | Dev. MC Appl SW DROP 4 | SW Engineer(1) | N | 2024-11-25 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 531 | Produce cables | Operations(5) | N | 2024-11-25 |  | NS | 4d |  |  |  |  | Guy Brill | 4d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 531 | Produce cables | Operations(5) | N | 2024-11-25 |  | NS | 4d |  |  |  |  | Guy Brill | 4d | Network | 1 | 0
R |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3949 | Tester Validation (Connectivity - LV Unit) | ATE(1) | N | 2024-11-25 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | WMS en RETAIL | 29 | Pruebas Unitarias y Entrenamiento de COMPRAS & INVENTARIO | Experto de Procesos(1) | N | 2024-11-25 |  | NS | 15d |  |  |  |  | Fiallos | 15d | Network | 1 | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9950 | Tester Validation (Hipot) | ATE(1) | N | 2024-11-25 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9954 | Tester Validation (Connectivity) | ATE(1) | N | 2024-11-25 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10256 | Tester Validation (Connectivity - MV Unit) | ATE(1) | N | 2024-11-25 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11052 | Testing before potting (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-11-25 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Lead Engineer | Test Part 1 | 1951 | Prepare for Design Review #1 of 3 | Engineering(1) | N | 2024-11-25 | engr | NS | 3d |  |  |  |  | George |  |  |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3480 | 1.4 LH Wing Center TFC's/ Blends/ Support Needed | 629_SMM(2) | N | 2024-11-26 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3488 | 1.4 RH Wing Center TFC's/ Blends/ Support Needed | 629_SMM(2) | N | 2024-11-26 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3449 | 3.1 Repairs/ Replacements | 629_SMM(2) | N | 2024-11-26 |  | NS | 15d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 505 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 124 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 143 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 641 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 656 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 671 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 686 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 700 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 715 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 730 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 745 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1014 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1030 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1046 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1062 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 626 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-11-26 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11051 | Bobbin potting (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-11-26 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 3608 | Mechanics Approval (D1682A) | Mechanics(1) | N | 2024-11-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 3633 | MP pilot PCBAs + shipment (100 units) (D1682A) | Jabil(1) | N | 2024-11-27 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | V1 S06 1 86 | 3 | Project End |  | N | 2024-11-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | V1 S08 1 82 | 3 | Project End |  | N | 2024-11-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | V1 S09 1 87 | 3 | Project End |  | N | 2024-11-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | V1 S11 1 89 | 3 | Project End |  | N | 2024-11-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 627 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-28 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 628 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-28 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10007 | Potting materials supply to Hilkar | Material(1) | N | 2024-11-28 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10014 | Potting material selection for trails | Material(1) | N | 2024-11-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Lead Engineer | Test Part 1 | 2395 | Conduct "Design Review" #1 of 3 | Design_Review_Committee(1) | N | 2024-11-28 | engr | NS | 1d |  |  |  |  | George |  |  |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 507 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 126 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 145 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 642 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 657 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 672 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 687 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 701 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 716 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 731 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 746 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1015 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1031 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1047 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1063 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 508 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 127 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 146 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 643 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 658 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 673 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 688 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 702 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 717 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 732 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 747 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1016 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1032 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1048 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1064 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-11-29 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 61 | Produce TER Data Cable | Operations(1) | N | 2024-11-29 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 532 | Produce MC Power Cable | Operations(1) | N | 2024-11-29 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 533 | Produce TER Power Cable | Operations(1) | N | 2024-11-29 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 534 | Produce IB-Radio Cable | Operations(1) | N | 2024-11-29 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 535 | Produce MC Data Cable | Operations(1) | N | 2024-11-29 |  | NS | 4d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1124 | Cables bring up | HW Engineer(1) | N | 2024-11-29 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1124 | Cables bring up | HW Engineer(1) | N | 2024-11-29 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Test11 | 5 | Fabrication | DHD(1) | N | 2024-11-29 |  | NS | 15d |  |  |  |  | Deepak Jha |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 3658 | Mechanics Approval (D1738A) | Mechanics(1) | N | 2024-11-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8935 | MP pilot PCBAs + shipment (25 units) (D1738A) | Jabil(1) | N | 2024-11-29 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.k | Majoris - 1 Mega INV_04-04_14-52 | 2243 | Mechanics Approval (D1739A) | Mechanics(1) | N | 2024-11-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8963 | MP pilot PCBAs + shipment (25 units) (D1739A) | Jabil(1) | N | 2024-11-29 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9335 | Transformer component approval for assembly (5 Hilkar transformer prototype) | Mechanics(1) | N | 2024-11-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 261 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-12-02 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 995 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-12-02 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 72 | Perform Simulator ATP | HW Engineer(1) | N | 2024-12-02 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 72 | Perform Simulator ATP | HW Engineer(1) | N | 2024-12-02 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 72 | Perform Simulator ATP | HW Engineer(1) | N | 2024-12-02 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8335 | Production (D1679A Setup) | Utility(1) | N | 2024-12-02 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4501 | Elec. Design Review (HW + Embedded + System) (D1732A) | Utility(1) | N | 2024-12-02 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4503 | ATP Preparation 90% (D1732A) | Utility(1) | N | 2024-12-02 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9039 | Mechanics Design (D1732A) | Utility(1) | N | 2024-12-02 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9194 | SW Basic Version (D1737A) | SW(1) | N | 2024-12-02 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11548 | Elec. Design Review (HW + Embedded + System) (D1420A) | Utility(1) | N | 2024-12-02 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11549 | ATP Preparation 90% (D1420A) | Utility(1) | N | 2024-12-02 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11550 | Mechanics Design (D1420A) | Mechanics(1) | N | 2024-12-02 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3459 | 3.3 Bond/Install Windows | 629_SMM(1) | N | 2024-12-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3454 | 3.2 Bond/Install Windows | 629_SMM(1) | N | 2024-12-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 0
R | IMS | 2022-08-18 |  | ACE Demo detiled tasks 240822_RZ | 77 | Deliver Simulator to MC/FTER/GTER Bring up | PM(1) | N | 2024-12-03 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-08-18 |  | ACE Demo 240822_RZ | 77 | Deliver Simulator to MC/FTER/GTER Bring up | PM(1) | N | 2024-12-03 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-08-18 |  | ACE Demo 240822 | 77 | Deliver Simulator to MC/FTER/GTER Bring up | PM(1) | N | 2024-12-03 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3441 | HW Testing 25c (D1740A) | Utility(1) | N | 2024-12-03 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3585 | 1.1 RH SMM Repairs | 629_SMM(1) | N | 2024-12-04 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3593 | 1.1 LH SMM Repairs | 629_SMM(1) | N | 2024-12-04 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3586 | 1.1 RH Repair De Ice Boot | 629_SMM(2) | N | 2024-12-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3594 | 1.1 LH Repair De Ice Boot | 629_SMM(2) | N | 2024-12-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 262 | Prepare card CDR | HW Engineer(1) | N | 2024-12-04 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 996 | Prepare card CDR | HW Engineer(1) | N | 2024-12-04 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9751 | Samples Production & shipment - for Batch -1 (Rack Shelves) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9763 | Samples Production & shipment - for Batch -1 (Rack Metal legs) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9776 | Samples Production & shipment - for Batch -1 (Rack Isolated legs) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9790 | Samples Production & shipment - for Batch -1 (Rack Shelf holder) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9803 | Samples Production & shipment - for Batch -1 (Rack Legs base) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9817 | Samples Production & shipment - for Batch -1 (Air core reactor Holder) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9829 | Samples Production & shipment - for Batch -1 (Air core reactor Coil) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9843 | Samples Production & shipment - for Batch -1 (MV busbars) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9856 | Samples Production & shipment - for Batch -1 (LV busbars - busbars) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9868 | Samples Production & shipment - for Batch -1 (LV busbars - holder) | Mechanics(1) | N | 2024-12-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | TestNilesh2 | 9 | t8 | Default(1) | N | 2024-12-04 |  | NS | 21d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3460 | 3.3 Repairs | 629_SMM(1) | N | 2024-12-05 |  | NS | 11d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | T44_February_2019 | 3600 | 3.2 Repairs | 629_SMM(1) | N | 2024-12-05 |  | NS | 8d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1124 | Cables bring up | HW Engineer(1) | N | 2024-12-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 67 | Perform Cables ATP | HW Engineer(1) | N | 2024-12-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 67 | Perform Cables ATP | HW Engineer(1) | N | 2024-12-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1110 | Cables HW tests | HW Engineer(1) | N | 2024-12-06 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1110 | Cables HW tests | HW Engineer(1) | N | 2024-12-06 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 15 | Review preliminary quotes | Team(1) | N | 2024-12-06 |  | NS | 5d |  |  |  |  | George |  |  |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 263 | Conduct card CDR | HW Engineer(1) | N | 2024-12-09 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 997 | Conduct card CDR | HW Engineer(1) | N | 2024-12-09 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 523 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2024-12-09 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 353 | Prepare mechanical CDR | mechanical Engineer(1) | N | 2024-12-09 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1077 | Prepare mechanical CDR | mechanical Engineer(1) | N | 2024-12-09 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 254 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2024-12-09 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3741 | HW Testing 25c (D1741A) | Utility(1) | N | 2024-12-09 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9463 | CDR Approval (LV Cabinet x2) | Mechanics(1) | N | 2024-12-09 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9464 | Packing Preparation (LV Cabinet x2) | Mechanics(1) | N | 2024-12-09 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9466 | PO Preperation Process +Sending (LV Cabinet x2) | Mechanics(1) | N | 2024-12-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9488 | CDR Approval (MV Cabinet x2) | Mechanics(1) | N | 2024-12-09 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9489 | Packing Preparation (MV Cabinet x2) | Mechanics(1) | N | 2024-12-09 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9491 | PO Preperation Process +Sending (MV Cabinet x2) | Mechanics(1) | N | 2024-12-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3481 | 1.4 LH Wing Center Initial Repairs | 629_SMM(2) | N | 2024-12-10 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3489 | 1.4 RH Wing Center Initial Repairs | 629_SMM(2) | N | 2024-12-10 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 264 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-12-10 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 998 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-12-10 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3442 | HW Testing 85\125 (D1740A) | Utility(1) | N | 2024-12-10 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 524 | Freeze Chassis | mechanical Engineer(1) | N | 2024-12-11 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 255 | Freeze MC Chassis | mechanical Engineer(1) | N | 2024-12-11 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8351 | Production (D1541B Setup) | Utility(1) | N | 2024-12-11 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2849 | final test after aging (GPO3 parts) | Material(1) | N | 2024-12-11 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3742 | HW Testing 85\125 (D1741A) | Utility(1) | N | 2024-12-11 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 525 | Produce IB Chassis parts | mechanical Engineer(1) | N | 2024-12-12 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 354 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2024-12-12 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1078 | Conduct mechanical CDR | mechanical Engineer(1) | N | 2024-12-12 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 256 | Produce MC Chassis parts | mechanical Engineer(1) | N | 2024-12-12 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 67 | Perform Cables ATP | HW Engineer(1) | N | 2024-12-12 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1110 | Cables HW tests | HW Engineer(1) | N | 2024-12-12 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10034 | Core material approval | Material(1) | N | 2024-12-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 266 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-12-13 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 999 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-12-13 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 267 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-12-13 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1000 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-12-13 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R | IMS | 2022-10-18 |  | ACE Demo 240822 | 76 | Deliver Cables to MC/FTER/GTER bring up | PM(1) | N | 2024-12-13 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-10-18 |  | ACE Demo 240822_RZ | 76 | Deliver Cables to MC/FTER/GTER bring up | PM(1) | N | 2024-12-13 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11900 | Dust Chamber tests (2 Prototypes) | Mechanics(1) | N | 2024-12-13 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3743 | HW Testing -40 (D1741A) | Utility(1) | N | 2024-12-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | buyer | Test Part 1 | 8121 | Prepare preliminary quotes (#2 of 2) | Supplier(1) | N | 2024-12-13 | buyer | NS | 15d |  |  |  |  | George |  |  |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 81 | Release partial BOM (80%) | HW Engineer(1) | N | 2024-12-16 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 237 | Dev. MC Appl SW DROP 5 | SW Engineer(1) | N | 2024-12-16 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 237 | Dev. MC Appl SW DROP 5 | SW Engineer(1) | N | 2024-12-16 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 237 | Dev. MC Appl SW DROP 5 | SW Engineer(1) | N | 2024-12-16 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 355 | Freeze FTER Chassis | mechanical Engineer(1) | N | 2024-12-16 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1079 | Freeze GTER Chassis | mechanical Engineer(1) | N | 2024-12-16 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 245 | Dev. MC Comm SW DROP 4 | SW Engineer(1) | N | 2024-12-16 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 249 | Dev. MC Disp SW DROP 4 | SW Engineer(1) | N | 2024-12-16 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 245 | Dev. MC Comm SW DROP 4 | SW Engineer(1) | N | 2024-12-16 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 245 | Dev. MC Comm SW DROP 4 | SW Engineer(1) | N | 2024-12-16 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 249 | Dev. MC Disp SW DROP 4 | SW Engineer(1) | N | 2024-12-16 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 249 | Dev. MC Disp SW DROP 4 | SW Engineer(1) | N | 2024-12-16 |  | NS | 20d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8334 | Tester Validation (D1679A Setup) | Utility(1) | N | 2024-12-16 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | WMS en RETAIL | 40 | Pruebas de Integración | Experto de Procesos(1) | N | 2024-12-16 |  | NS | 15d |  |  |  |  | Fiallos | 15d | Network | 1 | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9467 | Sending PO (LV Cabinet x2) | Mechanics(1) | N | 2024-12-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9492 | Sending PO (MV Cabinet x2) | Mechanics(1) | N | 2024-12-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10458 | Mech - Racks assembly x2 | Mechanics(1) | N | 2024-12-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10459 | Mech - Air core reactor assembly x2 | Mechanics(1) | N | 2024-12-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10460 | Mech - MV busbars assembly x2 | Mechanics(1) | N | 2024-12-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10461 | Mech - LV busbars assembly x2 | Mechanics(1) | N | 2024-12-16 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3385 | 3.6 Cockpit/Cabin External | 629_SMM(1) | N | 2024-12-17 |  | NS | 12d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3386 | 3.5 Nose External | 629_SMM(1) | N | 2024-12-17 |  | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 356 | Produce FTER Chassis parts | mechanical Engineer(1) | N | 2024-12-17 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1080 | Produce GTER Chassis parts | mechanical Engineer(1) | N | 2024-12-17 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | Test11 | 6 | Erection Equipment | DHD(1) | N | 2024-12-17 |  | NS | 10d |  |  |  |  | Deepak Jha |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3443 | HW Testing -40 (D1740A) | Utility(1) | N | 2024-12-17 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3744 | Tests result review (D1741A) | Utility(1) | N | 2024-12-17 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9468 | PO Approved & Send to Production (LV Cabinet x2) | Mechanics(1) | N | 2024-12-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9493 | PO Approved & Send to Production (MV Cabinet x2) | Mechanics(1) | N | 2024-12-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 82 | Prepare card CDR | HW Engineer(1) | N | 2024-12-18 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 630 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-19 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 629 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-19 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R | IMS | 2022-10-18 |  | ACE Demo detiled tasks 240822_RZ | 76 | Deliver Cables to MC/FTER/GTER bring up | PM(1) | N | 2024-12-19 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3383 | 3.7 AFT Fuselage External | 629_SMM(1) | N | 2024-12-20 |  | NS | 6d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 509 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 129 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 148 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 645 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 660 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 675 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 690 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 704 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 719 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 734 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 749 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1018 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1034 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1050 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1066 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-20 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 128 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 147 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 644 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 659 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 674 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 689 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 703 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 718 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 733 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 748 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1017 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1033 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1049 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1065 | Prepare Gerber files | HW Engineer(1) | N | 2024-12-20 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11457 | ECO of PCB (D1744A) | Utility(1) | N | 2024-12-20 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10696 | PO Preparation Process + Sending (LV Unit Enclosure base) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10709 | PO Preparation Process + Sending (LV Unit Busbars) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10714 | PO Preparation Process + Sending (LV Unit Heat sink) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10719 | PO Preparation Process + Sending (LV Unit Enclosure cover) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Elad.T | Majoris - 1 Mega INV_04-04_14-52 | 11835 | Review for the 2 Prototypes (QnR) | QnR(1) | N | 2024-12-20 | Dana.h, Elianna.z | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11836 | Review for the 2 Prototypes (OPS) | Ops(1) | N | 2024-12-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | yonatan.b | Majoris - 1 Mega INV_04-04_14-52 | 11837 | Review for the 2 Prototypes (ATE) | ATE(1) | N | 2024-12-20 | Hagit.R | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3510 | Final DR Layout end (D1742A) | Utility(1) | N | 2024-12-20 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8955 | HW Bring Up Test plan review and approved (D1742A) | Utility(1) | N | 2024-12-20 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9511 | PO Preperation Process + Sending (MV Unit Enclosure base) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10566 | PO Preparation Process + Sending (MV Unit Enclosure cover) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10596 | PO Preparation Process + Sending (MV Unit Heat sink) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10602 | PO Preparation Process + Sending (MV Unit Air duct) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10608 | PO Preparation Process + Sending (MV Unit Busbars) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10825 | PO Preparation Process + Sending (Enclosure Base plate) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10831 | PO Preparation Process + Sending (Enclosure Separators) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10838 | PO Preparation Process + Sending (Enclosure Back plate) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10843 | PO Preparation Process + Sending (Enclosure Fan) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10848 | PO Preparation Process + Sending (Enclosure Front plate) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10853 | PO Preparation Process + Sending (Enclosure Planum) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 3275 | 3D models preparation (Batch RnD (5 Hilkar transformer)) | Mechanics(1) | N | 2024-12-20 | michael.ra | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 83 | Conduct card CDR | HW Engineer(1) | N | 2024-12-23 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 510 | Freeze electronic BOM | HW Engineer(1) | N | 2024-12-23 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 631 | Check Layout DFM | PCB production SC(1) | N | 2024-12-23 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11456 | pre-placement (D1744A) | Utility(1) | N | 2024-12-23 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11415 | ECO of PCB approval (D1742A) | Utility(1) | N | 2024-12-23 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8356 | Design (D1742A Setup) | Utility(1) | N | 2024-12-23 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3951 | Production (D1740A) | ATE(1) | N | 2024-12-23 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3952 | Production (D1679A) | ATE(1) | N | 2024-12-23 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3956 | Production (D1541B) | ATE(1) | N | 2024-12-23 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3958 | Design (D1742A) | ATE(1) | N | 2024-12-23 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4891 | Production (D1741A) | ATE(1) | N | 2024-12-23 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10495 | Production (D1710B) | ATE(1) | N | 2024-12-23 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 84 | Freeze schematics after implementing CDR comments | HW Engineer(1) | N | 2024-12-24 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 131 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 150 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 646 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 661 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 676 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 691 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 705 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 720 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 735 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 750 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1019 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1035 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1051 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1067 | Check Layout DFM | PCB production SC(1) | N | 2024-12-24 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3532 | BOM 100% (D1742A) | Utility(1) | N | 2024-12-24 | shani.a | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3444 | Tests result review (D1740A) | Utility(1) | N | 2024-12-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3954 | Production (D1738A) | ATE(1) | N | 2024-12-24 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4898 | Production (D1739A) | ATE(1) | N | 2024-12-24 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11081 | Bobbin testing after potting (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-12-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 512 | Check Layout DFM | PCB production SC(1) | N | 2024-12-25 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3276 | DFM Approved (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-12-25 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 87 | Design PCB Layout | PCB layout sub contractor(1) | N | 2024-12-26 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 88 | Prepare Interface Control Drawing | HW Engineer(1) | N | 2024-12-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 632 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-26 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 526 | Assemble IB Chassis | mechanical Engineer(1) | N | 2024-12-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 257 | Assemble MC Chassis | mechanical Engineer(1) | N | 2024-12-26 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3273 | Magnetics RnD batch assembly (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2024-12-26 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 132 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 151 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 647 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 662 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 677 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 692 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 706 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 721 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 736 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 751 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1020 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1036 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1052 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1068 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-27 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10697 | Sending PO (LV Unit Enclosure base) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10710 | Sending PO (LV Unit Busbars) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10715 | Sending PO (LV Unit Heat sink) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10720 | Sending PO (LV Unit Enclosure cover) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9512 | Sending PO (MV Unit Enclosure base) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10567 | Sending PO (MV Unit Enclosure cover) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10597 | Sending PO (MV Unit Heat sink) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10603 | Sending PO (MV Unit Air duct) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10609 | Sending PO (MV Unit Busbars) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10826 | Sending PO (Enclosure Base plate) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10832 | Sending PO (Enclosure Separators) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10839 | Sending PO (Enclosure Back plate) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10844 | Sending PO (Enclosure Fan) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10849 | Sending PO (Enclosure Front plate) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10854 | Sending PO (Enclosure Planum) | Mechanics(1) | N | 2024-12-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Test11 | 7 | Commisioning | DHD(1) | N | 2024-12-28 |  | NS | 5d |  |  |  |  | Deepak Jha |  | Network |  | 0
R |  |  | 629 MODS | T44_February_2019 | 3435 | Electrical O&As | 629_AE(4) | N | 2024-12-30 | Electrician | NS | 14d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3436 | O&As Mechanical Repair | 629_ACM(6) | N | 2024-12-30 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 513 | Prepare panelization and masks | PCB production SC(1) | N | 2024-12-30 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 633 | PCB Production | PCB production SC(1) | N | 2024-12-30 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11452 | Mech. Design Review (D1744A) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11453 | ATE Design Review (ATP 100%) (D1744A) | Utility(1) | N | 2024-12-30 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11454 | Q&R Design Review (D1744A) | QnR(1) | N | 2024-12-30 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10698 | PO Approved & Send to Production (LV Unit Enclosure base) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10711 | PO Approved & Send to Production (LV Unit Busbars) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10716 | PO Approved & Send to Production (LV Unit Heat sink) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10721 | PO Approved & Send to Production (LV Unit Enclosure cover) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11403 | Cell Standalone - block 1 development - with Hybrid | SW(1) | N | 2024-12-30 |  | NS | 50d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9513 | PO Approved & Send to Production (MV Unit Enclosure base) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10568 | PO Approved & Send to Production (MV Unit Enclosure cover) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10598 | PO Approved & Send to Production (MV Unit Heat sink) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10604 | PO Approved & Send to Production (MV Unit Air duct) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10610 | PO Approved & Send to Production (MV Unit Busbars) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8350 | RnD automation setup validation (D1541B Setup) | Utility(1) | N | 2024-12-30 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10488 | Tester Validation (D1710B Setup) | Utility(1) | N | 2024-12-30 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10827 | PO Approved & Send to Production (Enclosure Base plate) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10833 | PO Approved & Send to Production (Enclosure Separators) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10840 | PO Approved & Send to Production (Enclosure Back plate) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10845 | PO Approved & Send to Production (Enclosure Fan) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10850 | PO Approved & Send to Production (Enclosure Front plate) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10855 | PO Approved & Send to Production (Enclosure Planum) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9207 | ATE Design Review (ATP 100%) (D1715A) | Utility(1) | N | 2024-12-30 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9248 | ATE Design Review (ATP 100%) (D1421B) | Utility(1) | N | 2024-12-30 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11501 | Mech. Design Review (D1711B) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11502 | Elec. Design Review (HW + Embedded + System) (D1711B) | Utility(1) | N | 2024-12-30 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11503 | Q&R Design Review (D1711B) | QnR(1) | N | 2024-12-30 | Dana.h, Elianna.z | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11506 | Q&R Design Review (D1733A) | QnR(1) | N | 2024-12-30 | Dana.h, Elianna.z | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11507 | ATE Design Review (ATP 100%) (D1733A) | Utility(1) | N | 2024-12-30 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11508 | Mech. Design Review (D1733A) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11516 | Q&R Design Review (D1737A) | QnR(1) | N | 2024-12-30 | Dana.h, Elianna.z | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11518 | Mech. Design Review (D1737A) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11527 | Q&R Design Review (D1715A) | QnR(1) | N | 2024-12-30 | Dana.h, Elianna.z | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11529 | Mech. Design Review (D1715A) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11536 | Q&R Design Review (D1715A) | QnR(1) | N | 2024-12-30 | Dana.h, Elianna.z | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11538 | Mech. Design Review (D1421B) | Mechanics(1) | N | 2024-12-30 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3482 | 1.4 LH Wing Center Repairs/ O&A's | 629_SMM(2) | N | 2024-12-31 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3490 | 1.4 RH Wing Center Repairs/ O&A's | 629_SMM(2) | N | 2024-12-31 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 133 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 152 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 648 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 663 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 678 | PCB Production | HW Engineer(0.5), Operations(0.5) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 693 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 707 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 722 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 737 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 752 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1021 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1037 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1053 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1069 | PCB Production | PCB production SC(1) | N | 2024-12-31 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 527 | Deliver IB Chassis for IB ATP | mechanical Engineer(1) | N | 2024-12-31 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 357 | Assemble FTER Chassis | mechanical Engineer(1) | N | 2024-12-31 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1081 | Assemble GTER Chassis | mechanical Engineer(1) | N | 2024-12-31 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 258 | Deliver MC Chassis for MC ATP | mechanical Engineer(1) | N | 2024-12-31 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8343 | Production (D1738A Setup) | Utility(1) | N | 2024-12-31 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8347 | Production (D1682A Setup) | Utility(1) | N | 2024-12-31 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8359 | Production (D1739A Setup) | Utility(1) | N | 2024-12-31 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9469 | DFM approval (LV Cabinet x2) | Mechanics(1) | N | 2024-12-31 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9470 | Mold/Tool Design(LV Cabinet x2) | Mechanics(1) | N | 2024-12-31 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9494 | DFM approval (MV Cabinet x2) | Mechanics(1) | N | 2024-12-31 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9495 | Mold/Tool Design(MV Cabinet x2) | Mechanics(1) | N | 2024-12-31 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3587 | 1.1 RH Electrical Zonals | 629_AE(1) | N | 2025-01-01 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3595 | 1.1 LH Electrical Zonals | 629_AE(1) | N | 2025-01-01 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 514 | PCB Production | PCB production SC(1) | N | 2025-01-01 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 2839 | Design for Testing Process (GPO3 parts) | Material(1) | N | 2025-01-01 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3287 | allocate SEM PN (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-01 | Reuven.Z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3288 | allocate ECM PN (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-01 | Reuven.Z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8959 | MP pilot PCBAs + shipment (25 units) (D1742A) | Jabil(1) | N | 2025-01-02 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3289 | initiate BOM 90% (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-02 | Reuven.Z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 3853 | Assembly instruction document (Batch -2 (25 Cells)) | Ops(1) | N | 2025-01-02 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 3854 | BOM 100% (Batch -2 (25 Cells)) | Ops(1) | N | 2025-01-02 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | yossi.g | Majoris - 1 Mega INV_04-04_14-52 | 3855 | BOM & Assembly instruction review (Batch -2 (25 Cells)) (QnR) | QnR(1) | N | 2025-01-02 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 3856 | LLI (Batch -2 (25 Cells)) | Ops(1) | N | 2025-01-02 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 3857 | Shortage Report ( Batch -2 (25 Cells)) | Ops(1) | N | 2025-01-02 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 3858 | ECOs in Agile (Batch -2 (25 Cells)) | Ops(1) | N | 2025-01-02 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 3859 | Product line readiness (Batch -2 (25 Cells)) | Ops(1) | N | 2025-01-02 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8958 | Mech kit - Busbars (D1742A) | Utility(1) | N | 2025-01-02 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | Test11 | 9 | Project End |  | N | 2025-01-02 |  | NS | 0d |  |  |  |  | Deepak Jha |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 269 | Freeze electronic BOM | HW Engineer(1) | N | 2025-01-03 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1002 | Freeze electronic BOM | HW Engineer(1) | N | 2025-01-03 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 268 | Prepare Gerber files | HW Engineer(1) | N | 2025-01-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1001 | Prepare Gerber files | HW Engineer(1) | N | 2025-01-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 358 | Deliver FTER Chassis for FTER ATP | mechanical Engineer(1) | N | 2025-01-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Sergey | ACE Demo detiled tasks 240822_RZ | 1082 | Deliver GTER Chassis for GTER ATP | mechanical Engineer(1) | N | 2025-01-03 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 8122 | Review preliminary quotes (#2 of 2) | Team(1) | N | 2025-01-03 |  | NS | 2d |  |  |  |  | George |  |  |  | 1
R | PE |  |  | WMS en RETAIL | 50 | Salida a VIVO |  | N | 2025-01-03 |  | NS | 0d |  |  |  |  | Fiallos |  |  |  | 0
R |  |  | 629 Metals_44 | T44_February_2019 | 3589 | 1.1 RH Final Install/Close Ups Electrical | 629_AE(1) | N | 2025-01-06 |  | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3588 | 1.1 RH Final Install/Close Ups | 629_ACM(1) | N | 2025-01-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3596 | 1.1 LH Final Install/Close Ups | 629_ACM(1) | N | 2025-01-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals_44 | T44_February_2019 | 3597 | 1.1 LH Final Install/Close Ups Electrical | 629_AE(1) | N | 2025-01-06 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Dov | ACE Demo detiled tasks 240822_RZ | 238 | Dev. MC Appl SW DROP 6 | SW Engineer(1) | N | 2025-01-06 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822 | 238 | Dev. MC Appl SW DROP 6 | SW Engineer(1) | N | 2025-01-06 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Dov | ACE Demo 240822_RZ | 238 | Dev. MC Appl SW DROP 6 | SW Engineer(1) | N | 2025-01-06 |  | NS | 15d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4389 | PCB automation testing (LV IN RELAY (D1679A)) | Utility(1) | N | 2025-01-06 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4388 | PCB automation testing (MV POWER (D1541B)) | Utility(1) | N | 2025-01-06 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10503 | PCB automation testing (MV BYPASS (D1710B)) | Utility(1) | N | 2025-01-06 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 271 | Check Layout DFM | PCB production SC(1) | N | 2025-01-07 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1003 | Check Layout DFM | PCB production SC(1) | N | 2025-01-07 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9471 | Tool/Mold production (LV Cabinet x2) | Mechanics(1) | N | 2025-01-07 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9496 | Tool/Mold production (MV Cabinet x2) | Mechanics(1) | N | 2025-01-07 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | buyer | Test Part 1 | 7996 | Prepare quotes for BC2 | Supplier(1) | N | 2025-01-07 | buyer | NS | 5d |  |  |  |  | George |  |  |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11579 | PCB first bring-up (MV DC CAPS (D1682A)) | Utility(1) | N | 2025-01-08 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11200 | Specifications (Choke for ER caps (1061PQ2012)) | Magnetic(1) | Y | 2025-01-08 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10006 | Potting process definition | Material(1) | N | 2025-01-09 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10499 | HW Testing 25c (D1710B) | Utility(1) | N | 2025-01-09 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11054 | Testing after assembly (Batch RnD (5 Hilkar transformer)) | Magnetic(1) | N | 2025-01-09 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 272 | Prepare panelization and masks | PCB production SC(1) | N | 2025-01-10 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1004 | Prepare panelization and masks | PCB production SC(1) | N | 2025-01-10 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11576 | PCB first bring-up (LV DIGITAL (D1738A)) | Utility(1) | N | 2025-01-10 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11578 | PCB first bring-up (MV DIGITAL (D1739A)) | Utility(1) | N | 2025-01-10 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11496 | Mech. Design Review (D1371B) | Utility(1) | N | 2025-01-13 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10699 | Samples Production & shipment (LV Unit Enclosure base) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10712 | Samples Production & shipment (LV Unit Busbars) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10717 | Samples Production & shipment (LV Unit Heat sink) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10722 | Samples Production & shipment (LV Unit Enclosure cover) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11495 | ATE Design Review (ATP 100%) (D1371B) | Utility(1) | N | 2025-01-13 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9061 | Q&R Design Review (D1371B) | Utility(1) | N | 2025-01-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8355 | Production (D1742A Setup) | Utility(1) | N | 2025-01-13 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9515 | Samples Production & shipment (MV Unit Enclosure base) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10569 | Samples Production & shipment (MV Unit Enclosure cover) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10599 | Samples Production & shipment (MV Unit Heat sink) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10605 | Samples Production & shipment (MV Unit Air duct) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10611 | Samples Production & shipment (MV Unit Busbars) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10828 | Samples Production & shipment (Enclosure Base plate) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10834 | Samples Production & shipment (Enclosure Separators) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10841 | Samples Production & shipment (Enclosure Back plate) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10846 | Samples Production & shipment (Enclosure Fan) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10851 | Samples Production & shipment (Enclosure Front plate) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10856 | Samples Production & shipment (Enclosure Planum) | Jabil(1) | N | 2025-01-13 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | ACE Demo 2-Tier | 12 | Develop MC ATP | System Engineer(1) | N | 2025-01-13 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9154 | SW Basic Version (D1733A) | SW(1) | N | 2025-01-13 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9234 | SW Basic Version (D1715A) | SW(1) | N | 2025-01-13 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9275 | SW Basic Version (D1421B) | SW(1) | N | 2025-01-13 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9752 | Mold Re-design (Rack Shelves) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9764 | Mold Re-design (Rack Metal legs) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9777 | Mold Re-design (Rack Isolated legs) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9791 | Mold Re-design (Rack Shelf holder) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9804 | Mold Re-design (Rack Legs base) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9818 | Mold Re-design (Air core reactor Holder) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9830 | Mold Re-design (Air core reactor Coil) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9844 | Mold Re-design (MV busbars) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9857 | Mold Re-design (LV busbars - busbars) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9869 | Mold Re-design (LV busbars - holder) | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10456 | Mech - Cell Cabinet assembly x2 | Mechanics(1) | N | 2025-01-13 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10500 | HW Testing 85\125 (D1710B) | Utility(1) | N | 2025-01-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 273 | PCB Production | PCB production SC(1) | N | 2025-01-14 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1005 | PCB Production | PCB production SC(1) | N | 2025-01-14 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 634 | Assemble MC Display Computer card | Operations(1) | N | 2025-01-14 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10005 | Potting trials test plan | Material(1) | N | 2025-01-14 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 7997 | Select supplier | Team(1) | N | 2025-01-14 |  | NS | 1d |  |  |  |  | George |  |  |  | 1
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 134 | Assemble MC Comm. computer card | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 153 | Assemble MC MB | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 207 | Assemble MC KB | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 225 | Assemble MC PS | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 649 | Assemble MC Disp. Module | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 664 | Assemble MC LCD Module | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 708 | Assemble FTER MB card | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 723 | Assemble FTER Disp. Module card | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 738 | Assemble FTER Key Board | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 753 | Assemble FTER Power Supply | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 1022 | Assemble GTER MB card | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 1038 | Assemble GTER Disp. Module card | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 1054 | Assemble GTER Key Board | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 1070 | Assemble GTER Power Supply | Operations(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10501 | HW Testing -40 (D1710B) | Utility(1) | N | 2025-01-15 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11201 | New chock spec preparation (Elec & Mech) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-01-15 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 6710 | Update Phase 2 Business Case | Product_Mgmt(1) | N | 2025-01-15 |  | NS | 1d |  |  |  |  | George |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 90 | Freeze electronic BOM | HW Engineer(1) | N | 2025-01-16 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 89 | Prepare Gerber files | HW Engineer(1) | N | 2025-01-16 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 515 | Assemble IB MB | Operations(1) | N | 2025-01-16 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3274 | Magnetics RnD batch approved (5 Hilkar transformer) | Magnetic(1) | N | 2025-01-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3280 | Core spec (design approved) (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-16 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9979 | PD tests (5 Hilkar transformer prototype) | Utility(1) | N | 2025-01-16 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 10507 | winding, Bobin (after potting) other items/tools availability (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11071 | Thermal tests (5 Hilkar transformer prototype) | Mechanics(1) | N | 2025-01-16 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11072 | production line design (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 6711 | Approve Phase 2 Business Case & Submit Financial Data | Team(1) | N | 2025-01-16 |  | NS | 3d |  |  |  |  | George |  |  |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10502 | Tests result review (D1710B) | Utility(1) | N | 2025-01-17 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 93 | Check Layout DFM | PCB production SC(1) | N | 2025-01-20 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8354 | Tester Validation (D1742A Setup) | Utility(1) | N | 2025-01-20 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3431 | Tester Validation (D1740A) | ATE(1) | N | 2025-01-20 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3580 | Test Validation (D1541B) | ATE(1) | N | 2025-01-20 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3779 | Tester Validation(D1679A) | ATE(1) | N | 2025-01-20 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4892 | Tester Validation(D1741A) | ATE(1) | N | 2025-01-20 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 10496 | Tester Validation (D1710B) | ATE(1) | N | 2025-01-20 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3483 | 1.4 LH 44 Gallon Repairs | 629_SMM(2) | N | 2025-01-21 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Metals | T44_February_2019 | 3606 | 1.4 RH 44 Gallon Repairs | 629_SMM(2) | N | 2025-01-21 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 635 | Bring up MC Display Computer card | HW Engineer(1) | N | 2025-01-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10004 | Potting trials execution | Material(1) | N | 2025-01-21 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | steinerm | Test Part 1 | 5702 | Final design intent (#3 of 3) (1 solution) | ID_Design(1) | N | 2025-01-21 |  | NS | 5d |  |  |  |  | George |  |  |  | 1
R |  |  | buyer | Test Part 1 | 7309 | Issue Award Letter to Supplier | Purchasing(1) | N | 2025-01-21 |  | NS | 0d 4h |  |  |  |  | George |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 135 | Bring up MC Comm. computer card | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 154 | Bring up MC MB | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 208 | Bring up MC KB | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 226 | Bring up MC PS | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 650 | Bring up MC Disp Module | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 665 | Bring up MC LCD Module | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 709 | Bring up FTER MB card | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 724 | Bring up FTER Disp. Module card | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 739 | Bring up FTER Key Board | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 754 | Bring up FTER Power Supply | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1023 | Bring up GTER MB card | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1039 | Bring up GTER Disp. Module card | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1055 | Bring up GTER Key Board | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1071 | Bring up GTER Power Supply | HW Engineer(1) | N | 2025-01-22 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11592 | SW development for PCB test Version (D1682A Setup) | SW(1) | N | 2025-01-22 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11203 | Core , coil , winding , bonding jig, other items/tools availability (RnD batch (up to 5 units)) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-01-22 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 94 | Prepare panelization and masks | PCB production SC(1) | N | 2025-01-23 |  | NS | 2d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 516 | Bring up IB MB | HW Engineer(1) | N | 2025-01-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1108 | IB bring up | HW Engineer(1), SW Engineer(1) | N | 2025-01-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1108 | IB bring up | HW Engineer(1), SW Engineer(1) | N | 2025-01-23 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3278 | Core , coil, bonding jig, other items/tools availability (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-01-23 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 3686 | SW development for PCB test Version (D1738A) | SW(1) | N | 2025-01-24 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 3265 | SW development for PCB test Version (D1739A) | SW(1) | N | 2025-01-24 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | TestNilesh2 | 11 | Project End |  | N | 2025-01-24 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 95 | PCB Production | PCB production SC(1) | N | 2025-01-27 |  | NS | 11d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4472 | Layout (D1744A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 60d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11451 | Design Review (D1744A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8972 | HW Bring Up Test plan review and approved (D1744A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3959 | Production (D1742A) | ATE(1) | N | 2025-01-27 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4466 | BOM 90% (D1744A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 4467 | BOM Review by Q&R (D1744A) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8557 | Mega INV Setup integration and Certification | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9087 | SW Basic Version (D1371B) | SW(1) | N | 2025-01-27 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9097 | Design Review (D1711B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9099 | BOM 98% (D1711B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9100 | BOM Review by Q&R (D1711B) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9105 | ECO of PCB (D1711B) | Utility(1) | N | 2025-01-27 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9111 | HW Bring Up Test plan & RnD Automation review and approved (D1711B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9126 | Design Review (D1733A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9129 | BOM 95% (D1733A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9130 | BOM Review by Q&R (D1733A) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9135 | ECO of PCB (D1733A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9141 | HW Bring Up Test plan review and approved (D1733A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9166 | Design Review (D1737A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9169 | BOM 95% (D1737A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9170 | BOM Review by Q&R (D1737A) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9175 | ECO of PCB (D1737A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9181 | HW Bring Up Test plan review and approved (D1737A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9206 | Design Review (D1715A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9209 | BOM 95% (D1715A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9210 | BOM Review by Q&R (D1715A) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9215 | ECO of PCB (D1715A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9221 | HW Bring Up Test plan review and approved (D1715A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9247 | Design Review (D1421B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9250 | BOM 95% (D1421B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9251 | BOM Review by Q&R (D1421B) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9262 | HW Bring Up Test plan review and approved (D1421B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9286 | ATE Design Review (ATP 100%) (D1420A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9754 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9766 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9779 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9793 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9806 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9820 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9832 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9846 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9859 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9871 | Component approval for Mega INV Readiness | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11480 | Mech. Design Review (D1732A) | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11482 | Q&R Design Review (D1732A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11483 | ATE Design Review (ATP 100%) (D1732A) | Utility(1) | N | 2025-01-27 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11542 | ECO of PCB (D1421B) | Utility(1) | N | 2025-01-27 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11545 | Q&R Design Review (D1420A) | QnR(1) | N | 2025-01-27 | Dana.h, Elianna.z | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11547 | Mech. Design Review (D1420A) | Mechanics(1) | N | 2025-01-27 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3491 | 1.4 RH Wing Center Final Repairs | 629_SMM(2) | N | 2025-01-28 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3605 | 1.4 LH Wing Center Final Repairs | 629_SMM(2) | N | 2025-01-28 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 636 | Deliver MC Display Computer for MC ATP | HW Engineer(1) | N | 2025-01-28 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8973 | Design (D1744A Setup) | Utility(1) | N | 2025-01-28 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9112 | Design (D1711B Setup) | Utility(1) | N | 2025-01-28 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9136 | pre-placement (D1733A) | Mechanics(1) | N | 2025-01-28 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9142 | Design (D1733A Setup) | Utility(1) | N | 2025-01-28 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9182 | Design (D1737A Setup) | Utility(1) | N | 2025-01-28 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9216 | pre-placement (D1715A) | Mechanics(1) | N | 2025-01-28 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9222 | Design (D1715A Setup) | Utility(1) | N | 2025-01-28 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9263 | Design (D1421B Setup) | Utility(1) | N | 2025-01-28 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | steinerm | Test Part 1 | 8133 | Technical Design review of design concept (# 3 of 3) | ID_Design(1) | N | 2025-01-28 |  | NS | 4d |  |  |  |  | George |  |  |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 274 | Assemble FTER Processor card | Operations(1) | N | 2025-01-29 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 1006 | Assemble GTER Processor card | Operations(1) | N | 2025-01-29 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 136 | Deliver MC Comm. computer for MC ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 155 | Deliver MC MB for MC ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 209 | Deliver MC KB for MC ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 227 | Deliver MC PS for MC ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 651 | Deliver MC Disp. Module for MC ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 666 | Deliver MC LCD Module for MC ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 710 | Deliver FTER MB for FTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 725 | Deliver FTER Disp. Module for FTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 740 | Deliver FTER Key Board for FTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 755 | Deliver FTER Power Supply for FTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1024 | Deliver GTER MB for GTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1040 | Deliver GTER Disp. Module for GTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1056 | Deliver GTER Key Board for GTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1072 | Deliver GTER Power Supply for GTER ATP | HW Engineer(1) | N | 2025-01-29 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 517 | Deliver IB MB for IB ATP | HW Engineer(1) | N | 2025-01-30 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 55 | Perform IB ATP | HW Engineer(1) | N | 2025-01-30 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 55 | Perform IB ATP | HW Engineer(1) | N | 2025-01-30 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1109 | IB HW tests | HW Engineer(1) | N | 2025-01-30 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1109 | IB HW tests | HW Engineer(1) | N | 2025-01-30 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9375 | Sending PO (40 Hilkar transformer MP for Batch -1) | Mechanics(1) | N | 2025-01-30 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10003 | Potting process report from Hilkar | Material(1) | N | 2025-01-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1108 | IB bring up | HW Engineer(1), SW Engineer(1) | N | 2025-01-31 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9376 | PO Approved & Send to Production (40 Hilkar transformer MPfor Batch -1) | Mechanics(1) | N | 2025-01-31 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11400 | Mech parts purchase process | Mechanics(1) | N | 2025-01-31 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3791 | HW Testing 25c (D1679A) | Utility(1) | N | 2025-02-03 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 8967 | Component sampels (D1744A) | QnR(1) | N | 2025-02-03 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9102 | Component sampels (D1711B) | QnR(1) | N | 2025-02-03 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9132 | Component sampels (D1733A) | QnR(1) | N | 2025-02-03 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9172 | Component sampels (D1737A) | QnR(1) | N | 2025-02-03 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9212 | Component sampels (D1715A) | QnR(1) | N | 2025-02-03 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9253 | Component sampels (D1421B) | QnR(1) | N | 2025-02-03 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Product Manager | Test Part 1 | 5703 | Team review of final design intent (#3 of 3) (1 solution) | Team(1) | N | 2025-02-03 |  | NS | 0d 4h |  |  |  |  | George |  |  |  | 1
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9103 | Component Evaluation (D1711B) | QnR(1) | N | 2025-02-04 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9137 | Layout (D1733A) | Utility(1) | N | 2025-02-04 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9217 | Layout (D1715A) | Utility(1) | N | 2025-02-04 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9472 | Samples Production & shipment - for Batch -1 (LV Cabinet x2) | Mechanics(1) | N | 2025-02-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9497 | Samples Production & shipment - for Batch -1 (MV Cabinet x2) | Mechanics(1) | N | 2025-02-04 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | Test Part 1 | 7650 | Project End |  | N | 2025-02-04 |  | NS | 0d |  |  |  |  | George |  |  |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 275 | Bring up FTER Processor card | HW Engineer(1) | N | 2025-02-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1007 | Bring up GTER Processor card | HW Engineer(1) | N | 2025-02-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3792 | HW Testing 85\125 (D1679A) | Utility(1) | N | 2025-02-05 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2022-10-20 |  | ACE Demo 240822_RZ | 75 | Deliver IB to MC/FTER/GTER bring up | PM(1) | N | 2025-02-06 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-10-20 |  | ACE Demo 240822 | 75 | Deliver IB to MC/FTER/GTER bring up | PM(1) | N | 2025-02-06 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  |  | ACE Demo 240822 | 563 | FTER bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 563 | FTER bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1095 | GTER bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1095 | GTER bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-06 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9994 | Review and approval of transformer prototype assembly process | Material(1) | N | 2025-02-06 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10243 | Received potted samples from Hilkar | Mechanics(1) | N | 2025-02-06 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 55 | Perform IB ATP | HW Engineer(1) | N | 2025-02-07 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1109 | IB HW tests | HW Engineer(1) | N | 2025-02-07 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3793 | HW Testing -40 (D1679A) | Utility(1) | N | 2025-02-07 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9379 | Tool/Mold production (40 Hilkar transformer MPfor Batch -1) | Mechanics(1) | N | 2025-02-07 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10011 | Transformer materials examination before aging | Material(1) | N | 2025-02-07 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11401 | material lead time | Mechanics(1) | N | 2025-02-07 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11494 | Design Review (D1371B) | Utility(1) | N | 2025-02-10 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11500 | ECO of PCB (D1371B) | Utility(1) | N | 2025-02-10 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9075 | HW Bring Up Test plan review and approved (D1371B) | Utility(1) | N | 2025-02-10 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9063 | BOM 90% (D1371B) | Utility(1) | N | 2025-02-10 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9064 | BOM Review by Q&R (D1371B) | QnR(1) | N | 2025-02-10 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 9311 | SW Basic Version (D1420A) | SW(1) | N | 2025-02-10 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10010 | Transformers CT scan - before aging | Material(1) | N | 2025-02-10 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3485 | 1.4 LH Wing Center Final Closeups | 629_SMM(2) | N | 2025-02-11 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Metals | T44_February_2019 | 3492 | 1.4 RH Wing Center Final Closeups | 629_SMM(2) | N | 2025-02-11 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Elias | ACE Demo detiled tasks 240822_RZ | 96 | Assemble MC Processor card | Operations(1) | N | 2025-02-11 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9070 | pre-placement (D1371B) | Mechanics(1) | N | 2025-02-11 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9076 | Design (D1371B Setup) | Utility(1) | N | 2025-02-11 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3794 | Tests result review (D1679A) | Utility(1) | N | 2025-02-11 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9264 | Production (D1421B Setup) | Utility(1) | N | 2025-02-11 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 276 | Deliver FTER Processor for FTER ATP | HW Engineer(1) | N | 2025-02-12 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 1008 | Deliver GTER Processor for GTER ATP | HW Engineer(1) | N | 2025-02-12 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8346 | RnD automation setup validation (D1682A Setup) | Utility(1) | N | 2025-02-12 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11204 | Magnetics RnD batch assembly (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-02-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 564 | FTER HW tests | HW Engineer(1) | N | 2025-02-13 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 564 | FTER HW tests | HW Engineer(1) | N | 2025-02-13 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 1096 | GTER HW tests | HW Engineer(1) | N | 2025-02-13 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 1096 | GTER HW tests | HW Engineer(1) | N | 2025-02-13 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 38 | Perform FTER ATP | INT Engineer(1.9), SW Engineer(2.8) | N | 2025-02-13 |  | NS | 28d |  |  |  |  | Guy Brill | 28d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 38 | Perform FTER ATP | INT Engineer(1.9), SW Engineer(2.8) | N | 2025-02-13 |  | NS | 28d |  |  |  |  | Guy Brill | 28d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 1098 | Perform GTER ATP | INT Engineer(1.9), SW Engineer(2.8) | N | 2025-02-13 |  | NS | 28d |  |  |  |  | Guy Brill | 28d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 1098 | Perform GTER ATP | INT Engineer(1.9), SW Engineer(2.8) | N | 2025-02-13 |  | NS | 28d |  |  |  |  | Guy Brill | 28d | Network | 1 | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4385 | PCB automation testing (MV BYPASS (D1742A)) | Utility(1) | N | 2025-02-13 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 9983 | Potting materials preliminary tests after aging | Material(1) | N | 2025-02-13 |  | NS | 45d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10009 | Mid-aging test | Material(1) | N | 2025-02-13 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2022-10-20 |  | ACE Demo detiled tasks 240822_RZ | 75 | Deliver IB to MC/FTER/GTER bring up | PM(1) | N | 2025-02-14 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 563 | FTER bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-14 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1095 | GTER bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-14 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10455 | Mech - LV Cabinet assembly x2 | Mechanics(1) | N | 2025-02-14 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10457 | Mech - MV Cabinet assembly x2 | Mechanics(1) | N | 2025-02-14 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo 2-Tier | 561 | MC bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-17 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3591 | HW Testing 25c (D1541B) | Utility(1) | N | 2025-02-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 4469 | Component Evaluation (D1744A) | QnR(1) | N | 2025-02-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9066 | Component sampels (D1371B) | QnR(1) | N | 2025-02-17 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9133 | Component Evaluation (D1733A) | QnR(1) | N | 2025-02-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9173 | Component Evaluation (D1737A) | QnR(1) | N | 2025-02-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9213 | Component Evaluation (D1715A) | QnR(1) | N | 2025-02-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9254 | Component Evaluation (D1421B) | QnR(1) | N | 2025-02-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11107 | ATP finalized (Batch -1 (50 Hilkar transformer)) | Utility(1) | N | 2025-02-17 | Reuven.Z, shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 97 | Bring up MC Processor card | HW Engineer(1) | N | 2025-02-18 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9071 | Layout (D1371B) | Utility(1) | N | 2025-02-18 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9067 | Component Evaluation (D1371B) | QnR(1) | N | 2025-02-18 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9449 | PCB automation testing (MV DC CAPS (D1682A)) | Utility(1) | N | 2025-02-19 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3592 | HW Testing 85\125 (D1541B) | Utility(1) | N | 2025-02-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11205 | Magnetics RnD batch approved (final yield approve) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-02-19 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11209 | Core , coil , winding , bonding jig, other items/tools availability (proto batch (up to 30 units)) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-02-19 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 564 | FTER HW tests | HW Engineer(1) | N | 2025-02-21 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1096 | GTER HW tests | HW Engineer(1) | N | 2025-02-21 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 566 | FTER ATP Cycle 1 | INT Engineer(5) | N | 2025-02-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1099 | GTER ATP Cycle 1 | INT Engineer(5) | N | 2025-02-21 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3593 | HW Testing -40 (D1541B) | Utility(1) | N | 2025-02-21 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | christo.wentzel | Smart PowerPack_05-09_07-06 | 3 | Project Review | Project Manager(1) | N | 2025-02-21 | corne.jansevanrensburg | NS | 1d 7h |  |  |  |  | Christo Wentzel |  | Network |  | 0
R |  |  |  | ACE Demo 2-Tier | 562 | MC HW tests | HW Engineer(1) | N | 2025-02-24 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  |  | ACE Demo 2-Tier | 26 | Perform MC ATP | INT Engineer(2.3), SW Engineer(2.4) | N | 2025-02-24 |  | NS | 32d |  |  |  |  | Guy Brill | 32d | Network | 1 | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3530 | Tester Validation (D1742A) | ATE(1) | N | 2025-02-24 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4505 | BOM 90% (D1732A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 4506 | BOM Review by Q&R (D1732A) | QnR(1) | N | 2025-02-24 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 4521 | SW Basic Version (D1732A) | SW(1) | N | 2025-02-24 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9046 | HW Bring Up Test plan review and approved (D1732A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9285 | Design Review (D1420A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9288 | BOM 95% (D1420A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9289 | BOM Review by Q&R (D1420A) | QnR(1) | N | 2025-02-24 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9300 | HW Bring Up Test plan review and approved (D1420A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11481 | Design Review (D1732A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11487 | ECO of PCB (D1732A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11553 | ECO of PCB (D1420A) | Utility(1) | N | 2025-02-24 | shani.a | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  | christo.wentzel | Smart PowerPack_05-09_07-06 | 7 | Project End |  | N | 2025-02-24 |  | NS | 0d |  |  |  |  | Christo Wentzel |  |  |  | 1
R | IMS | 2022-11-30 | PS | T44_February_2019 | 2650 | IMS-Release to G0=Initial Assembly | Hold(1) | N | 2025-02-25 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3438 | Select Assembly | 629_ACM(2) | N | 2025-02-25 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Jacob | ACE Demo detiled tasks 240822_RZ | 98 | Deliver MC Processor for MC ATP | HW Engineer(1) | N | 2025-02-25 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8974 | Production (D1744A Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3594 | Tests result review (D1541B) | Utility(1) | N | 2025-02-25 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9047 | Design (D1732A Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9113 | Production (D1711B Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9143 | Production (D1733A Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9183 | Production (D1737A Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9223 | Production (D1715A Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9265 | Tester Validation (D1421B Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9301 | Design (D1420A Setup) | Utility(1) | N | 2025-02-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 561 | MC bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 561 | MC bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 561 | MC bring up | HW Engineer(1), SW Engineer(1) | N | 2025-02-26 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 567 | Bug fixes | SW Engineer(5) | N | 2025-02-28 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1100 | Bug fixes | SW Engineer(5) | N | 2025-02-28 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9050 | Component sampels (D1732A) | QnR(1) | N | 2025-03-03 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9291 | Component sampels (D1420A) | QnR(1) | N | 2025-03-03 | Dana.h, Elianna.z | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3439 | Surface Installs | 629_ACM(2) | N | 2025-03-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 4508 | Component Evaluation (D1732A) | QnR(1) | N | 2025-03-04 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 562 | MC HW tests | HW Engineer(1) | N | 2025-03-05 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 562 | MC HW tests | HW Engineer(1) | N | 2025-03-05 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 562 | MC HW tests | HW Engineer(1) | N | 2025-03-05 |  | NS | 60d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 554 | MC ATP Cycle 1 | INT Engineer(5) | N | 2025-03-05 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 26 | Perform MC ATP | INT Engineer(2.4), SW Engineer(2.5) | N | 2025-03-05 |  | NS | 31d |  |  |  |  | Guy Brill | 31d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 26 | Perform MC ATP | INT Engineer(2.4), SW Engineer(2.5) | N | 2025-03-05 |  | NS | 31d |  |  |  |  | Guy Brill | 31d | Network | 1 | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11171 | ATP initiated (Choke for ER caps (4081PQ2620) , magnetics batch Proto) | Magnetic(1) | N | 2025-03-05 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2904 | PREP FOR WING INSTALL | 629_ACM(3) | N | 2025-03-06 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11076 | Core assembly (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-03-06 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11080 | Hot crimp terminal (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-03-06 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2905 | WING INSTALL L/H & R/H | 629_ACM(4), 629_AE(1) | N | 2025-03-07 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8342 | RnD automation setup validation (D1738A Setup) | Utility(1) | N | 2025-03-07 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11417 | MV Unit tester version | SW(1) | N | 2025-03-07 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11418 | LV Unit tester version | SW(1) | N | 2025-03-07 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8358 | RnD automation setup validation (D1739A Setup) | Utility(1) | N | 2025-03-07 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3680 | Test Validation (D1738A) | ATE(1) | N | 2025-03-07 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4899 | Tester Validation (D1739A) | ATE(1) | N | 2025-03-07 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9380 | Samples Production & shipment - for Batch -1 (40 Hilkar transformer MPfor Batch -1) | Mechanics(1) | N | 2025-03-07 | michael.ra | NS | 8d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11352 | Block 2 - Cell B2B development | SW(1) | N | 2025-03-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11577 | Cell Standalone - block 1 development | SW(1) | N | 2025-03-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2871 | PANEL INSTALLS | 629_AE(1) | N | 2025-03-11 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2872 | INSTALL CIRCUIT CARDS | 629_AE(1) | N | 2025-03-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2876 | INSTALL LIGHT ASSEMBLIES | 629_AE(1) | N | 2025-03-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2887 | INSTALL PEDESTAL AND COMPONENTS | 629_ACM(1), 629_AT(1) | N | 2025-03-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2892 | INSTALL A/C BATTERY | 629_AE(1) | N | 2025-03-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2922 | PERFORM SET UP, BATTERY & ANNUNCIATOR PANEL | 629_AE(1) | N | 2025-03-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2923 | PERFORM OP CHECK OF ELECTRICAL POWER SYSTEM | 629_AE(2) | N | 2025-03-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9077 | Production (D1371B Setup) | Utility(1) | N | 2025-03-11 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 555 | Bug fixes | SW Engineer(5) | N | 2025-03-12 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 11176 | ATE tests & tester preparation (Choke for ER caps (4081PQ2620)) | ATE(1) | N | 2025-03-12 | Reuven.Z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11210 | ATP initiated (Choke for ER caps (1061PQ2012) , magnetics proto batch) | Magnetic(1) | N | 2025-03-12 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11212 | Magnetics Proto batch assembly (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-03-12 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2982 | WET CHECK PRE-TEST SET UP. | 629_AE(2) | N | 2025-03-13 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3541 | HW Testing 25c (D1742A) | Utility(1) | N | 2025-03-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10002 | Transformers CT scan - Mid aging | Material(1) | N | 2025-03-13 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11075 | Magnetics batch -2 assembly (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-03-13 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11079 | Testing before potting (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-03-13 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11172 | Core spec (design approved) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-03-13 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11211 | Core spec (design approved) (Choke for ER caps (1061PQ2012) , magnetics proto batch) | Magnetic(1) | N | 2025-03-13 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2933 | PERFORM OP CHECK OF FUEL QUANTITY SYSTEM. | 629_AE(1) | N | 2025-03-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 568 | SW version freeze | SW Engineer(1) | N | 2025-03-14 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1101 | SW version freeze | SW Engineer(1) | N | 2025-03-14 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4387 | PCB automation testing (LV DIGITAL (D1738A)) | Utility(1) | N | 2025-03-14 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4390 | PCB automation testing (MV DIGITAL (D1739A)) | Utility(1) | N | 2025-03-14 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9473 | Mold Re-design (Batch -1) (LV Cabinet x2) | Mechanics(1) | N | 2025-03-14 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9498 | Mold Re-design (Batch -1) (MV Cabinet x2) | Mechanics(1) | N | 2025-03-14 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 569 | FTER ATP Cycle 2 | INT Engineer(5) | N | 2025-03-17 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1102 | GTER ATP Cycle 2 | INT Engineer(5) | N | 2025-03-17 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3542 | HW Testing 85\125 (D1742A) | Utility(1) | N | 2025-03-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9292 | Component Evaluation (D1420A) | QnR(1) | N | 2025-03-17 | Dana.h, Elianna.z | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11167 | 3D models preparation (Choke for ER caps (4081PQ2620)) | Mechanics(1) | N | 2025-03-17 | michael.ra | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11206 | 3D models preparation (Choke for ER caps (1061PQ2012)) | Mechanics(1) | N | 2025-03-17 | michael.ra | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2983 | WET CHECK | 629_ACM(3), 629_AE(1) | N | 2025-03-18 |  | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9104 | DR Elec. By Q&R (D1711B) | QnR(1) | N | 2025-03-18 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10008 | After-aging test | Material(1) | N | 2025-03-18 |  | NS | 45d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3543 | HW Testing -40 (D1742A) | Utility(1) | N | 2025-03-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9382 | ECO STP (40 Hilkar transformer Mpfor Batch -1) | Mechanics(1) | N | 2025-03-19 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 11215 | ATE tests & tester preparation (Choke for ER caps (1061PQ2012)) | ATE(1) | N | 2025-03-19 | Reuven.Z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11078 | Bobbin potting (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-03-20 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11168 | DFM Approved (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-03-20 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11174 | HW tests (Choke for ER caps (4081PQ2620)) | Utility(1) | N | 2025-03-20 | Reuven.Z, shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 11175 | Materials tests (Choke for ER caps (4081PQ2620)) | Material(1) | N | 2025-03-20 | Reuven.Z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11178 | Magnetics proto batch approved (final yield > 95%) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-03-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11183 | Core , coil , winding (EnE tooling) , bonding jig (mfg. solution) , other items/tools availability (batch -1 (up to 500 units)) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-03-20 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11207 | DFM Approved (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-03-20 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11213 | HW tests (Choke for ER caps (1061PQ2012)) | Utility(1) | N | 2025-03-20 | Reuven.Z, shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | adi.p | Majoris - 1 Mega INV_04-04_14-52 | 11214 | Materials tests (Choke for ER caps (1061PQ2012)) | Material(1) | N | 2025-03-20 | Reuven.Z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 11216 | QnR tests (Choke for ER caps (1061PQ2012)) | QnR(1) | N | 2025-03-20 | Dana.h, Elianna.z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11217 | Magnetics proto batch approved (final yield > 95%) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-03-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11222 | Core , coil , winding (EnE tooling) , bonding jig (mfg. solution) , other items/tools availability (batch -1 (up to 500 units)) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-03-20 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3544 | Tests result review (D1742A) | Utility(1) | N | 2025-03-21 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3051 | PERFORM LEAK CHECK OF OXYGEN SYSTEM | 629_ACM(1) | N | 2025-03-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 570 | Bug fixes | SW Engineer(5) | N | 2025-03-24 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1103 | Bug fixes | SW Engineer(5) | N | 2025-03-24 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R | IMS | 2022-12-15 |  | ACE Demo 240822 | 74 | Deliver FTER to System ATP | PM(1) | N | 2025-03-25 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-12-15 |  | ACE Demo 240822_RZ | 74 | Deliver FTER to System ATP | PM(1) | N | 2025-03-25 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-12-15 |  | ACE Demo 240822_RZ | 1106 | Deliver GTER to System ATP | PM(1) | N | 2025-03-25 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-12-15 |  | ACE Demo 240822 | 1106 | Deliver GTER to System ATP | PM(1) | N | 2025-03-25 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8975 | Tester Validation (D1744A Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9048 | Production (D1732A Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9114 | Tester Validation (D1711B Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9144 | Tester Validation (D1733A Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9184 | Tester Validation (D1737A Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9224 | Tester Validation (D1715A Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9302 | Production (D1420A Setup) | Utility(1) | N | 2025-03-25 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2881 | INSTALL TEMP. CONTROL COMPONENTS | 629_ACM(2), 629_AE(1) | N | 2025-03-26 |  | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2907 | INSTALL FLIGHT CONTROL SURFACES | 629_ACM(2) | N | 2025-03-26 |  | NS | 2d 4h |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2875 | INSTALL PITOT TUBES & MASTS | 629_AT(1) | N | 2025-03-26 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2943 | OP CHECK PNEUMATIC DE-ICE BOOTS | 629_ACM(1), 629_AE(1) | N | 2025-03-26 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2901 | INSTALL WIPER BLADE ASSEMBLIES | 629_ACM(2) | N | 2025-03-26 |  | NS | 0d 4h |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 556 | SW version freeze | SW Engineer(1) | N | 2025-03-26 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2928 | OP CHECK WINDSHIELD WIPERS | 629_ACM(1), 629_AE(1) | N | 2025-03-26 |  | NS | 0d 4h |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 557 | MC ATP Cycle 2 | INT Engineer(5) | N | 2025-03-27 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11074 | Testing after assembly (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-03-27 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11179 | allocate SEM PN (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-03-27 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11180 | allocate ECM PN (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-03-27 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11218 | allocate SEM PN (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-03-27 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11219 | allocate ECM PN (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-03-27 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11343 | Cell Standalone - SW tester version | SW(1) | N | 2025-03-28 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9383 | Transformer component approval for assembly (Batch -1) | Mechanics(1) | N | 2025-03-28 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 572 | FTER ATP 3 | INT Engineer(2) | N | 2025-03-31 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1104 | GTER ATP 3 | INT Engineer(2) | N | 2025-03-31 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 4470 | DR Elec. By Q&R (D1744A) | QnR(1) | N | 2025-03-31 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9134 | DR Elec. By Q&R (D1733A) | QnR(1) | N | 2025-03-31 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9174 | DR Elec. By Q&R (D1737A) | QnR(1) | N | 2025-03-31 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9214 | DR Elec. By Q&R (D1715A) | QnR(1) | N | 2025-03-31 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9255 | DR Elec. By Q&R (D1421B) | QnR(1) | N | 2025-03-31 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2874 | AIR STAIR DOOR INSTALL | 629_ACM(2) | N | 2025-04-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 573 | SW version release | SW Engineer(1) | N | 2025-04-01 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 1105 | SW version release | SW Engineer(1) | N | 2025-04-01 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9072 | Final DR Layout end (D1371B) | Utility(1) | N | 2025-04-01 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9068 | DR Elec. By Q&R (D1371B) | QnR(1) | N | 2025-04-01 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9106 | pre-placement (D1711B) | Mechanics(1) | N | 2025-04-01 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9138 | Final DR Layout end (D1733A) | Utility(1) | N | 2025-04-01 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9176 | pre-placement (D1737A) | Mechanics(1) | N | 2025-04-01 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9218 | Final DR Layout end (D1715A) | Utility(1) | N | 2025-04-01 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9257 | pre-placement (D1421B) | Mechanics(1) | N | 2025-04-01 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2022-12-15 |  | ACE Demo detiled tasks 240822_RZ | 74 | Deliver FTER to System ATP | PM(1) | N | 2025-04-02 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-12-15 |  | ACE Demo detiled tasks 240822_RZ | 1106 | Deliver GTER to System ATP | PM(1) | N | 2025-04-02 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2972 | OP TEST VACUUM SYSTEM (LEAK TEST PROCEDURE) | 629_AE(2) | N | 2025-04-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 558 | Bug fixes | SW Engineer(5) | N | 2025-04-03 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3281 | Magnetics batch -2 assembly (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-04-03 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11181 | Initiate and approve BOM 90% (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-04-03 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11220 | Initiate and approve BOM 90% (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-04-03 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2984 | CABIN PRESSURE TEST | 629_ACM(3) | N | 2025-04-07 |  | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11588 | Block 2 - Cell B2B development | SW(1) | N | 2025-04-07 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11590 | Mega Inverter open loop - block 3 development | SW(1) | N | 2025-04-07 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11185 | ATP finalized (Choke for ER caps (4081PQ2620) , magnetics batch -1) | Magnetic(1) | N | 2025-04-07 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9080 | BOM 100% (D1371B) | Utility(1) | N | 2025-04-08 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9078 | Tester Validation (D1371B Setup) | Utility(1) | N | 2025-04-08 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9084 | Design (D1371B) | ATE(1) | N | 2025-04-08 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9107 | Layout (D1711B) | Utility(1) | N | 2025-04-08 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9146 | BOM 100% (D1733A) | Utility(1) | N | 2025-04-08 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9151 | Design (D1733A) | ATE(1) | N | 2025-04-08 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9177 | Layout (D1737A) | Utility(1) | N | 2025-04-08 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9226 | BOM 100% (D1715A) | Utility(1) | N | 2025-04-08 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9231 | Design (D1715A) | ATE(1) | N | 2025-04-08 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9258 | Layout (D1421B) | Utility(1) | N | 2025-04-08 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11223 | ATP finalized (Choke for ER caps (1061PQ2012) , magnetics batch -1) | Magnetic(1) | N | 2025-04-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11186 | Test fixture readiness (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-04-09 | ATE | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 565 | MC ATP 3 | INT Engineer(5) | N | 2025-04-10 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 3285 | QnR tests (Batch -2 (30 Hilkar transformer)) | QnR(1) | N | 2025-04-10 | Dana.h, Elianna.z | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9964 | Design (Hipot) | ATE(1) | N | 2025-04-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9968 | Design (Connectivity) | ATE(1) | N | 2025-04-10 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11085 | Magnetics batch -2 approved (30 Hilkar transformer) | Magnetic(1) | N | 2025-04-10 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11187 | Magnetics batch -1 assembly (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-04-10 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11225 | Magnetics batch -1 assembly (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-04-10 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2885 | INSTALL AVIONICS EQUIPMENT L/H & R/H | 629_AT(1) | N | 2025-04-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2886 | INSTALL INSTRUMENT PANEL AND COMPONENTS | 629_AE(2) | N | 2025-04-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2888 | INSTALL PITOT STATIC COMPONENTS | 629_AE(1) | N | 2025-04-11 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3291 | Core , coil , winding (EnE tooling) , bonding jig (mfg. solution) , other items/tools availability (Batch -1 (50 Hilkar transformer)) | Magnetic(1) | N | 2025-04-11 |  | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 10229 | Transformer testing (10 units) #1 (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-04-11 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11106 | winding, Bobin (after potting) other items/tools availability (Batch -1 (50 Hilkar transformer)) | Magnetic(1) | N | 2025-04-11 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11108 | Core spec (design approved) (Batch -1 (50 Hilkar transformer)) | Magnetic(1) | N | 2025-04-11 | Reuven.Z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2889 | INSTALL MISC COMPONENTS IN AV BAYS | 629_AT(1) | N | 2025-04-15 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2893 | AVIONICS BAY SHELF INSTALLATION | 629_AE(1) | N | 2025-04-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9081 | MP pilot PCBAs (10 units) (D1371B) | Utility(1) | N | 2025-04-15 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 4509 | DR Elec. By Q&R (D1732A) | QnR(1) | N | 2025-04-15 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9082 | Mech kit (D1371B) | Utility(1) | N | 2025-04-15 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9148 | MP pilot PCBAs (10 units) (D1733A) | Jabil(1) | N | 2025-04-15 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9149 | Mech kit - Heat sinks (D1733A) | Utility(1) | N | 2025-04-15 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9228 | MP pilot PCBAs (50 units) (D1715A) | Jabil(1) | N | 2025-04-15 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9229 | Mech kit - Heat sinks (D1715A) | Utility(1) | N | 2025-04-15 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9474 | ECO STP (LV Cabinet x2) | Mechanics(1) | N | 2025-04-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9499 | ECO STP (MV Cabinet x2) | Mechanics(1) | N | 2025-04-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11224 | Test fixture readiness (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-04-16 | ATE | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 560 | SW version release | SW Engineer(1) | N | 2025-04-17 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 56 | Perform System ATP | INT Engineer(1.9), SW Engineer(2.9) | N | 2025-04-17 |  | NS | 26d |  |  |  |  | Guy Brill | 26d | Network | 1 | 0
R |  |  |  | ACE Demo 240822 | 56 | Perform System ATP | INT Engineer(1.9), SW Engineer(2.9) | N | 2025-04-17 |  | NS | 26d |  |  |  |  | Guy Brill | 26d | Network | 1 | 0
R | IMS | 2022-07-11 | gbrill | ACE Demo 240822 | 59 | Deliver MC to System ATP | PM(1) | N | 2025-04-17 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2022-07-11 | gbrill | ACE Demo 240822_RZ | 59 | Deliver MC to System ATP | PM(1) | N | 2025-04-17 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5089 | Mechanical approval for Mega INV Readiness | Mechanics(1) | N | 2025-04-17 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9475 | Component Approval For production (LV Cabinet x2) | Mechanics(1) | N | 2025-04-17 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 9500 | Component Approval For production | Mechanics(1) | N | 2025-04-17 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9969 | Production (Connectivity) | ATE(1) | N | 2025-04-17 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11077 | Bobbin testing after potting (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-04-17 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11188 | Magnetics Batch -1 approved (final yield > 97%) (Choke for ER caps (4081PQ2620)) | Magnetic(1) | N | 2025-04-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11226 | Magnetics Batch -1 approved (final yield > 97%) (Choke for ER caps (1061PQ2012)) | Magnetic(1) | N | 2025-04-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ofer.E | Majoris - 1 Mega INV_04-04_14-52 | 11317 | QnR FA Policy | QnR(1) | Y | 2025-04-17 | Dana.h, Elianna.z | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2941 | OP CHECK & RIG LANDING GEAR | 629_ACM(3), 629_AE(1) | N | 2025-04-18 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2948 | RIG & OP CHECK ELEV. CONTROL | 629_ACM(2), 629_AE(1) | N | 2025-04-18 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2951 | PITOT STATIC SYSTEM CHECK & TEST | 629_AE(1) | N | 2025-04-18 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R | IMS | 2022-07-11 | gbrill | ACE Demo detiled tasks 240822_RZ | 59 | Deliver MC to System ATP | PM(1) | N | 2025-04-18 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 539 | System ATP Cycle 1 | INT Engineer(5) | N | 2025-04-18 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11346 | Cell Standalone - block 1 compliance testing | SW(1) | N | 2025-04-18 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 10236 | Transformer testing (10 units) #2 (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-04-18 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4473 | Final DR Layout end (D1744A) | Utility(1) | N | 2025-04-21 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11552 | pre-placement (D1420A) | Utility(1) | N | 2025-04-21 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9049 | Tester Validation (D1732A Setup) | Utility(1) | N | 2025-04-22 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9303 | Tester Validation (D1420A Setup) | Utility(1) | N | 2025-04-22 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2950 | RIG & OP CHECK OF RUDDER & RUDDER TAB SYSTEM | 629_ACM(2), 629_AE(1) | N | 2025-04-23 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 3286 | HW batch -2 approved (30 Hilkar transformer) | Magnetic(1) | N | 2025-04-24 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9970 | Tester Validation (Connectivity) | ATE(1) | N | 2025-04-24 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3046 | RIG & OP CHECK AILERON TAB CONTROL SYS. | 629_ACM(2), 629_AE(1) | N | 2025-04-25 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 540 | Bug fixes | SW Engineer(5) | N | 2025-04-25 |  | NS | 10d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5209 | LV PCB's tests complete | Utility(1) | N | 2025-04-25 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10532 | Batch RnD - LV Unit (10 Cells assembly) | Mechanics(1) | N | 2025-04-25 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4492 | PCB's tests completed | Utility(1) | N | 2025-04-25 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5210 | MV PCB's tests complete | Utility(1) | N | 2025-04-25 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10531 | Batch RnD - MV Unit (10 Cells assembly) | Mechanics(1) | N | 2025-04-25 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2527 | HW Testing 25c (D1739A) | Utility(1) | N | 2025-04-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3691 | HW Testing 25c (D1738A) | Utility(1) | N | 2025-04-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 10235 | Transformer testing (10 units) #3 (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-04-25 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4478 | BOM 100% (D1744A) | Utility(1) | N | 2025-04-28 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4475 | Design (D1744A) | ATE(1) | N | 2025-04-28 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yaniv.s | Majoris - 1 Mega INV_04-04_14-52 | 9293 | DR Elec. By Q&R (D1420A) | QnR(1) | N | 2025-04-28 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9296 | Layout (D1420A) | Utility(1) | N | 2025-04-28 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3045 | RIG & OP CHECK AILERON | 629_ACM(2), 629_AE(1) | N | 2025-04-29 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3047 | RIG & OP CHECK FLAPS | 629_ACM(2), 629_AE(1) | N | 2025-04-29 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3048 | RIG & OP CHECK ANTI-SERVO TAB SYS | 629_ACM(2), 629_AE(1) | N | 2025-04-29 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2526 | HW Testing 85\125 (D1739A) | Utility(1) | N | 2025-04-29 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3692 | HW Testing 85\125 (D1738A) | Utility(1) | N | 2025-04-29 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3294 | INTERIOR BUILDUP AFT | 629_ACM(1), 629_AE(1) | N | 2025-05-01 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2890 | RADIO ALTIMETER TEMPORARY INSTALL | 629_AT(1) | N | 2025-05-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2891 | INSTALL CONTROL SURFACE LIGHTS | 629_AE(1) | N | 2025-05-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2898 | INSTALL CENTER SECTION LEADING EDGES | 629_ACM(2) | N | 2025-05-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2910 | OP TEST EXTERIOR LIGHTS | 629_AE(1) | N | 2025-05-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3312 | INTERIOR BUILDUP CABIN | 629_ACM(2) | N | 2025-05-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2525 | HW Testing -40 (D1739A) | Utility(1) | N | 2025-05-01 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3693 | HW Testing -40 (D1738A) | Utility(1) | N | 2025-05-01 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3082 | Received Samples (Transformer) | Certification(1) | N | 2025-05-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3087 | Received units from Batch -1 (Transformer) | Certification(1) | N | 2025-05-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8409 | Received Data sheet and labels from product (Transformer) | Certification(1) | N | 2025-05-02 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 8564 | Sent transformer unit for Certification (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-05-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 9446 | Sent transformer unit for Integration (Batch -2 (30 Hilkar transformer)) | Magnetic(1) | N | 2025-05-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8976 | MP pilot PCBAs (10 units) (D1744A) | Jabil(1) | N | 2025-05-05 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11591 | Mega Inverter open loop - block 3 development | SW(1) | N | 2025-05-05 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2019 | Tests result review (D1739A) | Utility(1) | N | 2025-05-05 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3083 | Received Schematic and Layout from HW & Data sheet for components (Transformer) | Certification(1) | N | 2025-05-05 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3694 | Tests result review (D1738A) | Utility(1) | N | 2025-05-05 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4479 | Mech kit (D1744A) | Utility(1) | N | 2025-05-05 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-02-08 | PS | T44_February_2019 | 2981 | IMS-Release to H0=Final Assembly | Hold(1) | N | 2025-05-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3053 | INSTALL DOORS AND PANELS | 629_ACM(2) | N | 2025-05-06 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3037 | OP CHECK STALL WARNING SYSTEM | 629_AE(1) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3038 | OP CHECK FIRE DETECTION SYSTEM. | 629_AE(1) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | T44_February_2019 | 3039 | PERFORM OP CHECKS OF ENVIRONMENTAL SYSTEM | 629_AE(2) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3040 | OP CHECK ANTI-ICE & DEICE SYSTEMS. | 629_AE(2) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3052 | INSTALL WING PANELS AND COWLINGS | 629_ACM(2) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3296 | RADIO ALTIMETER INSTALLS | 629_AT(1) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3311 | AHRS INSTALL | 629_AT(1) | N | 2025-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3433 | OP CHECK TRANSPONDER & ALT Decoder | 629_AT(1) | N | 2025-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9965 | Production (Hipot) | ATE(1) | N | 2025-05-08 |  | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3035 | OP CHECK AVIONCS POWER | 629_AT(1) | N | 2025-05-09 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3036 | OP CHECK VHF/UHF COMMS PILOT/COPILOT STA. | 629_AT(1) | N | 2025-05-09 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2990 | INSTALL WING PANELS | 629_ACM(2) | N | 2025-05-09 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 541 | SW version freeze | SW Engineer(1) | N | 2025-05-09 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3042 | OP CHECK LOCALIZER (LOC) & GLIDESLOPE (GS) | 629_AT(1) | N | 2025-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 542 | System ATP Cycle 2 | INT Engineer(5) | N | 2025-05-12 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3041 | OP TEST ICS | 629_AT(2) | N | 2025-05-13 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9085 | Production (D1371B) | ATE(1) | N | 2025-05-13 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9152 | Production (D1733A) | ATE(1) | N | 2025-05-13 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9232 | Production (D1715A) | ATE(1) | N | 2025-05-13 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2894 | FLOORBOARD FOD AND SECURITIES | 629_ACM(2) | N | 2025-05-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3031 | OP CHECK FLIGHT MANAGEMENT SYS (FMS) | 629_AT(1) | N | 2025-05-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3033 | PERFORM OP TEST OF ELT | 629_AE(2) | N | 2025-05-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3034 | OP CHECK VHF OMNIDIRECTIONAL RANGE (VOR) 1 & 2 | 629_AT(1) | N | 2025-05-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3044 | OP CHECK TACAN & DISTANCE MEASURING EQUIP | 629_AT(1) | N | 2025-05-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3054 | OP CHECK (FGS) - FLIGHT DIRECTOR & AUTO PILOT | 629_AE(2) | N | 2025-05-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11351 | Cell B2B - block 2 compliance | SW(1) | N | 2025-05-16 |  | NS | 50d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11440 | Block 1 - Cell Standalone version | SW(1) | N | 2025-05-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  | gbrill | ACE Demo 2-Tier | 566 | Deliver MC |  | N | 2025-05-16 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2986 | INTERIOR BUILDUP Cockpit | 629_ACM(3) | N | 2025-05-19 |  | NS | 4d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2896 | INSTALL COCKPIT FURNISHINGS | 629_ACM(2) | N | 2025-05-19 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2909 | OP TEST INTERIOR LIGHTS | 629_AE(1) | N | 2025-05-19 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 3032 | OP CHECK RADIO ALTIMETER | 629_AT(1) | N | 2025-05-19 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Assy_44 | T44_February_2019 | 2977 | INSTALL TAIL CONE | 629_ACM(2) | N | 2025-05-19 |  | NS | 1d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 543 | Bug fixes | SW Engineer(5) | N | 2025-05-19 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3090 | Open project (by Certification vs. labs) (Transformer) | Certification(1) | N | 2025-05-19 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9108 | Final DR Layout (D1711B) | Utility(1) | N | 2025-05-20 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Adi.P | Majoris - 1 Mega INV_04-04_14-52 | 10001 | Transformers CT scan - after aging | Material(1) | N | 2025-05-20 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11490 | pre-placement (D1976A) | Utility(1) | N | 2025-05-20 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3581 | Integrated Systems Check | 629_AE(2) | N | 2025-05-23 |  | NS | 4d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5203 | Connectivity&Hipot&PD (LV Unit) | Utility(1) | N | 2025-05-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5204 | Connectivity&Hipot&PD(MV Unit) | Utility(1) | N | 2025-05-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11109 | Hot crimp terminal (Batch -1 (50 Hilkar transformer)) | Magnetic(1) | N | 2025-05-23 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11113 | Core assembly (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-05-23 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11319 | Functionality and calibration (LV Unit) | Utility(1) | N | 2025-05-27 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11331 | Connectivity&Hipot&PD (LV Unit) | Utility(1) | N | 2025-05-27 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11318 | Functionality and calibration (MV Unit) | Utility(1) | N | 2025-05-27 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9116 | BOM 100% (D1711B) | Utility(1) | N | 2025-05-27 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9908 | Layout (D1976A) | Utility(1) | N | 2025-05-27 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 574 | Perform System Customer ATP | INT Engineer(5) | N | 2025-05-28 |  | NS | 5d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 545 | System Customer ATP | INT Engineer(5), SW Engineer(0.2) | N | 2025-05-28 |  | NS | 5d |  |  |  |  | Guy Brill | 5d | Network | 1 | 0
R |  |  |  | ACE Demo 240822_RZ | 545 | System Customer ATP | INT Engineer(5), SW Engineer(0.2) | N | 2025-05-28 |  | NS | 5d |  |  |  |  | Guy Brill | 5d | Network | 1 | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 3319 | Ground Check Prior to Final Walk Around | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-05-29 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11332 | Functionality and calibration (LV Unit) | Utility(1) | N | 2025-05-29 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11110 | Testing before potting (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-05-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11114 | Magnetics batch -1 assembly (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-05-30 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Assy_44 | T44_February_2019 | 2976 | Final Walk Around | 629_AE(1), 629_AT(1) | N | 2025-06-02 |  | NS | 3d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3081 | PDR + Construction review (Transformer level) (after RnD provides info) (Transformer) | Certification(1) | N | 2025-06-02 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4476 | Production (D1744A) | ATE(1) | N | 2025-06-02 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9117 | MP pilot PCBAs (100 units) (D1711B) | Jabil(1) | N | 2025-06-03 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9178 | Final DR Layout end (D1737A) | Utility(1) | N | 2025-06-03 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9259 | Final DR Layout end (D1421B) | Utility(1) | N | 2025-06-03 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10053 | Mech kit (D1711B) | Utility(1) | N | 2025-06-03 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 544 | SW version release | SW Engineer(1) | N | 2025-06-04 |  | NS | 1d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822_RZ | 553 | System packaging and delivery | PM(1) | N | 2025-06-04 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  |  | ACE Demo 240822 | 553 | System packaging and delivery | PM(1) | N | 2025-06-04 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
R |  |  | PS | T44_February_2019 | 2997 | Assembly Pipeline Duration | Hold(1) | N | 2025-06-05 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | ACE Demo detiled tasks 240822_RZ | 553 | System packaging and delivery | PM(1) | N | 2025-06-05 |  | NS | 3d |  |  |  |  | Guy Brill |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11111 | Bobbin potting (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-06-06 |  | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | ACE Demo 240822 | 593 | Project End |  | N | 2025-06-06 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | PE |  |  | ACE Demo 240822_RZ | 593 | Project End |  | N | 2025-06-06 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R | IMS | 2023-03-14 | PS | T44_February_2019 | 3288 | IMS-Release to U0=Final Paint | Hold(1) | N | 2025-06-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | Painter AC | T44_February_2019 | 3289 | Final Paint | Painters_A/C(4) | N | 2025-06-09 |  | NS | 14d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9297 | Final DR Layout end (D1420A) | Utility(1) | N | 2025-06-09 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | ACE Demo detiled tasks 240822_RZ | 593 | Project End |  | N | 2025-06-09 |  | NS | 0d |  |  |  |  | Guy Brill |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9012 | Bring up testing (D1371B) | Utility(1) | N | 2025-06-10 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8983 | Bring up testing (D1733A) | Utility(1) | N | 2025-06-10 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9000 | Bring up testing (D1715A) | Utility(1) | N | 2025-06-10 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9086 | Tester Validation (D1371B) | ATE(1) | N | 2025-06-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9089 | HW Testing 25c (D1371B) | Utility(1) | N | 2025-06-10 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9153 | Tester Validation (D1733A) | ATE(1) | N | 2025-06-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9156 | HW Testing 25c (D1733A) | Utility(1) | N | 2025-06-10 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9186 | BOM 100% (D1737A) | Utility(1) | N | 2025-06-10 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9191 | Design (D1737A) | ATE(1) | N | 2025-06-10 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9233 | Tester Validation (D1715A) | ATE(1) | N | 2025-06-10 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9236 | HW Testing 25c (D1715A) | Utility(1) | N | 2025-06-10 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9267 | BOM 100% (D1421B) | Utility(1) | N | 2025-06-10 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9272 | Design (D1421B) | ATE(1) | N | 2025-06-10 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9090 | HW Testing 85\125 (D1371B) | Utility(1) | N | 2025-06-12 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11115 | Testing after assembly (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-06-13 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3089 | Reply to Findigs (Transformer) | Certification(1) | N | 2025-06-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9091 | HW Testing -40 (D1371B) | Utility(1) | N | 2025-06-16 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9305 | BOM 100% (D1420A) | Utility(1) | N | 2025-06-16 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9308 | Design (D1420A) | ATE(1) | N | 2025-06-16 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9157 | HW Testing 85\125 (D1733A) | Utility(1) | N | 2025-06-17 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9188 | MP pilot PCBAs (50 units) (D1737A) | Jabil(1) | N | 2025-06-17 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9189 | Mech kit - Heat sinks (D1737A) | Utility(1) | N | 2025-06-17 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9237 | HW Testing 85\125 (D1715A) | Utility(1) | N | 2025-06-17 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9269 | MP pilot PCBAs (50 units) (D1421B) | Jabil(1) | N | 2025-06-17 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9270 | Mech kit - Heat sinks (D1421B) | Utility(1) | N | 2025-06-17 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9092 | Tests result review (D1371B) | Utility(1) | N | 2025-06-18 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11116 | Magnetics batch -1 assembly (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-06-20 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3088 | Get test plan package (Transformer) | Certification(1) | N | 2025-06-23 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8404 | Insulation system CR (Transformer) | Certification(1) | N | 2025-06-23 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9306 | MP pilot PCBAs (25 units) (D1420A) | Jabil(1) | N | 2025-06-23 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10246 | Mech kit - Heat sinks (D1420A) | Utility(1) | N | 2025-06-23 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11329 | Connectivity&Hipot&PD(MV Unit) | Utility(1) | N | 2025-06-24 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9158 | HW Testing -40 (D1733A) | Utility(1) | N | 2025-06-24 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9238 | HW Testing -40 (D1715A) | Utility(1) | N | 2025-06-24 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11330 | Functionality and calibration (MV Unit) | Utility(1) | N | 2025-06-26 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2023-04-03 | PS | T44_February_2019 | 1948 | IMS-Release to S0=Ground Check | Hold(1) | N | 2025-06-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Ground_Check | T44_February_2019 | 3337 | PREP FOR W/B AND FINAL ARM | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-06-27 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11117 | Magnetics batch -1 approved (50 Hilkar transformer) | Magnetic(1) | N | 2025-06-27 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8906 | Bring up testing (D1744A) | Utility(1) | N | 2025-06-30 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11118 | Transformer testing (10 units) #1 (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-06-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3338 | Weight and Balance | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9013 | Automation testing (D1371B) | Utility(1) | N | 2025-07-01 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8984 | Automation testing (D1733A) | Utility(1) | N | 2025-07-01 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9001 | Automation testing (D1715A) | Utility(1) | N | 2025-07-01 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9159 | Tests result review (D1733A) | Utility(1) | N | 2025-07-01 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9239 | Tests result review (D1715A) | Utility(1) | N | 2025-07-01 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8405 | Insulation system safety test (Transformer) | Certification(1) | N | 2025-07-02 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3339 | DEPRES PREP FOR ENGINE RUNS | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9966 | Tester Validation (Hipot) | ATE(1) | N | 2025-07-03 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9014 | Testing results approval (D1371B) | Utility(1) | N | 2025-07-04 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8985 | Testing results approval (D1733A) | Utility(1) | N | 2025-07-04 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9002 | Testing results approval (D1715A) | Utility(1) | N | 2025-07-04 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3340 | ENGINE WASH | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-07 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Ground_Check | T44_February_2019 | 3345 | 02 CHECK | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-07 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8568 | temperature tests | Certification(1) | N | 2025-07-07 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11119 | Transformer testing (10 units) #2 (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-07-07 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11354 | Block 3 – VMU integration | SW(1) | N | 2025-07-08 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9672 | AUX AC2DC readiness for Integration (D1715A) | Utility(1) | N | 2025-07-08 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9673 | VMU main board readiness for Integration (D1371B) | Utility(1) | N | 2025-07-08 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9675 | AUX buck stage readiness for Integration (D1733A) | Utility(1) | N | 2025-07-08 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9909 | Final DR Layout end (D1976A) | Utility(1) | N | 2025-07-08 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11486 | pre-placement (D1732A) | Utility(1) | N | 2025-07-08 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3341 | ENGINE RUNS | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-09 |  | NS | 8d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8571 | Insulation aging test (Transformer) | Certification(1) | N | 2025-07-11 |  | NS | 60d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11120 | Transformer testing (10 units) #3 (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-07-14 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4511 | Layout (D1732A) | Utility(1) | N | 2025-07-15 | shani.a | NS | 30d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9192 | Production (D1737A) | ATE(1) | N | 2025-07-15 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9273 | Production (D1421B) | ATE(1) | N | 2025-07-15 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9917 | BOM 100% (D1976A) | Utility(1) | N | 2025-07-15 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9921 | Design (D1976A) | ATE(1) | N | 2025-07-15 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8567 | BIL tests | Certification(1) | N | 2025-07-16 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3342 | PERFORM FLIGHT CONTROLS AND SYSTEMS CHECKS | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-21 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | 629 Ground_Check | T44_February_2019 | 3347 | PERFORM AVIONICS SYSTEMS CHECKS | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-21 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8905 | Automation testing (D1744A) | Utility(1) | N | 2025-07-21 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8566 | Power frequence tests | Certification(1) | N | 2025-07-21 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9309 | Production (D1420A) | ATE(1) | N | 2025-07-21 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11121 | Transformer testing (10 units) #4 (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-07-21 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9918 | MP pilot PCBAs (10 units) (D1976A) | Utility(1) | N | 2025-07-22 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9919 | Mech kit (D1976A) | Utility(1) | N | 2025-07-22 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3346 | PERFORM ELECTRICAL SYSTEMS CHECKS | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-23 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8904 | Testing results approval (D1744A) | Utility(1) | N | 2025-07-24 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8569 | abnormal tests | Certification(1) | N | 2025-07-24 |  | NS | 4d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3343 | COMPASS SWING | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-25 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11404 | Mega Inverter open loop - block 3 compliance | SW(1) | N | 2025-07-25 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11442 | Block 2 - Cell B2B tester version | SW(1) | N | 2025-07-25 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11353 | Block 3 - MCU MP Tester Version | SW(1) | N | 2025-07-28 |  | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 4482 | SW Basic Version (D1744A) | SW(1) | N | 2025-07-28 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9671 | MCU main board Module readiness for Integration (D1744A) | Utility(1) | N | 2025-07-28 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 3344 | WALK AROUND PRIOR TO FIRST FLIGHT | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-29 |  | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9016 | Bring up testing (D1711B) | Utility(1) | N | 2025-07-29 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10464 | Tests result review (D1711B) | Utility(1) | N | 2025-07-29 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8400 | Final Safety test report (Transformer) | Certification(1) | N | 2025-07-30 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Hub_Scheduler | T44_February_2019 | 1950 | Aircraft FCF | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-07-31 | 629 Ground_Check | NS | 3d |  |  |  |  | Concerto Admin |  |  |  | 1
R | IMS | 2023-05-05 | PS | T44_February_2019 | 1955 | IMS-Release to T0=Flight Test | Hold(1) | N | 2025-07-31 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11112 | Bobbin testing after potting (Batch -1 (50 Hilkar transformer) | Magnetic(1) | N | 2025-08-01 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Ground_Check | T44_February_2019 | 2559 | Discrepancies | 629_ACM(1), 629_AE(1), 629_ASI(2) | N | 2025-08-05 |  | NS | 3d |  |  |  |  | Concerto Admin |  |  |  | 0
R | CMS | 2024-01-23 |  | Majoris - 1 Mega INV_04-04_14-52 | 11684 | Batch RnD - TLA (10 Cells assembly) |  | N | 2025-08-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | IMS | 2024-01-23 | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10533 | Batch RnD - TLA (10 Cells assembly) | Mechanics(1) | N | 2025-08-07 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10534 | Batch RnD TLA (#1-3 Cells assembly) | Mechanics(1) | N | 2025-08-07 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | 629 Hub_Scheduler | T44_February_2019 | 1951 | RFI | Hold(1) | N | 2025-08-08 | 629 Ground_Check, PS | NS | 2d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Reuven.Z | Majoris - 1 Mega INV_04-04_14-52 | 11088 | HW batch -1 approved (50 Hilkar transformer) | Magnetic(1) | N | 2025-08-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9930 | MCU system unit assembly ASLVS-MC-A1 | Utility(1) | N | 2025-08-11 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | T44_February_2019 | 3497 | Project End |  | N | 2025-08-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8979 | Bring up testing (D1737A) | Utility(1) | N | 2025-08-12 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9008 | Bring up testing (D1421B) | Utility(1) | N | 2025-08-12 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9193 | Tester Validation (D1737A) | ATE(1) | N | 2025-08-12 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9196 | HW Testing 25c (D1737A) | Utility(1) | N | 2025-08-12 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9274 | Tester Validation (D1421B) | ATE(1) | N | 2025-08-12 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9277 | HW Testing 25c (D1421B) | Utility(1) | N | 2025-08-12 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4487 | HW Testing 25c (D1744A) | Utility(1) | N | 2025-08-18 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9004 | Bring up testing (D1720A) | Utility(1) | N | 2025-08-18 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9310 | Test Validation (D1420A) | ATE(1) | N | 2025-08-18 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9313 | HW Testing 25c (D1420A) | Utility(1) | N | 2025-08-18 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9017 | Automation testing (D1711B) | Utility(1) | N | 2025-08-19 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9197 | HW Testing 85\125 (D1737A) | Utility(1) | N | 2025-08-19 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9278 | HW Testing 85\125 (D1421B) | Utility(1) | N | 2025-08-19 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9922 | Production (D1976A) | ATE(1) | N | 2025-08-19 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4488 | HW Testing 85\125 (D1744A) | Utility(1) | N | 2025-08-20 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9314 | HW Testing 85\125 (D1420A) | Utility(1) | N | 2025-08-20 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11901 | Batch RnD TLA (#4-10 Cells assembly) | Mechanics(1) | N | 2025-08-21 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5206 | Connectivity&Hipot&PD (#1-3 Cells) | Utility(1) | N | 2025-08-21 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3932 | Tester Validation FT (B2B) | ATE(1) | N | 2025-08-21 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4489 | HW Testing -40 (D1744A) | Utility(1) | N | 2025-08-22 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9018 | Testing results approval (D1711B) | Utility(1) | N | 2025-08-22 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9315 | HW Testing -40 (D1420A) | Utility(1) | N | 2025-08-22 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11322 | standalone low voltage (50V) (#1-3 Cells) | Utility(1) | N | 2025-08-25 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4490 | Tests result review (D1744A) | Utility(1) | N | 2025-08-26 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4512 | Final DR Layout end (D1732A) | Utility(1) | N | 2025-08-26 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9198 | HW Testing -40 (D1737A) | Utility(1) | N | 2025-08-26 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9279 | HW Testing -40 (D1421B) | Utility(1) | N | 2025-08-26 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9316 | Tests result review (D1420A) | Utility(1) | N | 2025-08-26 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9676 | VMU resistor tower readiness for Integration (D1711B) | Utility(1) | N | 2025-08-26 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4514 | Design (D1732A) | ATE(1) | N | 2025-09-02 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8980 | Automation testing (D1737A) | Utility(1) | N | 2025-09-02 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9009 | Automation testing (D1421B) | Utility(1) | N | 2025-09-02 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9051 | BOM 100% (D1732A) | Utility(1) | N | 2025-09-02 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9199 | Tests result review (D1737A) | Utility(1) | N | 2025-09-02 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11333 | Connectivity&Hipot&PD (#4-10 Cells) | Utility(1) | N | 2025-09-04 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 11569 | Mech vibration tests (Batch RnD type test) | Mechanics(1) | N | 2025-09-04 | michael.ra | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10046 | Batch revision after Batch RnD (optional) | Utility(1) | N | 2025-09-04 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5192 | Mech Readiness (Batch -2) | Mechanics(1) | N | 2025-09-04 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8981 | Testing results approval (D1737A) | Utility(1) | N | 2025-09-05 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9010 | Testing results approval (D1421B) | Utility(1) | N | 2025-09-05 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11335 | standalone low voltage (50V) (#4-10 Cells) | Utility(1) | N | 2025-09-08 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11338 | Back 2 Back MV (2,400V - 110 Lab) (#4-10 Cells) | Utility(1) | N | 2025-09-08 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11321 | standalone low voltage (1,000V - 105 Lab) (#1-3 Cells) | Utility(1) | N | 2025-09-08 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9005 | Automation testing (D1720A) | Utility(1) | N | 2025-09-08 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8761 | Crowbar main board readiness for Integration (D1421B) | Utility(1) | N | 2025-09-09 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9042 | Mech kit (D1732A) | Utility(1) | N | 2025-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9052 | MP pilot PCBAs (10 units) (D1732A) | Jabil(1) | N | 2025-09-09 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9280 | Tests result review (D1421B) | Utility(1) | N | 2025-09-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9674 | AUX DC2DC readiness for Integration (D1737A) | Utility(1) | N | 2025-09-09 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9886 | VMU system unit assembly ASMVS-VM-B1 | Utility(1) | N | 2025-09-09 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9006 | Testing results approval (D1720A) | Utility(1) | N | 2025-09-11 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | mmassa | DP273 | 28 | Finish Turn, Drill, & Inspect | OD_Warren(1) | N | 2025-09-11 |  | NS | 287d 6.4h |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8764 | DC Chanel readiness for Integration (D1420A) | Utility(1) | N | 2025-09-15 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 9923 | Tester Validation (D1976A) | ATE(1) | N | 2025-09-16 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9926 | HW Testing 25c (D1976A) | Utility(1) | N | 2025-09-16 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10042 | Bring up testing (D1976A) | Utility(1) | N | 2025-09-16 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9927 | HW Testing 85\125 (D1976A) | Utility(1) | N | 2025-09-18 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11376 | Mega Inverter close loop - block 4 compliance | SW(1) | N | 2025-09-22 |  | NS | 80d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11443 | Block 3 - Mega INV open loop version | SW(1) | N | 2025-09-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11323 | standalone MV (2,400V - 110 Lab) (full power #1-3 Cells) | Utility(1) | N | 2025-09-22 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4477 | Tester Validation (D1744A) | ATE(1) | N | 2025-09-22 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9928 | HW Testing -40 (D1976A) | Utility(1) | N | 2025-09-22 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9885 | AUX system unit assembly - ASLVS-FP-A1 | Utility(1) | N | 2025-09-23 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9931 | Crowbar system unit assembly ASLVS-CB-A1 | Utility(1) | N | 2025-09-23 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9929 | Tests result review (D1976A) | Utility(1) | N | 2025-09-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10541 | PO Preperation Process + Sending (MV Unit Enclosure base) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10573 | PO Preparation Process + Sending (MV Unit Enclosure cover) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10614 | PO Preparation Process + Sending (MV Unit Busbars) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10623 | PO Preparation Process + Sending (MV Unit Air duct) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10632 | PO Preparation Process + Sending (MV Unit Heat sink) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10725 | PO Preparation Process + Sending (LV Unit Heat sink) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10734 | PO Preparation Process + Sending (LV Unit Enclosure cover) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10743 | PO Preparation Process + Sending (LV Unit Enclosure base) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10753 | PO Preparation Process + Sending (LV Unit Busbars) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10859 | PO Preparation Process + Sending (Enclosure Separators) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10868 | PO Preparation Process + Sending (Enclosure Back plate) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10878 | PO Preparation Process + Sending (Enclosure Fan) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10888 | PO Preparation Process + Sending (Enclosure Front plate) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10898 | PO Preparation Process + Sending (Enclosure Planum) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10908 | PO Preparation Process + Sending (Enclosure Base plate) | Mechanics(1) | N | 2025-09-25 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10244 | DC Chanel system unit assembly ASLVS-PLC-A1 | Utility(1) | N | 2025-09-29 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10542 | Sending PO (MV Unit Enclosure base) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10574 | Sending PO (MV Unit Enclosure cover) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10615 | Sending PO (MV Unit Busbars) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10624 | Sending PO (MV Unit Air duct) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10633 | Sending PO (MV Unit Heat sink) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10726 | Sending PO (LV Unit Heat sink) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10735 | Sending PO (LV Unit Enclosure cover) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10744 | Sending PO (LV Unit Enclosure base) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10754 | Sending PO (LV Unit Busbars) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10860 | Sending PO (Enclosure Separators) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10869 | Sending PO (Enclosure Back plate) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10879 | Sending PO (Enclosure Fan) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10889 | Sending PO (Enclosure Front plate) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10899 | Sending PO (Enclosure Planum) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10909 | Sending PO (Enclosure Base plate) | Mechanics(1) | N | 2025-10-02 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10543 | PO Approved & Send to Production (MV Unit Enclosure base) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10575 | PO Approved & Send to Production (MV Unit Enclosure cover) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10616 | PO Approved & Send to Production (MV Unit Busbars) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10625 | PO Approved & Send to Production (MV Unit Air duct) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10634 | PO Approved & Send to Production (MV Unit Heat sink) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10727 | PO Approved & Send to Production (LV Unit Heat sink) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10736 | PO Approved & Send to Production (LV Unit Enclosure cover) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10745 | PO Approved & Send to Production (LV Unit Enclosure base) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10755 | PO Approved & Send to Production (LV Unit Busbars) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10861 | PO Approved & Send to Production (Enclosure Separators) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10870 | PO Approved & Send to Production (Enclosure Back plate) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10880 | PO Approved & Send to Production (Enclosure Fan) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10890 | PO Approved & Send to Production (Enclosure Front plate) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10900 | PO Approved & Send to Production (Enclosure Planum) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10910 | PO Approved & Send to Production (Enclosure Base plate) | Mechanics(1) | N | 2025-10-03 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8406 | Final Insulation System Certificate (Transformer) | Certification(1) | N | 2025-10-03 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11336 | standalone low voltage (1,000V - 105 Lab) (#4-10 Cells) | Utility(1) | N | 2025-10-06 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11324 | Back 2 Back MV (2,400V - 110 Lab) (#1-3 Cells) | Utility(1) | N | 2025-10-06 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4515 | Production (D1732A) | ATE(1) | N | 2025-10-07 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9887 | SMU CAN Terminal board readiness for Integration (D1976A) | Utility(1) | N | 2025-10-07 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10043 | Automation testing (D1976A) | Utility(1) | N | 2025-10-07 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10047 | Mech assembly wiring approval for power integration | Utility(1) | N | 2025-10-07 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8408 | preleminary construction review (Cell) | Certification(1) | N | 2025-10-10 |  | NS | 7d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 8572 | Transformer certification complete | Certification(1) | N | 2025-10-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 10044 | Testing results approval (D1976A) | Utility(1) | N | 2025-10-10 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10544 | Mold & Samples Production & shipment (MV Unit Enclosure base) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10576 | Mold & Samples Production & shipment (MV Unit Enclosure cover) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10617 | Mold & Samples Production & shipment (MV Unit Busbars) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10626 | Mold & Samples Production & shipment (MV Unit Air duct) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10635 | Mold & Samples Production & shipment (MV Unit Heat sink) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10728 | Mold & Samples Production & shipment (LV Unit Heat sink) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10737 | Mold & Samples Production & shipment (LV Unit Enclosure cover) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10746 | Mold & Samples Production & shipment (LV Unit Enclosure base) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10756 | Mold & Samples Production & shipment (LV Unit Busbars) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10862 | Mold & Samples Production & shipment (Enclosure Separators) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10871 | Mold & Samples Production & shipment (Enclosure Back plate) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10881 | Mold & Samples Production & shipment (Enclosure Fan) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10891 | Mold & Samples Production & shipment (Enclosure Front plate) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10901 | Mold & Samples Production & shipment (Enclosure Planum) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10911 | Mold & Samples Production & shipment (Enclosure Base plate) | Jabil(1) | N | 2025-10-17 | michael.ra | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 3305 | preleminary construction review complete | Certification(1) | N | 2025-10-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11337 | standalone MV (2,400V - 110 Lab) (full power #4-10 Cells) | Utility(1) | N | 2025-11-03 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 4516 | Tester Validation (D1732A) | ATE(1) | N | 2025-11-04 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4526 | HW Testing 25c (D1732A) | Utility(1) | N | 2025-11-04 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8987 | Bring up testing (D1732A) | Utility(1) | N | 2025-11-04 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4527 | HW Testing 85\125 (D1732A) | Utility(1) | N | 2025-11-06 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4528 | HW Testing -40 (D1732A) | Utility(1) | N | 2025-11-10 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4529 | Tests result review (D1732A) | Utility(1) | N | 2025-11-12 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8988 | Automation testing (D1732A) | Utility(1) | N | 2025-11-25 | shani.a | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8989 | Testing results approval (D1732A) | Utility(1) | N | 2025-11-28 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11570 | Cell EMI tests (Batch RnD) | Utility(1) | N | 2025-12-01 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11566 | Cell thermal testing (Batch RnD) | Utility(1) | N | 2025-12-01 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8745 | INV Level HW Tests completed | Utility(1) | N | 2025-12-02 | shani.a | NS | 50d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8757 | SMU main board readiness for Integration (D1732A) | Utility(1) | N | 2025-12-02 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11360 | SIU boards Tester | SW(1) | N | 2025-12-02 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10545 | Mold re-design (MV Unit Enclosure base) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10577 | Mold Re-design (MV Unit Enclosure cover) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10618 | Mold Re-design (MV Unit Busbars) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10627 | Mold Re-design (MV Unit Air duct) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10636 | Mold Re-design (MV Unit Heat sink) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10729 | Mold Re-design (LV Unit Heat sink) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10738 | Mold Re-design (LV Unit Enclosure cover) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10747 | Mold Re-design (LV Unit Enclosure base) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10757 | Mold Re-design (LV Unit Busbars) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10863 | Mold Re-design (Enclosure Separators) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10872 | Mold Re-design (Enclosure Back plate) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10882 | Mold Re-design (Enclosure Fan) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10892 | Mold Re-design (Enclosure Front plate) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10902 | Mold Re-design (Enclosure Planum) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10912 | Mold Re-design (Enclosure Base plate) | Mechanics(1) | N | 2025-12-12 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9888 | SMU system unit assembly ASLVS-SU-A1 | Utility(1) | N | 2025-12-16 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10546 | ECO STP (MV Unit Enclosure base) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10578 | ECO STP (MV Unit Enclosure cover) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10619 | ECO STP (MV Unit Busbars) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10628 | ECO STP (MV Unit Air duct) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10637 | ECO STP (MV Unit Heat sink) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10730 | ECO STP (LV Unit Heat sink) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10739 | ECO STP (LV Unit Enclosure cover) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10748 | ECO STP (LV Unit Enclosure base) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10758 | ECO STP (LV Unit Busbars) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10864 | ECO STP (Enclosure Separators) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10873 | ECO STP (Enclosure Back plate) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10883 | ECO STP (Enclosure Fan) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10893 | ECO STP (Enclosure Front plate) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10903 | ECO STP (Enclosure Planum) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10913 | ECO STP (Enclosure Base plate) | Mechanics(1) | N | 2025-12-26 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10563 | Component approval for Batch -2 (MV Unit Enclosure base) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10579 | Component approval for Batch -2 (MV Unit Enclosure cover) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10620 | Component approval for Batch -2 (MV Unit Busbars) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10629 | Component approval for Batch -2 (MV Unit Air duct) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10638 | Component approval for Batch -2 (MV Unit Heat sink) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10731 | Component approval for Batch -2 (LV Unit Heat sink) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10740 | Component approval for Batch -2 (LV Unit Enclosure cover) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10749 | Component approval for Batch -2 (LV Unit Enclosure base) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10759 | Component approval for Batch -2 (LV Unit Busbars) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10865 | Component approval for Batch -2 (Enclosure Separators) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10874 | Component approval for Batch -2 (Enclosure Back plate) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10884 | Component approval for Batch -2 (Enclosure Fan) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10894 | Component approval for Batch -2 (Enclosure Front plate) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10904 | Component approval for Batch -2 (Enclosure Planum) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10914 | Component approval for Batch -2 (Enclosure Base plate) | Mechanics(1) | N | 2025-12-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9884 | Mech assembly wiring approval for Integration | Utility(1) | N | 2025-12-30 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11359 | Mega Inverter APC - block 5 compliance | SW(1) | N | 2026-01-12 |  | NS | 100d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11444 | Block 4 - Mega INV close loop version | SW(1) | N | 2026-01-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11583 | Sanity test (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-01-26 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 4334 | SMT (Batch -2) | Jabil(1) | N | 2026-01-26 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 4335 | SMT (Batch -2) | Jabil(1) | N | 2026-01-26 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11584 | Low voltage assemblies (MCU, VMU, AUX) (First Mega INV setup) | Utility(1) | N | 2026-02-16 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 4336 | Shipment (Batch -2 (25 Cells)) | Jabil(1) | N | 2026-02-16 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 9878 | Shipment (Batch -2 (25 Cells)) | Jabil(1) | N | 2026-02-16 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 5234 | PCB Unified test (Batch -2) | Ops(1) | N | 2026-02-23 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11585 | Power train PKMK (standalone) (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-03-02 | shani.a | NS | 40d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10060 | Sub Assembly MV (Batch -2) #1 | Mechanics(1) | N | 2026-03-02 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10061 | Sub Assembly LV (Batch -2) #1 | Mechanics(1) | N | 2026-03-02 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10062 | Sub Assembly (Batch -2) #1 | Mechanics(1) | N | 2026-03-02 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10059 | MV Units testing (Batch -2) #1 | Mechanics(1) | N | 2026-03-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10063 | LV Units testing (Batch -2) #1 | Mechanics(1) | N | 2026-03-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10066 | Sub Assembly MV (Batch -2) #2 | Mechanics(1) | N | 2026-03-09 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10067 | Sub Assembly LV (Batch -2) #2 | Mechanics(1) | N | 2026-03-09 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10064 | MV Units testing (Batch -2) #2 | Mechanics(1) | N | 2026-03-11 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10065 | LV Units testing (Batch -2) #2 | Mechanics(1) | N | 2026-03-11 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10072 | Sub Assembly MV (Batch -2) #3 | Ops(1) | N | 2026-03-11 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10073 | Sub Assembly LV (Batch -2) #3 | Ops(1) | N | 2026-03-11 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5315 | Open cell automation tests (Batch -2) #2 | Mechanics(1) | N | 2026-03-13 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10070 | MV Units testing (Batch -2) #3 | Ops(1) | N | 2026-03-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10071 | LV Units testing (Batch -2) #3 | Ops(1) | N | 2026-03-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10078 | Sub Assembly MV (Batch -2) #4 | Ops(1) | N | 2026-03-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10079 | Sub Assembly LV (Batch -2) #4 | Ops(1) | N | 2026-03-13 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5301 | Open cell automation tests (Batch -2) #1 | Mechanics(1) | N | 2026-03-16 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5342 | Open cell automation tests (Batch -2) #3 | Ops(1) | N | 2026-03-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10076 | MV Units testing (Batch -2) #4 | Ops(1) | N | 2026-03-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10077 | LV Units testing (Batch -2) #4 | Ops(1) | N | 2026-03-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10084 | Sub Assembly MV (Batch -2) #5 | Ops(1) | N | 2026-03-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10085 | Sub Assembly LV (Batch -2) #5 | Ops(1) | N | 2026-03-17 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5350 | Open cell automation tests (Batch -2) #4 | Ops(1) | N | 2026-03-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10082 | MV Units testing (Batch -2) #5 | Ops(1) | N | 2026-03-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10083 | LV Units testing (Batch -2) #5 | Ops(1) | N | 2026-03-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10090 | Sub Assembly MV (Batch -2) #6 | Ops(1) | N | 2026-03-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10091 | Sub Assembly LV (Batch -2) #6 | Ops(1) | N | 2026-03-19 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2024-09-05 |  | Majoris - 1 Mega INV_04-04_14-52 | 11685 | Batch -2 - TLA (Cell #1) |  | N | 2026-03-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5300 | Batch -2 - TLA (Cell #1) | Mechanics(1) | N | 2026-03-23 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2024-09-05 | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10258 | Batch -2 - TLA (Cell #1) | Mechanics(1) | N | 2026-03-23 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5359 | Open cell automation tests (Batch -2) #5 | Ops(1) | N | 2026-03-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10088 | MV Units testing (Batch -2) #6 | Ops(1) | N | 2026-03-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10089 | LV Units testing (Batch -2) #6 | Ops(1) | N | 2026-03-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10095 | Sub Assembly MV (Batch -2) #7 | Ops(1) | N | 2026-03-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10096 | Sub Assembly LV (Batch -2) #7 | Ops(1) | N | 2026-03-23 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5370 | Open cell automation tests (Batch -2) #6 | Ops(1) | N | 2026-03-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10093 | MV Units testing (Batch -2) #7 | Ops(1) | N | 2026-03-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10094 | LV Units testing (Batch -2) #7 | Ops(1) | N | 2026-03-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10100 | Sub Assembly MV (Batch -2) #8 | Ops(1) | N | 2026-03-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10101 | Sub Assembly LV (Batch -2) #8 | Ops(1) | N | 2026-03-25 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5385 | Open cell automation tests (Batch -2) #7 | Ops(1) | N | 2026-03-27 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10098 | MV Units testing (Batch -2) #8 | Ops(1) | N | 2026-03-27 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10099 | LV Units testing (Batch -2) #8 | Ops(1) | N | 2026-03-27 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10105 | Sub Assembly MV (Batch -2) #9 | Ops(1) | N | 2026-03-27 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10106 | Sub Assembly LV (Batch -2) #9 | Ops(1) | N | 2026-03-27 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5314 | TLA (Batch -2) #2 | Mechanics(1) | N | 2026-03-30 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10069 | TLA (Batch -2) #2 | Mechanics(1) | N | 2026-03-30 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 8256 | Stand alone automation testing (Batch -2) #1 | Mechanics(1) | N | 2026-03-30 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5408 | Open cell automation tests (Batch -2) #8 | Ops(1) | N | 2026-03-31 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10103 | MV Units testing (Batch -2) #9 | Ops(1) | N | 2026-03-31 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10104 | LV Units testing (Batch -2) #9 | Ops(1) | N | 2026-03-31 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10110 | Sub Assembly MV (Batch -2) #10 | Ops(1) | N | 2026-03-31 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10111 | Sub Assembly LV (Batch -2) #10 | Ops(1) | N | 2026-03-31 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5343 | TLA (Batch -2) #3 | Ops(1) | N | 2026-04-01 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10075 | TLA (Batch -2) #3 | Ops(1) | N | 2026-04-01 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 8285 | Stand alone automation testing (Batch -2) #2 | Mechanics(1) | N | 2026-04-01 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5437 | Open cell automation tests (Batch -2) #9 | Ops(1) | N | 2026-04-02 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10108 | MV Units testing (Batch -2) #10 | Ops(1) | N | 2026-04-02 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10109 | LV Units testing (Batch -2) #10 | Ops(1) | N | 2026-04-02 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10115 | Sub Assembly MV (Batch -2) #11 | Ops(1) | N | 2026-04-02 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10116 | Sub Assembly LV (Batch -2) #11 | Ops(1) | N | 2026-04-02 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5351 | TLA (Batch -2) #4 | Ops(1) | N | 2026-04-03 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10081 | TLA (Batch -2) #4 | Ops(1) | N | 2026-04-03 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8287 | Stand alone automation testing (Batch -2) #3 | Ops(1) | N | 2026-04-03 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 8284 | Back 2 Back Tests (Batch -2) #2 | Mechanics(1) | N | 2026-04-03 | michael.ra | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 8255 | Back 2 Back Tests (Batch -2) #1 | Mechanics(1) | N | 2026-04-06 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5488 | Open cell automation tests (Batch -2) #10 | Ops(1) | N | 2026-04-06 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10113 | MV Units testing (Batch -2) #11 | Ops(1) | N | 2026-04-06 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10114 | LV Units testing (Batch -2) #11 | Ops(1) | N | 2026-04-06 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10120 | Sub Assembly MV (Batch -2) #12 | Ops(1) | N | 2026-04-06 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10121 | Sub Assembly LV (Batch -2) #12 | Ops(1) | N | 2026-04-06 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5360 | TLA (Batch -2) #5 | Ops(1) | N | 2026-04-07 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10086 | TLA (Batch -2) #5 | Ops(1) | N | 2026-04-07 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8289 | Stand alone automation testing (Batch -2) #4 | Ops(1) | N | 2026-04-07 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8286 | Back 2 Back Tests (Batch -2) #3 | Ops(1) | N | 2026-04-07 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5583 | Open cell automation tests (Batch -2) #11 | Ops(1) | N | 2026-04-08 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10118 | MV Units testing (Batch -2) #12 | Ops(1) | N | 2026-04-08 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10119 | LV Units testing (Batch -2) #12 | Ops(1) | N | 2026-04-08 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10125 | Sub Assembly MV (Batch -2) #13 | Ops(1) | N | 2026-04-08 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10126 | Sub Assembly LV (Batch -2) #13 | Ops(1) | N | 2026-04-08 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5371 | TLA (Batch -2) #6 | Ops(1) | N | 2026-04-09 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10092 | TLA (Batch -2) #6 | Ops(1) | N | 2026-04-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8291 | Stand alone automation testing (Batch -2) #5 | Ops(1) | N | 2026-04-09 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 8288 | Back 2 Back Tests (Batch -2) #4 | Ops(1) | N | 2026-04-09 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 5766 | Open cell automation tests (Batch -2) #12 | Ops(1) | N | 2026-04-10 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10123 | MV Units testing (Batch -2) #13 | Ops(1) | N | 2026-04-10 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10124 | LV Units testing (Batch -2) #13 | Ops(1) | N | 2026-04-10 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10130 | Sub Assembly MV (Batch -2) #14 | Ops(1) | N | 2026-04-10 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.r | Majoris - 1 Mega INV_04-04_14-52 | 10131 | Sub Assembly LV (Batch -2) #14 | Ops(1) | N | 2026-04-10 | shani.a | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 5386 | TLA (Batch -2) #7 | Ops(1) | N | 2026-04-13 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10097 | TLA (Batch -2) #7 | Ops(1) | N | 2026-04-13 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8293 | Stand alone automation testing (Batch -2) #6 | Ops(1) | N | 2026-04-13 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8290 | Back 2 Back Tests (Batch -2) #5 | Ops(1) | N | 2026-04-13 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 6125 | Open cell automation tests (Batch -2) #13 | Ops(1) | N | 2026-04-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10128 | MV Units testing (Batch -2) #14 | Ops(1) | N | 2026-04-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10129 | LV Units testing (Batch -2) #14 | Ops(1) | N | 2026-04-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10135 | Sub Assembly MV (Batch -2) #15 | Ops(1) | N | 2026-04-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10136 | Sub Assembly LV (Batch -2) #15 | Ops(1) | N | 2026-04-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 5409 | TLA (Batch -2) #8 | Ops(1) | N | 2026-04-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10102 | TLA (Batch -2) #8 | Ops(1) | N | 2026-04-15 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8292 | Back 2 Back Tests (Batch -2) #6 | Ops(1) | N | 2026-04-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8295 | Stand alone automation testing (Batch -2) #7 | Ops(1) | N | 2026-04-15 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 6836 | Open cell automation tests (Batch -2) #14 | Ops(1) | N | 2026-04-16 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10133 | MV Units testing (Batch -2) #15 | Ops(1) | N | 2026-04-16 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10134 | LV Units testing (Batch -2) #15 | Ops(1) | N | 2026-04-16 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10140 | Sub Assembly MV (Batch -2) #16 | Ops(1) | N | 2026-04-16 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10141 | Sub Assembly LV (Batch -2) #16 | Ops(1) | N | 2026-04-16 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 5438 | TLA (Batch -2) #9 | Ops(1) | N | 2026-04-17 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10107 | TLA (Batch -2) #9 | Ops(1) | N | 2026-04-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8559 | Mega INV Setup integration (after cell #6) | Utility(1) | N | 2026-04-17 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8297 | Stand alone automation testing (Batch -2) #8 | Ops(1) | N | 2026-04-17 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8294 | Back 2 Back Tests (Batch -2) #7 | Ops(1) | N | 2026-04-17 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8795 | Open cell automation tests (Batch -2) #15 | Ops(1) | N | 2026-04-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10138 | MV Units testing (Batch -2) #16 | Ops(1) | N | 2026-04-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10139 | LV Units testing (Batch -2) #16 | Ops(1) | N | 2026-04-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10145 | Sub Assembly MV (Batch -2) #17 | Ops(1) | N | 2026-04-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10146 | Sub Assembly LV (Batch -2) #17 | Ops(1) | N | 2026-04-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 5489 | TLA (Batch -2) #10 | Ops(1) | N | 2026-04-21 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10112 | TLA (Batch -2) #10 | Ops(1) | N | 2026-04-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8299 | Stand alone automation testing (Batch -2) #9 | Ops(1) | N | 2026-04-21 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8296 | Back 2 Back Tests (Batch -2) #8 | Ops(1) | N | 2026-04-21 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8806 | Open cell automation tests (Batch -2) #16 | Ops(1) | N | 2026-04-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10143 | MV Units testing (Batch -2) #17 | Ops(1) | N | 2026-04-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10144 | LV Units testing (Batch -2) #17 | Ops(1) | N | 2026-04-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10150 | Sub Assembly MV (Batch -2) #18 | Ops(1) | N | 2026-04-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10151 | Sub Assembly LV (Batch -2) #18 | Ops(1) | N | 2026-04-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 5584 | TLA (Batch -2) #11 | Ops(1) | N | 2026-04-23 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10117 | TLA (Batch -2) #11 | Ops(1) | N | 2026-04-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8301 | Stand alone automation testing (Batch -2) #10 | Ops(1) | N | 2026-04-23 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8298 | Back 2 Back Tests (Batch -2) #9 | Ops(1) | N | 2026-04-23 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 5767 | TLA (Batch -2) #12 | Ops(1) | N | 2026-04-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10122 | TLA (Batch -2) #12 | Ops(1) | N | 2026-04-24 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8817 | Open cell automation tests (Batch -2) #17 | Ops(1) | N | 2026-04-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10148 | MV Units testing (Batch -2) #18 | Ops(1) | N | 2026-04-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10149 | LV Units testing (Batch -2) #18 | Ops(1) | N | 2026-04-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10155 | Sub Assembly MV (Batch -2) #19 | Ops(1) | N | 2026-04-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10156 | Sub Assembly LV (Batch -2) #19 | Ops(1) | N | 2026-04-24 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8303 | Stand alone automation testing (Batch -2) #11 | Ops(1) | N | 2026-04-24 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11586 | Measurements quality PKMK (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-04-27 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8300 | Back 2 Back Tests (Batch -2) #10 | Ops(1) | N | 2026-04-27 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8302 | Back 2 Back Tests (Batch -2) #11 | Ops(1) | N | 2026-04-27 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 6126 | TLA (Batch -2) #13 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10127 | TLA (Batch -2) #13 | Ops(1) | N | 2026-04-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8828 | Open cell automation tests (Batch -2) #18 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10153 | MV Units testing (Batch -2) #19 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10154 | LV Units testing (Batch -2) #19 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10166 | Sub Assembly LV (Batch -2) #20 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10167 | Sub Assembly MV (Batch -2) #20 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8305 | Stand alone automation testing (Batch -2) #12 | Ops(1) | N | 2026-04-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 6837 | TLA (Batch -2) #14 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10132 | TLA (Batch -2) #14 | Ops(1) | N | 2026-04-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8839 | Open cell automation tests (Batch -2) #19 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10168 | LV Units testing (Batch -2) #20 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10169 | MV Units testing (Batch -2) #20 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10178 | Sub Assembly LV (Batch -2) #21 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10179 | Sub Assembly MV (Batch -2) #21 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8307 | Stand alone automation testing (Batch -2) #13 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8304 | Back 2 Back Tests (Batch -2) #12 | Ops(1) | N | 2026-04-30 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8796 | TLA (Batch -2) #15 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10137 | TLA (Batch -2) #15 | Ops(1) | N | 2026-05-04 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10170 | Open cell automation tests (Batch -2) #20 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10180 | LV Units testing (Batch -2) #21 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10181 | MV Units testing (Batch -2) #21 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10191 | Sub Assembly LV (Batch -2) #22 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10192 | Sub Assembly MV (Batch -2) #22 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8309 | Stand alone automation testing (Batch -2) #14 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8306 | Back 2 Back Tests (Batch -2) #13 | Ops(1) | N | 2026-05-04 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8807 | TLA (Batch -2) #16 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10142 | TLA (Batch -2) #16 | Ops(1) | N | 2026-05-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10182 | Open cell automation tests (Batch -2) #21 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10193 | LV Units testing (Batch -2) #22 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10194 | MV Units testing (Batch -2) #22 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10203 | Sub Assembly LV (Batch -2) #23 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10204 | Sub Assembly MV (Batch -2) #23 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8797 | Stand alone automation testing (Batch -2) #15 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8308 | Back 2 Back Tests (Batch -2) #14 | Ops(1) | N | 2026-05-06 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8818 | TLA (Batch -2) #17 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10147 | TLA (Batch -2) #17 | Ops(1) | N | 2026-05-08 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10195 | Open cell automation tests (Batch -2) #22 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10205 | LV Units testing (Batch -2) #23 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10206 | MV Units testing (Batch -2) #23 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10216 | Sub Assembly LV (Batch -2) #24 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10217 | Sub Assembly MV (Batch -2) #24 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8808 | Stand alone automation testing (Batch -2) #16 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8798 | Back 2 Back Tests (Batch -2) #15 | Ops(1) | N | 2026-05-08 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11587 | Trip tests PKMK (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-05-11 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8829 | TLA (Batch -2) #18 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10152 | TLA (Batch -2) #18 | Ops(1) | N | 2026-05-12 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10160 | Sub Assembly MV (Batch -2) #25 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10161 | Sub Assembly LV (Batch -2) #25 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10207 | Open cell automation tests (Batch -2) #23 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10218 | LV Units testing (Batch -2) #24 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10219 | MV Units testing (Batch -2) #24 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8819 | Stand alone automation testing (Batch -2) #17 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8809 | Back 2 Back Tests (Batch -2) #16 | Ops(1) | N | 2026-05-12 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8840 | TLA (Batch -2) #19 | Ops(1) | N | 2026-05-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10157 | TLA (Batch -2) #19 | Ops(1) | N | 2026-05-14 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10158 | MV Units testing (Batch -2) #25 | Ops(1) | N | 2026-05-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10159 | LV Units testing (Batch -2) #25 | Ops(1) | N | 2026-05-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10220 | Open cell automation tests (Batch -2) #24 | Ops(1) | N | 2026-05-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8830 | Stand alone automation testing (Batch -2) #18 | Ops(1) | N | 2026-05-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8820 | Back 2 Back Tests (Batch -2) #17 | Ops(1) | N | 2026-05-14 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10171 | TLA (Batch -2) #20 | Ops(1) | N | 2026-05-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10172 | TLA (Batch -2) #20 | Ops(1) | N | 2026-05-18 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8251 | Open cell automation tests (Batch -2) #25 | Ops(1) | N | 2026-05-18 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8841 | Stand alone automation testing (Batch -2) #19 | Ops(1) | N | 2026-05-18 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8831 | Back 2 Back Tests (Batch -2) #18 | Ops(1) | N | 2026-05-18 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10183 | TLA (Batch -2) #21 | Ops(1) | N | 2026-05-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10184 | TLA (Batch -2) #21 | Ops(1) | N | 2026-05-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10173 | Stand alone automation testing (Batch -2) #20 | Ops(1) | N | 2026-05-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8842 | Back 2 Back Tests (Batch -2) #19 | Ops(1) | N | 2026-05-20 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10196 | TLA (Batch -2) #22 | Ops(1) | N | 2026-05-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10197 | TLA (Batch -2) #22 | Ops(1) | N | 2026-05-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10185 | Stand alone automation testing (Batch -2) #21 | Ops(1) | N | 2026-05-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10174 | Back 2 Back Tests (Batch -2) #20 | Ops(1) | N | 2026-05-22 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3000 | Bring up + safety mechanism (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-05-25 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10208 | TLA (Batch -2) #23 | Ops(1) | N | 2026-05-26 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10209 | TLA (Batch -2) #23 | Ops(1) | N | 2026-05-26 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10198 | Stand alone automation testing (Batch -2) #22 | Ops(1) | N | 2026-05-26 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10186 | Back 2 Back Tests (Batch -2) #21 | Ops(1) | N | 2026-05-26 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10221 | TLA (Batch -2) #24 | Ops(1) | N | 2026-05-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10222 | TLA (Batch -2) #24 | Ops(1) | N | 2026-05-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10210 | Stand alone automation testing (Batch -2) #23 | Ops(1) | N | 2026-05-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10199 | Back 2 Back Tests (Batch -2) #22 | Ops(1) | N | 2026-05-28 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | CMS | 2024-11-14 |  | Majoris - 1 Mega INV_04-04_14-52 | 11686 | Batch -2 - TLA (Cell #25) |  | N | 2026-05-29 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 11425 | Block 5 - Integration testing (First Mega INV setup) | Utility(1) | N | 2026-06-01 | shani.a | NS | 60d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8252 | Batch -2 - TLA (Cell #25) | Ops(1) | N | 2026-06-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2024-11-14 | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 9877 | Batch -2 - TLA (Cell #25) | Ops(1) | N | 2026-06-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10223 | Stand alone automation testing (Batch -2) #24 | Ops(1) | N | 2026-06-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10211 | Back 2 Back Tests (Batch -2) #23 | Ops(1) | N | 2026-06-01 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11358 | Block 6 - Mega INV string OPT integration compliance version | SW(1) | N | 2026-06-01 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11445 | Block 5 - Mega INV APC version | SW(1) | N | 2026-06-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8311 | Stand alone automation testing (Batch -2) #25 | Ops(1) | N | 2026-06-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 10224 | Back 2 Back Tests (Batch -2) #24 | Ops(1) | N | 2026-06-03 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 4311 | Batch summary - action tracker (Batch -2) | Ops(1) | N | 2026-06-03 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8413 | Assembly instruction document (Batch -1 (40 Cells)) | Ops(1) | N | 2026-06-04 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8414 | BOM 100% (Batch -1 (40 Cells)) | Ops(1) | N | 2026-06-04 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8415 | BOM & Assembly instruction review (Batch -1 (40 Cells)) | Ops(1) | N | 2026-06-04 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8416 | LLI (Batch -1 (40 Cells)) | Ops(1) | N | 2026-06-04 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8417 | Shortage Report (Batch -1 (40 Cells)) | Ops(1) | N | 2026-06-04 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8418 | ECOs in Agile (Batch -1 (40 Cells)) | Ops(1) | N | 2026-06-04 |  | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | yossi.g | Majoris - 1 Mega INV_04-04_14-52 | 8419 | QnR PCB approval in line (Batch -1 (40 Cells)) | QnR(1) | N | 2026-06-04 | Dana.h, Elianna.z | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.J | Majoris - 1 Mega INV_04-04_14-52 | 8310 | Back 2 Back Tests (Batch -2) #25 | Ops(1) | N | 2026-06-05 |  | NS | 2d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2760 | Communication tests (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-06-08 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4313 | Unit for HW (Batch -2 Cell) | Utility(1) | N | 2026-06-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 5231 | HW Tests Cell level Complete (Batch -2) | Utility(1) | N | 2026-06-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10550 | PO Preperation Process + Sending (MV Unit Enclosure base) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10583 | PO Preparation Process + Sending (MV Unit Enclosure cover) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10641 | PO Preparation Process + Sending (MV Unit Heat sink) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10656 | PO Preparation Process + Sending (MV Unit Air duct) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10671 | PO Preparation Process + Sending (MV Unit Busbars) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10776 | PO Preparation Process + Sending (LV Unit Busbars) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10788 | PO Preparation Process + Sending (LV Unit Heat sink) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10800 | PO Preparation Process + Sending (LV Unit Enclosure cover) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10812 | PO Preparation Process + Sending (LV Unit Enclosure base) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10919 | PO Preparation Process + Sending (Enclosure Separators) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10931 | PO Preparation Process + Sending (Enclosure Fan) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10944 | PO Preparation Process + Sending (Enclosure Front plate) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10957 | PO Preparation Process + Sending (Enclosure Planum) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10970 | PO Preparation Process + Sending (Enclosure Base plate) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10983 | PO Preparation Process + Sending (Enclosure Back plate) | Mechanics(1) | N | 2026-06-09 | michael.ra | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Elianna.z | Majoris - 1 Mega INV_04-04_14-52 | 1721 | Aging (TC) minimal for GA | QnR(1) | N | 2026-06-09 | Dana.h | NS | 21d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Elianna.z | Majoris - 1 Mega INV_04-04_14-52 | 1722 | HALT | QnR(1) | N | 2026-06-09 | Dana.h | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | ATE | Majoris - 1 Mega INV_04-04_14-52 | 3933 | ATE readiness for batch -1 | ATE(1) | N | 2026-06-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 4344 | Unit for ATE (Batch -2 Cell) | Utility(1) | N | 2026-06-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8784 | Unit for QnR (Batch -2 Cell) | Utility(1) | N | 2026-06-09 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3001 | power train tests PKMK (grid compliance) (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-06-15 | shani.a | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10551 | Sending PO (MV Unit Enclosure base) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10584 | Sending PO (MV Unit Enclosure cover) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10642 | Sending PO (MV Unit Heat sink) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10657 | Sending PO (MV Unit Air duct) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10672 | Sending PO (MV Unit Busbars) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10777 | Sending PO (LV Unit Busbars) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10789 | Sending PO (LV Unit Heat sink) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10801 | Sending PO (LV Unit Enclosure cover) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10813 | Sending PO (LV Unit Enclosure base) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10920 | Sending PO (Enclosure Separators) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10932 | Sending PO (Enclosure Fan) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10945 | Sending PO (Enclosure Front plate) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10958 | Sending PO (Enclosure Planum) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10971 | Sending PO (Enclosure Base plate) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10984 | Sending PO (Enclosure Back plate) | Mechanics(1) | N | 2026-06-16 | michael.ra | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  | Ofer.E | Majoris - 1 Mega INV_04-04_14-52 | 11316 | QnR System integration | QnR(1) | N | 2026-06-16 | Dana.h, Elianna.z | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10552 | PO Approved & Send to Production (MV Unit Enclosure base) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10585 | PO Approved & Send to Production (MV Unit Enclosure cover) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10643 | PO Approved & Send to Production (MV Unit Heat sink) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10658 | PO Approved & Send to Production (MV Unit Air duct) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10673 | PO Approved & Send to Production (MV Unit Busbars) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10778 | PO Approved & Send to Production (LV Unit Busbars) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10790 | PO Approved & Send to Production (LV Unit Heat sink) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10802 | PO Approved & Send to Production (LV Unit Enclosure cover) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10814 | PO Approved & Send to Production (LV Unit Enclosure base) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10921 | PO Approved & Send to Production (Enclosure Separators) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10933 | PO Approved & Send to Production (Enclosure Fan) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10946 | PO Approved & Send to Production (Enclosure Front plate) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10959 | PO Approved & Send to Production (Enclosure Planum) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10972 | PO Approved & Send to Production (Enclosure Base plate) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10985 | PO Approved & Send to Production (Enclosure Back plate) | Mechanics(1) | N | 2026-06-17 | michael.ra | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Full Kit Test CCGAN-2483 | 1 | T1 | Civil(1) | Y | 2026-06-23 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | FK transitions Project | 14 | Project End |  | Y* | 2026-06-24 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | SNET |  |  | FK status Project | 1 | Task1 | Default(1) | Y | 2026-06-26 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | FK status Project | 7 | Project End |  | N | 2026-06-29 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 3 | 1 | T1 | Default(1) | Y | 2026-07-01 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10556 | Samples Production & shipment (MV Unit Enclosure base) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10589 | Samples Production & shipment (MV Unit Enclosure cover) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10647 | Samples Production & shipment (MV Unit Heat sink) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 10662 | Samples Production & shipment (MV Unit Air duct) | Jabil(1) | N | 2026-07-01 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10677 | Samples Production & shipment (MV Unit Busbars) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10782 | Samples Production & shipment (LV Unit Busbars) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10794 | Samples Production & shipment (LV Unit Heat sink) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10806 | Samples Production & shipment (LV Unit Enclosure cover) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10818 | Samples Production & shipment (LV Unit Enclosure base) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10925 | Samples Production & shipment (Enclosure Separators) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10937 | Samples Production & shipment (Enclosure Fan) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10950 | Samples Production & shipment (Enclosure Front plate) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10963 | Samples Production & shipment (Enclosure Planum) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10976 | Samples Production & shipment (Enclosure Base plate) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10989 | Samples Production & shipment (Enclosure Back plate) | Jabil(1) | N | 2026-07-01 | michael.ra | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ERP en ABC | 16 | Modelamiento de COMPRAS & INVENTARIO | Experto de Procesos(1) | N | 2026-07-03 |  | NS | 11d |  |  |  |  | Fiallos | 11d | Network | 1 | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3006 | Thermal tests PKMK (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-07-06 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11420 | Block 7 - Mega INV site level integration compliance version | SW(1) | N | 2026-07-06 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11446 | Block 6 - Mega INV string OPT integration version | SW(1) | N | 2026-07-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Aaron Martin | Test Automation Project 1 | 5 | Default Phase | CFD Group(1) | Y | 2026-07-08 | Aaron Wilbur | NS | 5d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  | acabrera | Test Automation Project 1 | 11 | T3 | CFD Group(1) | Y | 2026-07-08 | ahults | NS | 10d |  |  |  |  | ResAdmin1 |  | Volume of Work |  | 0
R | PT |  |  | Test Automation Project 1 | 3 | PT-Task | CFD Group(1) | Y | 2026-07-08 |  | NS | 2026-07-08 |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Test Automation Project 2 | 1 | T1 | Default(1) | Y | 2026-07-09 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation_FK_Pred_Test | 2 | Task | Default(1) | N | 2026-07-10 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
G |  |  |  | FK Automation Project | 2 | Task1SFK | Default(1) | N | 2026-07-10 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | PE |  |  | Automation_FK_Pred_Test | 6 | Project End |  | N | 2026-07-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2706 | HW Batch -2 approval - full automation (First Mega INV setup) | Utility(1) | N | 2026-07-13 | shani.a | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 2757 | EMC Testing PKMK (after Batch -2) (First Mega INV setup) | Utility(1) | N | 2026-07-13 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | FK Automation Project | 4 | Project End |  | N | 2026-07-13 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R |  |  |  | Full Kit Test CCGAN-2483 | 8 | T2 | Default(1) | N | 2026-07-14 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Automation Project ReadyToStart | 1 | Task1 | Default(1) | Y | 2026-07-14 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Test Automation Project 3 | 2 | T2 | Default(1) | N | 2026-07-15 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation Project ReadyToStart | 9 | Task4 | Default(1) | Y | 2026-07-15 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Gama2 | 1 | t1 | A(0.5), B(0.5) | Y | 2026-07-16 | admin | NS | 1d |  |  |  |  | Gama | 2d | Network | 0 | 0
R |  |  |  | Automation Project ReadyToStart | 13 | Task8 | Default(1) | Y | 2026-07-16 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation Project InlineEdit_DD1 | 1 | Task1 | Default(1) | Y | 2026-07-16 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation_Test_Status_Update_Project | 4 | Status Automation - 2 | Default(1) | Y | 2026-07-16 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
G |  |  |  | Automation_Test_Status_Update_Project | 1 | Status Automation - 1 | Default(1) | Y | 2026-07-16 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
G |  |  |  | Automation Project InlineEdit_DD2 | 1 | Task1 | Default(1) | Y | 2026-07-16 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | PE |  |  | Automation_Test_Status_Update_Project | 13 | Project End |  | N | 2026-07-16 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Automation Project ReadyToStart | 10 | Task5 | Default(1) | N | 2026-07-17 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation Project InlineEdit_DD1 | 7 | Test3 | Default(1) | Y | 2026-07-17 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project Checklist_FieldOps | 1 | Task1 | Default(1) | Y | 2026-07-17 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project_ErrorAndNotifications | 1 | Task1 | Default(1) | Y | 2026-07-17 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project InlineEdit_DD2 | 7 | Task3 | Default(1) | Y | 2026-07-17 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G | CMS | 2026-07-17 |  | Automation_Test_Status_Update_Project | 11 | Completion Milestone |  | N | 2026-07-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ERP en ABC | 17 | Datos Maestros de COMPRAS & INVENTARIO | Experto de Procesos(1) | N | 2026-07-20 |  | NS | 36d |  |  |  |  | Fiallos | 36d | Network | 1 | 0
R |  |  |  | Automation_Checklst_Project | 1 | T1 | Default(1) | Y | 2026-07-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Automation Project ReadyToStart | 14 | Task9 | Default(1) | N | 2026-07-20 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project QuickAccess_RunBM_2 | 1 | Task1 | Default(1) | Y | 2026-07-20 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project_ErrorAndNotifications | 2 | Task2 | Default(1) | N | 2026-07-20 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project Checklist_FieldOps | 2 | Task2 | Default(1) | N | 2026-07-20 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project Subtask_Structure | 8 | Task2 | Default(1) | N | 2026-07-20 |  | NS | 1d |  |  |  |  | ResAdmin1 | 1d | Network | 1 | 0
R |  |  |  | Automation_Checklst_Project | 2 | T2 | Default(1) | N | 2026-07-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Automation Project ReadyToStart | 12 | Task7 | Default(1) | Y* | 2026-07-21 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | test6578 | 1 | t1 | Default(1) | Y | 2026-07-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Automation_HelpNeeded_Project | 1 | HelpNeed Task | Default(1) | Y | 2026-07-21 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Automation Project QuickAccess_RunBM_2 | 2 | Task2 | Default(1) | N | 2026-07-21 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project_ErrorAndNotifications | 3 | Task3 | Default(1) | N | 2026-07-21 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G |  |  |  | Automation Project Checklist_FieldOps | 3 | Task3 | Default(1) | N | 2026-07-21 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | PE |  |  | Automation_Checklst_Project | 4 | Project End |  | N | 2026-07-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Automation Project ReadyToStart | 4 | Project End |  | N | 2026-07-21 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R | PE |  |  | test6578 | 4 | Project End |  | N | 2026-07-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Automation_HelpNeeded_Project | 5 | Project End |  | N | 2026-07-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | ahande | Test Automation Project 1 | 8 | T2 | CFD Group(1) | N | 2026-07-22 | aackmann | NS | 5d |  |  |  |  | ResAdmin1 | 5d | WIP | 0 | 0
R |  |  |  | Automation Project QuickAccess_RunBM | 1 | Task1 | Default(1) | Y | 2026-07-22 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Test Automation Project 1 | 12 | St1 | CFD Group(1) | N | 2026-07-22 |  | NS | 5d |  |  |  |  | ResAdmin1 | 5d | Network | 1 | 0
G |  |  |  | Automation Project QuickAccess_RunBM_2 | 3 | Task3 | Default(1) | N | 2026-07-22 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G | CMS | 2026-07-22 |  | test6578 | 2 | Completion Milestone |  | N | 2026-07-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | CMS | 2026-07-22 |  | Automation_HelpNeeded_Project | 3 | Completion Milestone |  | Y* | 2026-07-22 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 2 | 2 | T2 | Default(1) | N | 2026-07-23 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation Project QuickAccess_RunBM | 2 | Task2 | Default(1) | N | 2026-07-23 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | PE |  |  | automation_test_10158 | 4 | Project End |  | N | 2026-07-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Automation Project InlineEdit_DD1 | 4 | Project End |  | N | 2026-07-23 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
G | PE |  |  | Automation Project Checklist_FieldOps | 5 | Project End |  | N | 2026-07-23 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
G | PE |  |  | Automation Project_ErrorAndNotifications | 5 | Project End |  | N | 2026-07-23 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R |  |  |  | Automation Project QuickAccess_RunBM | 3 | Task3 | Default(1) | N | 2026-07-24 |  | NS | 1d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | PE |  |  | Gama2 | 3 | Project End |  | N | 2026-07-24 |  | NS | 0d |  |  |  |  | Gama |  |  |  | 0
R | PE |  |  | Automation Project QuickAccess_RunBM | 5 | Project End |  | N | 2026-07-24 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
G | PE |  |  | Automation Project QuickAccess_RunBM_2 | 5 | Project End |  | N | 2026-07-24 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 3349 | HW Tests after Batch -2 (First Mega INV setup) | Utility(1) | N | 2026-07-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 9023 | Unit for Integration (First Mega INV setup after Batch -2) | Utility(1) | N | 2026-07-27 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Automation Project Subtask_Structure | 29 | Task7 | Default(1) | Y* | 2026-07-27 |  | NS | 1d |  |  |  |  | ResAdmin1 | 1d | Network | 1 | 0
R | PE |  |  | Test Automation Project 1 | 18 | Project End |  | N | 2026-07-28 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R | IMS SNET | 2024-03-04 |  | Test Automation Project 1 | 15 | Internal Milestone |  | Y* | 2026-07-28 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R | CMS | 2024-03-04 |  | Test Automation Project 1 | 16 | Completion Milestone |  | N | 2026-07-28 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
G | PE |  |  | Automation Project InlineEdit_DD2 | 4 | Project End |  | N | 2026-07-28 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R |  |  |  | Test Automation Project 3 | 3 | T3 | Default(1) | N | 2026-07-29 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 5193 | Mech Readiness (Batch -1) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10559 | Component approval for Batch -1 | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10592 | Component approval for Batch -1 (MV Unit Enclosure cover) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10650 | Component approval for Batch -1 (MV Unit Heat sink) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10665 | Component approval for Batch -1 (MV Unit Air duct) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10680 | Component approval for Batch -1 (MV Unit Busbars) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10785 | Component approval for Batch -1 (LV Unit Busbars) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10797 | Component approval for Batch -1 (LV Unit Heat sink) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10809 | Component approval for Batch -1 (LV Unit Enclosure cover) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10821 | Component approval for Batch -1 (LV Unit Enclosure base) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10928 | Component approval for Batch -1 (Enclosure Separators) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10940 | Component approval for Batch -1 (Enclosure Fan) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10953 | Component approval for Batch -1 (Enclosure Front plate) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10966 | Component approval for Batch -1 (Enclosure Planum) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10979 | Component approval for Batch -1 (Enclosure Base plate) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yuval.K | Majoris - 1 Mega INV_04-04_14-52 | 10992 | Component approval for Batch -1 (Enclosure Back plate) | Mechanics(1) | N | 2026-07-29 | michael.ra | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Automation Project Subtask_Structure | 35 | Task9 | Default(1) | Y* | 2026-07-29 |  | NS | 3d |  |  |  |  | ResAdmin1 | 3d | WIP | 1 | 0
R |  |  |  | Automation_General_UI_TEST | 1 | FullKit Task Data | Default(1) | N | 2026-07-30 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Automation_Test_101518 | 1 | Task | Default(1) | Y | 2026-07-30 |  | NS | 5d |  |  |  |  | Concerto Admin | 5d | Network | 1 | 0
R | PE |  |  | Automation_General_UI_TEST | 4 | Project End |  | N | 2026-07-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | Automation_Checklist_Test_FK | 3 | Project End |  | N | 2026-07-31 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | Automation Project Subtask_Structure | 25 | Task6 | Default(1) | Y* | 2026-08-03 |  | NS | 3d |  |  |  |  | ResAdmin1 | 3d | Network | 1 | 0
R | PE |  |  | Full Kit Test CCGAN-2483 | 4 | Project End |  | N | 2026-08-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | AutomationFilterConfigTestProject | 3 | Project End |  | N | 2026-08-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | Automation_Test_101518 | 5 | Project End |  | N | 2026-08-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | Automation_LoggedInUserTest | 3 | Project End |  | N | 2026-08-04 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 2 | 3 | T3 | Default(1) | N | 2026-08-06 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | Automation_FKStatusTransitionProject | 2 | task | Default(1) | N | 2026-08-06 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Automation Project Subtask_Structure | 40 | Task10 | Default(1) | N | 2026-08-06 |  | NS | 3d |  |  |  |  | ResAdmin1 | 3d | WIP | 1 | 0
R | PE |  |  | Automation_FKStatusTransitionProject | 4 | Project End |  | N | 2026-08-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | AutomationTaskDocumentTestProject | 3 | Project End |  | N | 2026-08-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | Automation_Fk_Completion_Status | 3 | Project End |  | N | 2026-08-07 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11421 | Block 8 - Mega INV grid compliance integration compliance version | SW(1) | N | 2026-08-10 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11447 | Block 7 - Mega INV site level integration version | SW(1) | N | 2026-08-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | AutomationCustomTestProject | 3 | Project End |  | N | 2026-08-10 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | AutomationFilterPanelProjectTest | 3 | Project End |  | N | 2026-08-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 3 | 4 | T4 | Default(1) | N | 2026-08-12 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  | mmassa | DP273 | 29 | Sleeve Install, Turn Sleeves & Inspect | Weld_Multi(1) | N | 2026-08-13 |  | NS | 89d 7.5h |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | AutomationGridPercentCompProject | 3 | Project End |  | N | 2026-08-13 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | Automation_Test_101580 | 5 | Project End |  | N | 2026-08-17 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | AutomationRealTimeUpdateProject | 2 | Task | Default(1) | N | 2026-08-18 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | PE |  |  | AutomationRealTimeUpdateProject | 5 | Project End |  | N | 2026-08-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | AutomatiionFullKitDetailPopUpProject | 2 | CI | Default(1) | N | 2026-08-19 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | Automation Project Subtask_Structure | 5 | Project End |  | N | 2026-08-19 |  | NS | 0d |  |  |  |  | ResAdmin1 |  |  |  | 0
R |  |  |  | Test Automation Project 2 | 4 | T4 | Default(1) | N | 2026-08-20 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | AutomatiionFullKitDetailPopUpProject | 3 | Docker | Default(1) | N | 2026-08-20 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | IMS | 2026-08-20 |  | AutomatiionFullKitDetailPopUpProject | 4 | Internal Milestone | Default(1) | N | 2026-08-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | AutomatiionFullKitDetailPopUpProject | 6 | Project End |  | N | 2026-08-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | TestPlaywrightMcpProject | 3 | Project End |  | N | 2026-08-20 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | CMS | 2025-01-22 |  | Majoris - 1 Mega INV_04-04_14-52 | 11689 | Integration Readiness |  | N | 2026-08-21 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | IMS | 2025-01-22 | gal.k | Majoris - 1 Mega INV_04-04_14-52 | 3389 | Integration Readiness | Integration(1) | N | 2026-08-24 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Gal.K | Majoris - 1 Mega INV_04-04_14-52 | 8561 | Automation development | Integration(1) | N | 2026-08-24 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8421 | SMT (Batch -1 (40 Cells)) | Ops(1) | N | 2026-08-24 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Inbar.j | Majoris - 1 Mega INV_04-04_14-52 | 8422 | SMT (Batch -1 (40 Cells)) | Ops(1) | N | 2026-08-24 |  | NS | 15d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8683 | PCB MP order before Batch -1 (40 Cells) | Utility(1) | N | 2026-08-24 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
G | PE |  |  | Test_Automation_Project_Task_101577 | 5 | Project End |  | N | 2026-08-25 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 3 | 5 | T5 | Default(1) | N | 2026-08-26 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | IMS | 2022-06-07 | PS | T44_February_2019 2Tier | 3292 | IMS-Release to A0=Induction |  | Y | 2026-08-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  |  | T44_February_2019 2Tier | 3393 | Induction | 629_ACM(1), 629_AE(1), 629_ASI(2), 629_E&E(1) | N | 2026-08-27 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d | Network | 0 | 0
R | IMS | 2022-06-11 | PS | AutomationChainPanrlSelectionProject | 3292 | IMS-Release to A0=Induction |  | Y | 2026-08-27 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  |  | AutomationChainPanrlSelectionProject | 3393 | Induction | 629_ACM(1), 629_AE(1), 629_ASI(2), 629_E&E(1) | N | 2026-08-27 |  | NS | 2d |  |  |  |  | Concerto Admin | 2d | Network | 0 | 0
R |  |  |  | AutomationTaskEditingFieldProject | 2 | Playwright | Default(1) | N | 2026-08-27 |  | NS | 1d |  |  |  | Awaiting QA | Concerto Admin | 1d | Network | 1 | 0
R |  |  |  | Automation_UILayout | 1 | Task | Default(1) | Y | 2026-08-28 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R |  |  |  | AutomationTaskEditingFieldProject | 6 | BDD Framework | Default(1) | N | 2026-08-28 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | IMS | 2022-06-09 | PS | T44_February_2019 2Tier | 2767 | IMS-Release to B0=Pre-Strip Disassembly |  | N | 2026-08-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R | IMS | 2022-06-13 | PS | AutomationChainPanrlSelectionProject | 2767 | IMS-Release to B0=Pre-Strip Disassembly |  | N | 2026-08-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R | IMS | 2026-08-29 |  | Automation_UILayout | 4 | Internal Milestone |  | N | 2026-08-28 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | T44_February_2019 2Tier | 3429 | Pre-Strip | 629_ACM(2.5), 629_AE(0.5), 629_SMM(0.5) | N | 2026-08-31 |  | NS | 4d |  |  |  |  | Concerto Admin | 4d | Network | 0 | 0
R |  |  |  | AutomationChainPanrlSelectionProject | 3429 | Pre-Strip | 629_ACM(2.5), 629_AE(0.5), 629_SMM(0.5) | N | 2026-08-31 |  | NS | 4d |  |  |  |  | Concerto Admin | 4d | Network | 0 | 0
R | PT |  |  | Automation_UILayout | 12 | PT-Task | Default(1) | Y | 2026-08-31 |  | NS | 2026-08-25 |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | AutomationEntryPointAccess | 1 | task | Default(1) | Y | 2026-08-31 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | IMS | 2026-08-28 |  | AutomationTaskEditingFieldProject | 8 | Internal Milestone | Default(1) | N | 2026-08-31 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | AutomationTaskEditingFieldProject | 9 | API | Default(1) | N | 2026-08-31 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | PE |  |  | Automation_UILayout | 14 | Project End |  | N | 2026-08-31 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | IMS | 2026-09-01 |  | AutomationEntryPointAccess | 13 | Internal Milestone | Default(1) | N | 2026-08-31 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | AutomationEntryPointAccess | 4 | task | Default(1) | N | 2026-09-01 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R |  |  |  | Automation_UILayout | 5 | task2 | Default(1) | N | 2026-09-01 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | PE |  |  | AutomationTaskEditingFieldProject | 12 | Project End |  | N | 2026-09-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | AutomationEntryPointAccess | 8 | Project End |  | N | 2026-09-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | IMS | 2026-08-29 |  | Automation_UILayout | 8 | Internal Milestone | Default(1) | N | 2026-09-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Automation_UILayout | 9 | task3 | Default(1) | N | 2026-09-02 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | CMS | 2026-08-29 |  | Automation_UILayout | 11 | Completion Milestone |  | N | 2026-09-02 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 2 | 5 | T5 | Default(1) | N | 2026-09-03 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R | IMS | 2022-06-15 | PS | T44_February_2019 2Tier | 2768 | IMS-Release to C0=Strip & Prime | Hold(1) | N | 2026-09-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R | IMS | 2022-06-19 | PS | AutomationChainPanrlSelectionProject | 2768 | IMS-Release to C0=Strip & Prime | Hold(1) | N | 2026-09-03 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 1
R |  |  |  | T44_February_2019 2Tier | 3394 | Strip & Prime | Painters_A/C(0.6), Strip_Shop(1.7) | N | 2026-09-04 |  | NS | 14d |  |  |  |  | Concerto Admin | 14d | Network | 0 | 0
R |  |  |  | AutomationChainPanrlSelectionProject | 3394 | Strip & Prime | Painters_A/C(0.6), Strip_Shop(1.7) | N | 2026-09-04 |  | NS | 14d |  |  |  |  | Concerto Admin | 14d | Network | 0 | 0
R |  |  |  | Automation_Edit_Checkout_Validation | 2 | Task | Default(1) | N | 2026-09-07 |  | NS | 1d |  |  |  |  | Concerto Admin |  | Network |  | 0
R | PE |  |  | Automation_Edit_Checkout_Validation | 4 | Project End |  | N | 2026-09-07 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | ERP en ABC | 29 | Pruebas Unitarias y Entrenamiento de COMPRAS & INVENTARIO | Experto de Procesos(1) | N | 2026-09-08 |  | NS | 15d |  |  |  |  | Fiallos | 15d | Network | 1 | 0
R |  |  |  | Test Automation Project 3 | 6 | T6 | Default(1) | N | 2026-09-09 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | AutomationPrivilegeTest | 1 | test | Default(1) | Y | 2026-09-09 |  | NS | 1d |  |  |  |  | PMUser |  | Network |  | 0
R |  |  |  | Automation_Privilege_Admin | 1 | Task | Default(1) | Y | 2026-09-09 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
R | IMS | 2026-09-10 |  | AutomationPrivilegeTest | 2 | Internal Milestone | Default(1) | N | 2026-09-09 |  | NS | 0d |  |  |  |  | PMUser |  |  |  | 0
R | IMS | 2026-09-10 |  | Automation_Privilege_Admin | 4 | Internal Milestone | Default(1) | N | 2026-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | Automation_Privilege_Admin | 6 | Project End |  | N | 2026-09-09 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PT |  |  | AutomationPrivilegeTest | 3 | PT-Task | Default(1) | N | 2026-09-10 |  | NS | 2026-09-08 |  |  |  |  | PMUser |  | Network |  | 0
R |  |  |  | AutomationPrivilegeTest | 4 | task | Default(1) | N | 2026-09-11 |  | NS | 1d |  |  |  |  | PMUser | 1d | Network | 1 | 0
R | PE |  |  | AutomationPrivilegeTest | 8 | Project End |  | N | 2026-09-11 |  | NS | 0d |  |  |  |  | PMUser |  |  |  | 0
G | PE |  |  | AutomationInlineUpdateProject | 3 | Project End |  | N | 2026-09-11 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11422 | Block 9 - Mega INV migration to container compliance version | SW(1) | N | 2026-09-14 |  | NS | 25d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Foster | Majoris - 1 Mega INV_04-04_14-52 | 11448 | Block 8 - Mega INV grid compliance integration version | SW(1) | N | 2026-09-14 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8424 | Unified test (Batch -1 (40 Cells)) | Utility(1) | N | 2026-09-14 | shani.a | NS | 5d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Ania.Z | Majoris - 1 Mega INV_04-04_14-52 | 10524 | Certification Automation preparation | Certification(1) | N | 2026-09-14 |  | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Test Automation Project 2 | 6 | T6 | Default(1) | N | 2026-09-17 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  |  | AutomationEditNetworkProject | 1 | Task | Default(1) | Y | 2026-09-18 |  | NS | 1d |  |  | db-persist-check-1789727793246 |  | Concerto Admin | 1d | Network | 1 | 0
R | PE |  |  | AutomationNewUIConfigProject | 3 | Project End |  | N | 2026-09-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R | PE |  |  | AutomationEditNetworkProject | 5 | Project End |  | N | 2026-09-18 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  | gal.k | Majoris - 1 Mega INV_04-04_14-52 | 110 | Integration Acceptance Tests | Integration(1) | N | 2026-09-21 |  | NS | 3d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8426 | Sub Assembly (Batch -1 (Phase 1 - 10 Cells)) | Utility(1) | N | 2026-09-21 | shani.a | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8660 | Sub Assembly MV (Batch -1 (Phase 1 - 10 Cells)) | Utility(1) | N | 2026-09-21 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  | Yacov.R | Majoris - 1 Mega INV_04-04_14-52 | 8661 | Sub Assembly LV (Batch -1 (Phase 1 - 10 Cells)) | Utility(1) | N | 2026-09-21 | shani.a | NS | 20d |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | Test Automation Project 3 | 7 | T7 | Default(1) | N | 2026-09-23 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
R |  |  | PS | T44_February_2019 2Tier | 1954 | IMS-Release to D0=Post Strip Disassembly | Hold(1) | N | 2026-09-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  | PS | AutomationChainPanrlSelectionProject | 1954 | IMS-Release to D0=Post Strip Disassembly | Hold(1) | N | 2026-09-23 |  | NS | 0d |  |  |  |  | Concerto Admin |  | Network |  | 1
R |  |  |  | T44_February_2019 2Tier | 1908 | Post Strip Disassembly | 629_ACM(3.8), 629_AE(1.5) | N | 2026-09-24 |  | NS | 14d |  |  |  |  | Concerto Admin | 14d | Network | 0 | 0
R |  |  |  | AutomationChainPanrlSelectionProject | 1908 | Post Strip Disassembly | 629_ACM(3.8), 629_AE(1.5) | N | 2026-09-24 |  | NS | 14d |  |  |  |  | Concerto Admin | 14d | Network | 0 | 0
R |  |  | gal.k | Majoris - 1 Mega INV_04-04_14-52 | 113 | Opt - Inverter integration | Integration(1) | N | 2026-09-24 |  | NS | 10d |  |  |  |  | Concerto Admin |  | Network |  | 0
G |  |  |  | Automation_MilestonePanel | 1 | Task1 | Default(1) | Y | 2026-09-24 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
G | IMS | 2026-10-01 |  | Automation_MilestonePanel | 4 | Internal Milestone | Default(1) | N | 2026-09-25 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G |  |  |  | Automation_MilestonePanel | 6 | Task2 | Default(1) | N | 2026-09-25 |  | NS | 1d |  |  |  |  | Concerto Admin | 1d | Network | 1 | 0
G | PT |  |  | Automation_MilestonePanel | 10 | PT-Task | Default(1) | N | 2026-09-28 |  | NS | 2026-09-30 |  |  |  |  | Concerto Admin |  | Network |  | 0
R |  |  |  | ERP en ABC | 40 | Pruebas de Integración | Experto de Procesos(1) | N | 2026-09-29 |  | NS | 15d |  |  |  |  | Fiallos | 15d | Network | 1 | 0
G | PE |  |  | Automation_MilestonePanel | 11 | Project End |  | N | 2026-09-30 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
R |  |  |  | Test Automation Project 2 | 7 | T7 | Default(1) | N | 2026-10-01 |  | NS | 10d |  |  |  |  | ResAdmin1 |  | Network |  | 0
G | CMS | 2026-10-01 |  | Automation_MilestonePanel | 5 | Completion Milestone |  | N | 2026-10-01 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0
G | PE |  |  | AutomationInlineGanttUpdateProject | 3 | Project End |  | N | 2026-10-06 |  | NS | 0d |  |  |  |  | Concerto Admin |  |  |  | 0